## لیست ECهای کانی مس
Activity ID | ECC NO. | EC NO. | Area | ECC | Discipline | Activity Name | Duration | Start | Finish | Start | Finish
021-LV Switchgear System (23S3-ECC-MCC-037) | 23S3-ECC-MCC-037 |  | 021 | MCC |  |  | 4 | 2019-11-06 | 2019-11-10 | 1398/08/15 | 1398/08/19
LV Switchgear System (21-EC-LVS-EL-001) | 23S3-ECC-MCC-037 | 021-EC-LVS-EL-001 | 021 | MCC | EL |  | 3 | 2019-11-06 | 2019-11-09 | 1398/08/15 | 1398/08/18
23S3-PC-021-EL-100 | 23S3-ECC-MCC-037 | 021-EC-LVS-EL-001 | 021 | MCC | EL | Panel installation final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-021-EL-105 | 23S3-ECC-MCC-037 | 021-EC-LVS-EL-001 | 021 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-021-EL-110 | 23S3-ECC-MCC-037 | 021-EC-LVS-EL-001 | 021 | MCC | EL | Earthing check, test and punch clearance | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-021-EL-120 | 23S3-ECC-MCC-037 | 021-EC-LVS-EL-001 | 021 | MCC | EL | CT/PT check and test | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-021-EL-130 | 23S3-ECC-MCC-037 | 021-EC-LVS-EL-001 | 021 | MCC | EL | Relay setting test | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
UPS & Battery System (21-EC-UPS-EL-002) | 23S3-ECC-MCC-037 | 021-EC-UPS-EL-002 | 021 | MCC | EL |  | 4 | 2019-11-06 | 2019-11-10 | 1398/08/15 | 1398/08/19
23S3-PC-021-EL-150 | 23S3-ECC-MCC-037 | 021-EC-UPS-EL-002 | 021 | MCC | EL | Panel installation final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-021-EL-155 | 23S3-ECC-MCC-037 | 021-EC-UPS-EL-002 | 021 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-021-EL-160 | 23S3-ECC-MCC-037 | 021-EC-UPS-EL-002 | 021 | MCC | EL | Earthing / lightening check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-021-EL-165 | 23S3-ECC-MCC-037 | 021-EC-UPS-EL-002 | 021 | MCC | EL | UPS check and punch clearance | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-021-EL-170 | 23S3-ECC-MCC-037 | 021-EC-UPS-EL-002 | 021 | MCC | EL | Relay setting test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
Heat tracing System (21-EC-HET-EL-003) | 23S3-ECC-MCC-037 | 021-EC-HET-EL-003 | 021 | MCC | EL |  | 3 | 2019-11-06 | 2019-11-09 | 1398/08/15 | 1398/08/18
23S3-PC-021-EL-200 | 23S3-ECC-MCC-037 | 021-EC-HET-EL-003 | 021 | MCC | EL | Panel installation and final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-021-EL-205 | 23S3-ECC-MCC-037 | 021-EC-HET-EL-003 | 021 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-021-EL-210 | 23S3-ECC-MCC-037 | 021-EC-HET-EL-003 | 021 | MCC | EL | Earthing / lightening check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
150-LV Switchgear System (23S3-ECC-MCC-038) | 23S3-ECC-MCC-038 |  | 150 | MCC |  |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
LV Switchgear System (150-EC-LVS-EL-001) | 23S3-ECC-MCC-038 | 150-EC-LVS-EL-001 | 150 | MCC | EL |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
23S3-PC-150-EL-100 | 23S3-ECC-MCC-038 | 150-EC-LVS-EL-001 | 150 | MCC | EL | Panel installation and final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-150-EL-105 | 23S3-ECC-MCC-038 | 150-EC-LVS-EL-001 | 150 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-150-EL-110 | 23S3-ECC-MCC-038 | 150-EC-LVS-EL-001 | 150 | MCC | EL | Earthing / lightening check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-150-EL-120 | 23S3-ECC-MCC-038 | 150-EC-LVS-EL-001 | 150 | MCC | EL | CT/PT check and test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-150-EL-130 | 23S3-ECC-MCC-038 | 150-EC-LVS-EL-001 | 150 | MCC | EL | Relay setting test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
200-LV Switchgear System (23S3-ECC-MCC-039) | 23S3-ECC-MCC-039 |  | 200 | MCC |  |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
LV Switchgear System (200-EC-LVS-EL-002) | 23S3-ECC-MCC-039 | 200-EC-LVS-EL-002 | 200 | MCC | EL |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
23S3-PC-200-EL-100 | 23S3-ECC-MCC-039 | 200-EC-LVS-EL-002 | 200 | MCC | EL | Panel installation and final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-200-EL-105 | 23S3-ECC-MCC-039 | 200-EC-LVS-EL-002 | 200 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-200-EL-110 | 23S3-ECC-MCC-039 | 200-EC-LVS-EL-002 | 200 | MCC | EL | Earthing / lightening check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-200-EL-120 | 23S3-ECC-MCC-039 | 200-EC-LVS-EL-002 | 200 | MCC | EL | CT/PT check and test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-200-EL-130 | 23S3-ECC-MCC-039 | 200-EC-LVS-EL-002 | 200 | MCC | EL | Relay setting test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
210-LV Switchgear System (23S3-ECC-MCC-040) | 23S3-ECC-MCC-040 |  | 210 | MCC |  |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
Earthing & Lightning (210-EC-EAT-EL-001) | 23S3-ECC-MCC-040 | 210-EC-EAT-EL-001 | 210 | MCC | EL |  | 4 | 2019-11-06 | 2019-11-10 | 1398/08/15 | 1398/08/19
23S3-PC-210-EL-100 | 23S3-ECC-MCC-040 | 210-EC-EAT-EL-001 | 210 | MCC | EL | Panel installation and final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-210-EL-105 | 23S3-ECC-MCC-040 | 210-EC-EAT-EL-001 | 210 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-210-EL-110 | 23S3-ECC-MCC-040 | 210-EC-EAT-EL-001 | 210 | MCC | EL | Earthing / lightening check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-210-EL-120 | 23S3-ECC-MCC-040 | 210-EC-EAT-EL-001 | 210 | MCC | EL | Relay setting test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
LV Switchgear System (210-EC-LVS-EL-002) | 23S3-ECC-MCC-040 | 210-EC-LVS-EL-002 | 210 | MCC | EL |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
23S3-PC-210-EL-140 | 23S3-ECC-MCC-040 | 210-EC-LVS-EL-002 | 210 | MCC | EL | Panel installation and final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-210-EL-145 | 23S3-ECC-MCC-040 | 210-EC-LVS-EL-002 | 210 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-210-EL-150 | 23S3-ECC-MCC-040 | 210-EC-LVS-EL-002 | 210 | MCC | EL | Earthing / lightening check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-210-EL-160 | 23S3-ECC-MCC-040 | 210-EC-LVS-EL-002 | 210 | MCC | EL | CT/PT check and test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-210-EL-170 | 23S3-ECC-MCC-040 | 210-EC-LVS-EL-002 | 210 | MCC | EL | Relay setting test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
220-LV Switchgear System (23S3-ECC-MCC-041) | 23S3-ECC-MCC-041 |  | 220 | MCC |  |  | 9 | 2019-11-06 | 2019-11-15 | 1398/08/15 | 1398/08/24
LV Switchgear System (220-EC-LVS-EL-001) | 23S3-ECC-MCC-041 | 220-EC-LVS-EL-001 | 220 | MCC | EL |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
23S3-PC-220-EL-100 | 23S3-ECC-MCC-041 | 220-EC-LVS-EL-001 | 220 | MCC | EL | Panel installation and final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-220-EL-105 | 23S3-ECC-MCC-041 | 220-EC-LVS-EL-001 | 220 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-220-EL-110 | 23S3-ECC-MCC-041 | 220-EC-LVS-EL-001 | 220 | MCC | EL | Earthing / lightening check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-220-EL-120 | 23S3-ECC-MCC-041 | 220-EC-LVS-EL-001 | 220 | MCC | EL | CT/PT check and test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-220-EL-130 | 23S3-ECC-MCC-041 | 220-EC-LVS-EL-001 | 220 | MCC | EL | Relay setting test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
LV TRANSFORMER SYSTEM (220-EC-TR-EL-002) | 23S3-ECC-MCC-041 | 220-EC-TR-EL-002 | 220 | MCC | EL |  | 7 | 2019-11-06 | 2019-11-13 | 1398/08/15 | 1398/08/22
23S3-PC-220-EL-150 | 23S3-ECC-MCC-041 | 220-EC-TR-EL-002 | 220 | MCC | EL | Transformer Installation final Check | 3 | 2019-11-06 | 2019-11-09 | 1398/08/15 | 1398/08/18
23S3-PC-220-EL-155 | 23S3-ECC-MCC-041 | 220-EC-TR-EL-002 | 220 | MCC | EL | Earthing check, test and punch clearance | 2 | 2019-11-09 | 2019-11-11 | 1398/08/18 | 1398/08/20
23S3-PC-220-EL-160 | 23S3-ECC-MCC-041 | 220-EC-TR-EL-002 | 220 | MCC | EL | CT/PT check and test | 1 | 2019-11-11 | 2019-11-12 | 1398/08/20 | 1398/08/21
23S3-PC-220-EL-170 | 23S3-ECC-MCC-041 | 220-EC-TR-EL-002 | 220 | MCC | EL | Relay setting test | 1 | 2019-11-12 | 2019-11-13 | 1398/08/21 | 1398/08/22
Earthing & Lightning (220-EC-EAT-EL-003) | 23S3-ECC-MCC-041 | 220-EC-EAT-EL-003 | 220 | MCC | EL |  | 3 | 2019-11-12 | 2019-11-15 | 1398/08/21 | 1398/08/24
23S3-PC-220-EL-190 | 23S3-ECC-MCC-041 | 220-EC-EAT-EL-003 | 220 | MCC | EL | Relay setting test | 1 | 2019-11-12 | 2019-11-13 | 1398/08/21 | 1398/08/22
23S3-PC-220-EL-200 | 23S3-ECC-MCC-041 | 220-EC-EAT-EL-003 | 220 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-13 | 2019-11-14 | 1398/08/22 | 1398/08/23
23S3-PC-220-EL-210 | 23S3-ECC-MCC-041 | 220-EC-EAT-EL-003 | 220 | MCC | EL | Earthing / lightening check, test and punch clearance | 1 | 2019-11-14 | 2019-11-15 | 1398/08/23 | 1398/08/24
225-LV Switchgear System (23S3-ECC-MCC-042) | 23S3-ECC-MCC-042 |  | 225 | MCC |  |  | 9 | 2019-11-06 | 2019-11-15 | 1398/08/15 | 1398/08/24
LV TRANSFORMER SYSTEM (225-EC-TR-EL-001) | 23S3-ECC-MCC-042 | 225-EC-TR-EL-001 | 225 | MCC | EL |  | 7 | 2019-11-08 | 2019-11-15 | 1398/08/17 | 1398/08/24
23S3-PC-225-EL-100 | 23S3-ECC-MCC-042 | 225-EC-TR-EL-001 | 225 | MCC | EL | Transformer Installation final Check | 3 | 2019-11-08 | 2019-11-11 | 1398/08/17 | 1398/08/20
23S3-PC-225-EL-105 | 23S3-ECC-MCC-042 | 225-EC-TR-EL-001 | 225 | MCC | EL | Earthing check, test and punch clearance | 2 | 2019-11-11 | 2019-11-13 | 1398/08/20 | 1398/08/22
23S3-PC-225-EL-110 | 23S3-ECC-MCC-042 | 225-EC-TR-EL-001 | 225 | MCC | EL | CT/PT check and test | 1 | 2019-11-13 | 2019-11-14 | 1398/08/22 | 1398/08/23
23S3-PC-225-EL-120 | 23S3-ECC-MCC-042 | 225-EC-TR-EL-001 | 225 | MCC | EL | Relay setting test | 1 | 2019-11-14 | 2019-11-15 | 1398/08/23 | 1398/08/24
LV Switchgear System (225-EC-LVS-EL-002) | 23S3-ECC-MCC-042 | 225-EC-LVS-EL-002 | 225 | MCC | EL |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
23S3-PC-225-EL-140 | 23S3-ECC-MCC-042 | 225-EC-LVS-EL-002 | 225 | MCC | EL | Panel installation and final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-225-EL-145 | 23S3-ECC-MCC-042 | 225-EC-LVS-EL-002 | 225 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-225-EL-150 | 23S3-ECC-MCC-042 | 225-EC-LVS-EL-002 | 225 | MCC | EL | Earthing check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-225-EL-160 | 23S3-ECC-MCC-042 | 225-EC-LVS-EL-002 | 225 | MCC | EL | CT/PT check and test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-225-EL-170 | 23S3-ECC-MCC-042 | 225-EC-LVS-EL-002 | 225 | MCC | EL | Relay setting test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
230-LV Switchgear System (23S3-ECC-MCC-043) | 23S3-ECC-MCC-043 |  | 230 | MCC |  |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
LV Switchgear System (230-EC-LVS-EL-001) | 23S3-ECC-MCC-043 | 230-EC-LVS-EL-001 | 230 | MCC | EL |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
23S3-PC-230-EL-100 | 23S3-ECC-MCC-043 | 230-EC-LVS-EL-001 | 230 | MCC | EL | Panel installation and final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-230-EL-105 | 23S3-ECC-MCC-043 | 230-EC-LVS-EL-001 | 230 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-230-EL-110 | 23S3-ECC-MCC-043 | 230-EC-LVS-EL-001 | 230 | MCC | EL | Earthing check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-230-EL-120 | 23S3-ECC-MCC-043 | 230-EC-LVS-EL-001 | 230 | MCC | EL | CT/PT check and test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-230-EL-130 | 23S3-ECC-MCC-043 | 230-EC-LVS-EL-001 | 230 | MCC | EL | Relay setting test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
270-LV Switchgear System (23S3-ECC-MCC-044) | 23S3-ECC-MCC-044 |  | 270 | MCC |  |  | 18 | 2019-11-06 | 2019-11-24 | 1398/08/15 | 1398/09/03
LV TRANSFORMER SYSTEM (270-EC-TR-EL-001) | 23S3-ECC-MCC-044 | 270-EC-TR-EL-001 | 270 | MCC | EL |  | 6 | 2019-11-07 | 2019-11-13 | 1398/08/16 | 1398/08/22
23S3-PC-270-EL-100 | 23S3-ECC-MCC-044 | 270-EC-TR-EL-001 | 270 | MCC | EL | Transformer Installation final Check /oil circulation | 2 | 2019-11-07 | 2019-11-09 | 1398/08/16 | 1398/08/18
23S3-PC-270-EL-110 | 23S3-ECC-MCC-044 | 270-EC-TR-EL-001 | 270 | MCC | EL | Panel installation final check and punch clearance | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-270-EL-120 | 23S3-ECC-MCC-044 | 270-EC-TR-EL-001 | 270 | MCC | EL | Earthing check, test and punch clearance | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
23S3-PC-270-EL-130 | 23S3-ECC-MCC-044 | 270-EC-TR-EL-001 | 270 | MCC | EL | CT/PT check and test | 1 | 2019-11-11 | 2019-11-12 | 1398/08/20 | 1398/08/21
23S3-PC-270-EL-140 | 23S3-ECC-MCC-044 | 270-EC-TR-EL-001 | 270 | MCC | EL | Relay setting test | 1 | 2019-11-12 | 2019-11-13 | 1398/08/21 | 1398/08/22
LV Switchgear System (270-EC-LVS-EL-002) | 23S3-ECC-MCC-044 | 270-EC-LVS-EL-002 | 270 | MCC | EL |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
23S3-PC-270-EL-180 | 23S3-ECC-MCC-044 | 270-EC-LVS-EL-002 | 270 | MCC | EL | Panel installation final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-270-EL-185 | 23S3-ECC-MCC-044 | 270-EC-LVS-EL-002 | 270 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-270-EL-190 | 23S3-ECC-MCC-044 | 270-EC-LVS-EL-002 | 270 | MCC | EL | Earthing check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-270-EL-200 | 23S3-ECC-MCC-044 | 270-EC-LVS-EL-002 | 270 | MCC | EL | CT/PT check and test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-270-EL-210 | 23S3-ECC-MCC-044 | 270-EC-LVS-EL-002 | 270 | MCC | EL | Relay setting test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
Earthing & Lightning (270-EC-EAT-EL-003) | 23S3-ECC-MCC-044 | 270-EC-EAT-EL-003 | 270 | MCC | EL |  | 6 | 2019-11-13 | 2019-11-19 | 1398/08/22 | 1398/08/28
23S3-PC-270-EL-220 | 23S3-ECC-MCC-044 | 270-EC-EAT-EL-003 | 270 | MCC | EL | Cable Puling Check and megger test | 2 | 2019-11-13 | 2019-11-15 | 1398/08/22 | 1398/08/24
23S3-PC-270-EL-230 | 23S3-ECC-MCC-044 | 270-EC-EAT-EL-003 | 270 | MCC | EL | Earthing check, test and punch clearance | 2 | 2019-11-15 | 2019-11-17 | 1398/08/24 | 1398/08/26
23S3-PC-270-EL-240 | 23S3-ECC-MCC-044 | 270-EC-EAT-EL-003 | 270 | MCC | EL | Relay setting test | 2 | 2019-11-17 | 2019-11-19 | 1398/08/26 | 1398/08/28
F&G System (270-EC-F&G-EL-004) | 23S3-ECC-MCC-044 | 270-EC-F&G-EL-004 | 270 | MCC | EL |  | 6 | 2019-11-16 | 2019-11-22 | 1398/08/25 | 1398/09/01
23S3-PC-270-EL-250 | 23S3-ECC-MCC-044 | 270-EC-F&G-EL-004 | 270 | MCC | EL | Cable Puling Check and megger test | 2 | 2019-11-16 | 2019-11-18 | 1398/08/25 | 1398/08/27
23S3-PC-270-EL-260 | 23S3-ECC-MCC-044 | 270-EC-F&G-EL-004 | 270 | MCC | EL | Earthing check, test and punch clearance | 2 | 2019-11-18 | 2019-11-20 | 1398/08/27 | 1398/08/29
23S3-PC-270-EL-270 | 23S3-ECC-MCC-044 | 270-EC-F&G-EL-004 | 270 | MCC | EL | Relay setting test | 2 | 2019-11-20 | 2019-11-22 | 1398/08/29 | 1398/09/01
Heat tracing System (270-EC-HET-EL-005) | 23S3-ECC-MCC-044 | 270-EC-HET-EL-005 | 270 | MCC | EL |  | 4 | 2019-11-20 | 2019-11-24 | 1398/08/29 | 1398/09/03
23S3-PC-270-EL-460 | 23S3-ECC-MCC-044 | 270-EC-HET-EL-005 | 270 | MCC | EL | Cable Puling Check and megger test | 2 | 2019-11-20 | 2019-11-22 | 1398/08/29 | 1398/09/01
23S3-PC-270-EL-490 | 23S3-ECC-MCC-044 | 270-EC-HET-EL-005 | 270 | MCC | EL | Earthing check, test and punch clearance | 2 | 2019-11-22 | 2019-11-24 | 1398/09/01 | 1398/09/03
Lighting and Small Power System (270-EC-LIT-EL-006) | 23S3-ECC-MCC-044 | 270-EC-LIT-EL-006 | 270 | MCC | EL |  | 7 | 2019-11-14 | 2019-11-21 | 1398/08/23 | 1398/08/30
23S3-PC-270-EL-500 | 23S3-ECC-MCC-044 | 270-EC-LIT-EL-006 | 270 | MCC | EL | Panel installation final check and punch clearance | 4 | 2019-11-14 | 2019-11-18 | 1398/08/23 | 1398/08/27
23S3-PC-270-EL-510 | 23S3-ECC-MCC-044 | 270-EC-LIT-EL-006 | 270 | MCC | EL | Cable Puling Check and megger test | 3 | 2019-11-17 | 2019-11-20 | 1398/08/26 | 1398/08/29
23S3-PC-270-EL-520 | 23S3-ECC-MCC-044 | 270-EC-LIT-EL-006 | 270 | MCC | EL | Earthing check, test and punch clearance | 2 | 2019-11-19 | 2019-11-21 | 1398/08/28 | 1398/08/30
200-MV PANEL SYSTEM (23S3-ECC-MCC-045) | 23S3-ECC-MCC-045 |  | 200 | MCC |  |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
MV PANEL ELECTRICAL SYSTEM (200-EC-MV-EL-001) | 23S3-ECC-MCC-045 | 200-EC-MV-EL-001 | 200 | MCC | EL |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
23S3-PC-200-EL-190 | 23S3-ECC-MCC-045 | 200-EC-MV-EL-001 | 200 | MCC | EL | Panel installation and check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-200-EL-195 | 23S3-ECC-MCC-045 | 200-EC-MV-EL-001 | 200 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-200-EL-200 | 23S3-ECC-MCC-045 | 200-EC-MV-EL-001 | 200 | MCC | EL | Earthing check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-200-EL-210 | 23S3-ECC-MCC-045 | 200-EC-MV-EL-001 | 200 | MCC | EL | CT/PT check and test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-200-EL-220 | 23S3-ECC-MCC-045 | 200-EC-MV-EL-001 | 200 | MCC | EL | Relay setting test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
220-MAIN CONTROL ROOM (23S3-ECC-ITR-046) | 23S3-ECC-ITR-046 |  | 220 | ITR |  |  | 26 | 2019-11-07 | 2019-12-03 | 1398/08/16 | 1398/09/12
Plant Control System - DCS (220-EC-ITR-IN-001) | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN |  | 26 | 2019-11-07 | 2019-12-03 | 1398/08/16 | 1398/09/12
23S3-PC-220-IN-340 | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN | Cabinet installation check and punch clearance | 3 | 2019-11-07 | 2019-11-10 | 1398/08/16 | 1398/08/19
23S3-PC-220-IN-345 | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN | PDP panel installation check and punch clearance | 2 | 2019-11-10 | 2019-11-12 | 1398/08/19 | 1398/08/21
23S3-PC-220-IN-350 | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN | PDP panel Energizing | 1 | 2019-11-12 | 2019-11-13 | 1398/08/21 | 1398/08/22
23S3-PC-220-IN-352 | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN | Vendor At Site ( PLT ) | 0 | 2019-11-13 |  | 1398/08/22
23S3-PC-220-IN-355 | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN | Logic Check and Function Test ( Area 270 ) | 5 | 2019-11-13 | 2019-11-18 | 1398/08/22 | 1398/08/27
23S3-PC-220-IN-360 | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN | Logic Check and Function Test ( Area 220 ) | 5 | 2019-11-15 | 2019-11-20 | 1398/08/24 | 1398/08/29
23S3-PC-220-IN-365 | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN | Logic Check and Function Test ( Area 150,210,200,225,230 ) | 7 | 2019-11-18 | 2019-11-25 | 1398/08/27 | 1398/09/04
23S3-PC-220-IN-370 | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN | Alarm and Trip Setting Configuration | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
23S3-PC-220-IN-375 | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN | Control system and software loading and feedback check and redinees for Function test | 20 | 2019-11-13 | 2019-12-03 | 1398/08/22 | 1398/09/12
200 - PLANT AIR COMPRESSED SYSTEM (23S3-ECC-PLA-003) | 23S3-ECC-PLA-003 |  | 200 | PLA |  |  | 16 | 2019-11-07 | 2019-11-23 | 1398/08/16 | 1398/09/02
PLANT AIR COMPRESSED ELECTRICAL SYSTEM (200-EC-PLA-EL-001) | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-001 | 200 | PLA | EL |  | 8 | 2019-11-07 | 2019-11-15 | 1398/08/16 | 1398/08/24
23S3-PC-200-EL-260 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-001 | 200 | PLA | EL | Electrical Cable Check and continuity megger test | 3 | 2019-11-07 | 2019-11-10 | 1398/08/16 | 1398/08/19
23S3-PC-200-EL-270 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-001 | 200 | PLA | EL | motor continuity megger test | 2 | 2019-11-08 | 2019-11-10 | 1398/08/17 | 1398/08/19
23S3-PC-200-EL-280 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-001 | 200 | PLA | EL | gland and connection final inspection | 2 | 2019-11-09 | 2019-11-11 | 1398/08/18 | 1398/08/20
23S3-PC-200-EL-290 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-001 | 200 | PLA | EL | Local panel final function test | 2 | 2019-11-10 | 2019-11-12 | 1398/08/19 | 1398/08/21
23S3-PC-200-EL-300 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-001 | 200 | PLA | EL | feeder final checking | 2 | 2019-11-11 | 2019-11-13 | 1398/08/20 | 1398/08/22
23S3-PC-200-EL-305 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-001 | 200 | PLA | EL | Vendor At Site ( Novin Hava ) | 0 | 2019-11-13 |  | 1398/08/22
23S3-PC-200-EL-310 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-001 | 200 | PLA | EL | motor free run and load run test | 2 | 2019-11-13 | 2019-11-15 | 1398/08/22 | 1398/08/24
PLANT AIR COMPRESSED ELECTRICAL SYSTEM (200-EC-PLA-EL-002) | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-002 | 200 | PLA | EL |  | 8 | 2019-11-07 | 2019-11-15 | 1398/08/16 | 1398/08/24
23S3-PC-200-EL-320 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-002 | 200 | PLA | EL | Electrical Cable Check and continuity megger test | 3 | 2019-11-07 | 2019-11-10 | 1398/08/16 | 1398/08/19
23S3-PC-200-EL-330 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-002 | 200 | PLA | EL | motor continuity megger test | 2 | 2019-11-08 | 2019-11-10 | 1398/08/17 | 1398/08/19
23S3-PC-200-EL-340 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-002 | 200 | PLA | EL | gland and connection final inspection | 2 | 2019-11-09 | 2019-11-11 | 1398/08/18 | 1398/08/20
23S3-PC-200-EL-350 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-002 | 200 | PLA | EL | Local panel final function test | 2 | 2019-11-10 | 2019-11-12 | 1398/08/19 | 1398/08/21
23S3-PC-200-EL-360 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-002 | 200 | PLA | EL | feeder final checking | 2 | 2019-11-11 | 2019-11-13 | 1398/08/20 | 1398/08/22
23S3-PC-200-EL-370 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-002 | 200 | PLA | EL | motor free run and load run test | 2 | 2019-11-13 | 2019-11-15 | 1398/08/22 | 1398/08/24
PLANT AIR COMPRESSED ELECTRICAL SYSTEM (200-EC-PLA-EL-003) | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-003 | 200 | PLA | EL |  | 8 | 2019-11-07 | 2019-11-15 | 1398/08/16 | 1398/08/24
23S3-PC-200-EL-380 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-003 | 200 | PLA | EL | Electrical Cable Check and continuity megger test | 3 | 2019-11-07 | 2019-11-10 | 1398/08/16 | 1398/08/19
23S3-PC-200-EL-390 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-003 | 200 | PLA | EL | motor continuity megger test | 2 | 2019-11-08 | 2019-11-10 | 1398/08/17 | 1398/08/19
23S3-PC-200-EL-400 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-003 | 200 | PLA | EL | gland and connection final inspection | 2 | 2019-11-09 | 2019-11-11 | 1398/08/18 | 1398/08/20
23S3-PC-200-EL-410 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-003 | 200 | PLA | EL | Local panel final function test | 2 | 2019-11-10 | 2019-11-12 | 1398/08/19 | 1398/08/21
23S3-PC-200-EL-420 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-003 | 200 | PLA | EL | feeder final checking | 2 | 2019-11-11 | 2019-11-13 | 1398/08/20 | 1398/08/22
23S3-PC-200-EL-430 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-003 | 200 | PLA | EL | motor free run and load run test | 2 | 2019-11-13 | 2019-11-15 | 1398/08/22 | 1398/08/24
PLANT AIR COMPRESSED CRANE ELECTRICAL SYSTEM (200-EC-PLA-EL-004) | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-004 | 200 | PLA | EL |  | 7 | 2019-11-07 | 2019-11-14 | 1398/08/16 | 1398/08/23
23S3-PC-200-EL-440 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-004 | 200 | PLA | EL | Electrical Cable Check and continuity megger test | 3 | 2019-11-07 | 2019-11-10 | 1398/08/16 | 1398/08/19
23S3-PC-200-EL-450 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-004 | 200 | PLA | EL | motor continuity megger test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-200-EL-460 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-004 | 200 | PLA | EL | gland and connection final inspection | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
23S3-PC-200-EL-480 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-004 | 200 | PLA | EL | feeder final checking | 1 | 2019-11-12 | 2019-11-13 | 1398/08/21 | 1398/08/22
23S3-PC-200-EL-490 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-004 | 200 | PLA | EL | motor free run and load run test | 1 | 2019-11-13 | 2019-11-14 | 1398/08/22 | 1398/08/23
PLANT AIR COMPRESSED INSTRUMENT SYSTEM (200-EC-PLA-IN-001) | 23S3-ECC-PLA-003 | 200-EC-PLA-IN-001 | 200 | PLA | IN |  | 13 | 2019-11-10 | 2019-11-23 | 1398/08/19 | 1398/09/02
23S3-PC-200-IN-100 | 23S3-ECC-PLA-003 | 200-EC-PLA-IN-001 | 200 | PLA | IN | device calibration | 3 | 2019-11-10 | 2019-11-13 | 1398/08/19 | 1398/08/22
23S3-PC-200-IN-110 | 23S3-ECC-PLA-003 | 200-EC-PLA-IN-001 | 200 | PLA | IN | Instrument Cable Check and continuity megger test | 5 | 2019-11-11 | 2019-11-16 | 1398/08/20 | 1398/08/25
23S3-PC-200-IN-120 | 23S3-ECC-PLA-003 | 200-EC-PLA-IN-001 | 200 | PLA | IN | device installation final check and punch clearance | 3 | 2019-11-13 | 2019-11-16 | 1398/08/22 | 1398/08/25
23S3-PC-200-IN-130 | 23S3-ECC-PLA-003 | 200-EC-PLA-IN-001 | 200 | PLA | IN | IO and loop checking | 4 | 2019-11-15 | 2019-11-19 | 1398/08/24 | 1398/08/28
23S3-PC-200-IN-140 | 23S3-ECC-PLA-003 | 200-EC-PLA-IN-001 | 200 | PLA | IN | function test | 4 | 2019-11-19 | 2019-11-23 | 1398/08/28 | 1398/09/02
PLANT AIR COMPRESSED MECHANICAL SYSTEM (200-EC-PLA-ME-001) | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-001 | 200 | PLA | ME |  | 5 | 2019-11-10 | 2019-11-16 | 1398/08/19 | 1398/08/25
23S3-PC-200-ME-100 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-001 | 200 | PLA | ME | Motor and Compressor installation final check and punch clearance | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
23S3-PC-200-ME-110 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-001 | 200 | PLA | ME | Flange Parallel Check and adjastment | 1 | 2019-11-11 | 2019-11-12 | 1398/08/20 | 1398/08/21
23S3-PC-200-ME-120 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-001 | 200 | PLA | ME | Coupling Compressor and motor / load run test | 1 | 2019-11-15 | 2019-11-16 | 1398/08/24 | 1398/08/25
23S3-PC-200-ME-130 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-001 | 200 | PLA | ME | check for pre box-up and punch clearance | 3 | 2019-11-10 | 2019-11-13 | 1398/08/19 | 1398/08/22
23S3-PC-200-ME-150 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-001 | 200 | PLA | ME | final boxup | 1 | 2019-11-13 | 2019-11-14 | 1398/08/22 | 1398/08/23
PLANT AIR COMPRESSED MECHANICAL SYSTEM (200-EC-PLA-ME-002) | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-002 | 200 | PLA | ME |  | 5 | 2019-11-10 | 2019-11-16 | 1398/08/19 | 1398/08/25
23S3-PC-200-ME-160 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-002 | 200 | PLA | ME | Motor and Compressor installation final check and punch clearance | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
23S3-PC-200-ME-170 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-002 | 200 | PLA | ME | Flange Parallel Check and adjastment | 1 | 2019-11-11 | 2019-11-12 | 1398/08/20 | 1398/08/21
23S3-PC-200-ME-180 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-002 | 200 | PLA | ME | Coupling Compressor and motor / load run test | 1 | 2019-11-15 | 2019-11-16 | 1398/08/24 | 1398/08/25
23S3-PC-200-ME-190 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-002 | 200 | PLA | ME | check for pre box-up and punch clearance | 3 | 2019-11-10 | 2019-11-13 | 1398/08/19 | 1398/08/22
23S3-PC-200-ME-210 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-002 | 200 | PLA | ME | final boxup | 1 | 2019-11-13 | 2019-11-14 | 1398/08/22 | 1398/08/23
PLANT AIR COMPRESSED MECHANICAL SYSTEM (200-EC-PLA-ME-003) | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-003 | 200 | PLA | ME |  | 5 | 2019-11-10 | 2019-11-16 | 1398/08/19 | 1398/08/25
23S3-PC-200-ME-220 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-003 | 200 | PLA | ME | Motor and Compressor installation final check and punch clearance | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
23S3-PC-200-ME-230 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-003 | 200 | PLA | ME | Flange Parallel Check and adjastment | 1 | 2019-11-11 | 2019-11-12 | 1398/08/20 | 1398/08/21
23S3-PC-200-ME-240 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-003 | 200 | PLA | ME | Coupling Compressor and motor / load run test | 1 | 2019-11-15 | 2019-11-16 | 1398/08/24 | 1398/08/25
23S3-PC-200-ME-250 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-003 | 200 | PLA | ME | check for pre box-up and punch clearance | 3 | 2019-11-11 | 2019-11-14 | 1398/08/20 | 1398/08/23
23S3-PC-200-ME-270 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-003 | 200 | PLA | ME | final boxup | 1 | 2019-11-14 | 2019-11-15 | 1398/08/23 | 1398/08/24
PLANT AIR COMPRESSED CRANE MECHANICAL SYSTEM (200-EC-PLA-ME-004) | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-004 | 200 | PLA | ME |  | 2 | 2019-11-15 | 2019-11-17 | 1398/08/24 | 1398/08/26
23S3-PC-200-ME-320 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-004 | 200 | PLA | ME | Punch Clearance | 1 | 2019-11-15 | 2019-11-16 | 1398/08/24 | 1398/08/25
23S3-PC-200-ME-330 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-004 | 200 | PLA | ME | Load Test | 1 | 2019-11-16 | 2019-11-17 | 1398/08/25 | 1398/08/26
PLANT AIR COMPRESSED PIPING SYSTEM (200-EC-PLA-PI-001) | 23S3-ECC-PLA-003 | 200-EC-PLA-PI-001 | 200 | PLA | PI |  | 3 | 2019-11-10 | 2019-11-13 | 1398/08/19 | 1398/08/22
23S3-PC-200-PI-100 | 23S3-ECC-PLA-003 | 200-EC-PLA-PI-001 | 200 | PLA | PI | Punch Clearance | 3 | 2019-11-10 | 2019-11-13 | 1398/08/19 | 1398/08/22
220-FSF PLANT AIR DISTRIBUTION NET WORK (23S3-ECC-PLA-018) | 23S3-ECC-PLA-018 |  | 220 | PLA |  |  | 8 | 2019-11-19 | 2019-11-27 | 1398/08/28 | 1398/09/06
FSF Plant Air Distribution Net Work Instrument System (220-EC-PLA-IN-001) | 23S3-ECC-PLA-018 | 220-EC-PLA-IN-001 | 220 | PLA | IN |  | 6 | 2019-11-19 | 2019-11-25 | 1398/08/28 | 1398/09/04
23S3-PC-220-IN-380 | 23S3-ECC-PLA-018 | 220-EC-PLA-IN-001 | 220 | PLA | IN | device calibration | 1 | 2019-11-19 | 2019-11-20 | 1398/08/28 | 1398/08/29
23S3-PC-220-IN-390 | 23S3-ECC-PLA-018 | 220-EC-PLA-IN-001 | 220 | PLA | IN | Instrument Cable Check and continuity megger test | 2 | 2019-11-20 | 2019-11-22 | 1398/08/29 | 1398/09/01
23S3-PC-220-IN-400 | 23S3-ECC-PLA-018 | 220-EC-PLA-IN-001 | 220 | PLA | IN | device installation final check and punch clearance | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-220-IN-410 | 23S3-ECC-PLA-018 | 220-EC-PLA-IN-001 | 220 | PLA | IN | IO and loop checking | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-220-IN-420 | 23S3-ECC-PLA-018 | 220-EC-PLA-IN-001 | 220 | PLA | IN | function test | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
FSF Plant Air Distribution Net Work Mechanic System (220-EC-PLA-ME-001) | 23S3-ECC-PLA-018 | 220-EC-PLA-ME-001 | 220 | PLA | ME |  | 2 | 2019-11-23 | 2019-11-25 | 1398/09/02 | 1398/09/04
23S3-PC-220-ME-100 | 23S3-ECC-PLA-018 | 220-EC-PLA-ME-001 | 220 | PLA | ME | check for pre box-up and punch clearance | 2 | 2019-11-23 | 2019-11-25 | 1398/09/02 | 1398/09/04
23S3-PC-220-ME-110 | 23S3-ECC-PLA-018 | 220-EC-PLA-ME-001 | 220 | PLA | ME | final boxup | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
FSF Plant Air Distribution Net Work Piping System (220-EC-PLA-PI-001) | 23S3-ECC-PLA-018 | 220-EC-PLA-PI-001 | 220 | PLA | PI |  | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
23S3-PC-220-PI-100 | 23S3-ECC-PLA-018 | 220-EC-PLA-PI-001 | 220 | PLA | PI | Punch Clearance | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
220-FSF INSTRUMENT AIR DISTRIBUTION NET WORK (23S3-ECC-INA-019) | 23S3-ECC-INA-019 |  | 220 | INA |  |  | 8 | 2019-11-19 | 2019-11-27 | 1398/08/28 | 1398/09/06
FSF Instrument Air Distribution Net Work Instrument System (220-EC-INA-IN-001) | 23S3-ECC-INA-019 | 220-EC-INA-IN-001 | 220 | INA | IN |  | 6 | 2019-11-19 | 2019-11-25 | 1398/08/28 | 1398/09/04
23S3-PC-220-IN-430 | 23S3-ECC-INA-019 | 220-EC-INA-IN-001 | 220 | INA | IN | device calibration | 1 | 2019-11-19 | 2019-11-20 | 1398/08/28 | 1398/08/29
23S3-PC-220-IN-440 | 23S3-ECC-INA-019 | 220-EC-INA-IN-001 | 220 | INA | IN | Instrument Cable Check and continuity megger test | 2 | 2019-11-20 | 2019-11-22 | 1398/08/29 | 1398/09/01
23S3-PC-220-IN-450 | 23S3-ECC-INA-019 | 220-EC-INA-IN-001 | 220 | INA | IN | device installation final check and punch clearance | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-220-IN-460 | 23S3-ECC-INA-019 | 220-EC-INA-IN-001 | 220 | INA | IN | IO and loop checking | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-220-IN-470 | 23S3-ECC-INA-019 | 220-EC-INA-IN-001 | 220 | INA | IN | function test | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
FSF Instrument Air Distribution Net Work Piping System (220-EC-INA-PI-001) | 23S3-ECC-INA-019 | 220-EC-INA-PI-001 | 220 | INA | PI |  | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
23S3-PC-220-PI-110 | 23S3-ECC-INA-019 | 220-EC-INA-PI-001 | 220 | INA | PI | Punch Clearance | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
220-FSF LIGHT FUEL OIL DISTRIBUTION NET WORK (23S3-ECC-LFO-021) | 23S3-ECC-LFO-021 |  | 220 | LFO |  |  | 6 | 2019-11-20 | 2019-11-26 | 1398/08/29 | 1398/09/05
FSFLight Fuel Oil Distribution Net Work Instrument System (220-EC-LFO-IN-001) | 23S3-ECC-LFO-021 | 220-EC-LFO-IN-001 | 220 | LFO | IN |  | 4 | 2019-11-20 | 2019-11-24 | 1398/08/29 | 1398/09/03
23S3-PC-220-IN-480 | 23S3-ECC-LFO-021 | 220-EC-LFO-IN-001 | 220 | LFO | IN | device calibration | 1 | 2019-11-20 | 2019-11-21 | 1398/08/29 | 1398/08/30
23S3-PC-220-IN-490 | 23S3-ECC-LFO-021 | 220-EC-LFO-IN-001 | 220 | LFO | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-21 | 2019-11-22 | 1398/08/30 | 1398/09/01
23S3-PC-220-IN-500 | 23S3-ECC-LFO-021 | 220-EC-LFO-IN-001 | 220 | LFO | IN | device installation final check and punch clearance | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-220-IN-510 | 23S3-ECC-LFO-021 | 220-EC-LFO-IN-001 | 220 | LFO | IN | IO and loop checking | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-220-IN-520 | 23S3-ECC-LFO-021 | 220-EC-LFO-IN-001 | 220 | LFO | IN | function test | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
FSFLight Fuel Oil Distribution Net Work Piping System (220-EC-LFO-PI-001) | 23S3-ECC-LFO-021 | 220-EC-LFO-PI-001 | 220 | LFO | PI |  | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
23S3-PC-220-PI-120 | 23S3-ECC-LFO-021 | 220-EC-LFO-PI-001 | 220 | LFO | PI | Punch Clearance | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
220-FSF FUEL GAS DISTRIBUTION NET WORK (23S3-ECC-FNG-020) | 23S3-ECC-FNG-020 |  | 220 | FNG |  |  | 6 | 2019-11-20 | 2019-11-26 | 1398/08/29 | 1398/09/05
FSF Fuel Gas Distribution Net Work Instrument System (220-EC-FNG-IN-001) | 23S3-ECC-FNG-020 | 220-EC-FNG-IN-001 | 220 | FNG | IN |  | 4 | 2019-11-20 | 2019-11-24 | 1398/08/29 | 1398/09/03
23S3-PC-220-IN-530 | 23S3-ECC-FNG-020 | 220-EC-FNG-IN-001 | 220 | FNG | IN | device calibration | 1 | 2019-11-20 | 2019-11-21 | 1398/08/29 | 1398/08/30
23S3-PC-220-IN-540 | 23S3-ECC-FNG-020 | 220-EC-FNG-IN-001 | 220 | FNG | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-21 | 2019-11-22 | 1398/08/30 | 1398/09/01
23S3-PC-220-IN-550 | 23S3-ECC-FNG-020 | 220-EC-FNG-IN-001 | 220 | FNG | IN | device installation final check and punch clearance | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-220-IN-560 | 23S3-ECC-FNG-020 | 220-EC-FNG-IN-001 | 220 | FNG | IN | IO and loop checking | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-220-IN-570 | 23S3-ECC-FNG-020 | 220-EC-FNG-IN-001 | 220 | FNG | IN | function test | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
FSF Fuel Gas Distribution Net Work Piping System (220-EC-FNG-PI-001) | 23S3-ECC-FNG-020 | 220-EC-FNG-PI-001 | 220 | FNG | PI |  | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
23S3-PC-220-PI-130 | 23S3-ECC-FNG-020 | 220-EC-FNG-PI-001 | 220 | FNG | PI | Punch Clearance | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
270-Water Handling Area (23S3-ECC-JCW-007) | 23S3-ECC-JCW-007 |  | 270 | JCW |  |  | 24 | 2019-11-09 | 2019-12-03 | 1398/08/18 | 1398/09/12
JACKET COOLING WATER INSTRUMENTATION (270-EC-JCW-IN-001) | 23S3-ECC-JCW-007 | 270-EC-JCW-IN-001 | 270 | JCW | IN |  | 10 | 2019-11-23 | 2019-12-03 | 1398/09/02 | 1398/09/12
23S3-PC-270-IN-100 | 23S3-ECC-JCW-007 | 270-EC-JCW-IN-001 | 270 | JCW | IN | Instrument Cable Check and continuity megger test | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
23S3-PC-270-IN-110 | 23S3-ECC-JCW-007 | 270-EC-JCW-IN-001 | 270 | JCW | IN | device calibration | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-270-IN-120 | 23S3-ECC-JCW-007 | 270-EC-JCW-IN-001 | 270 | JCW | IN | device installation final check and punch clearance | 5 | 2019-11-25 | 2019-11-30 | 1398/09/04 | 1398/09/09
23S3-PC-270-IN-130 | 23S3-ECC-JCW-007 | 270-EC-JCW-IN-001 | 270 | JCW | IN | IO and loop checking | 4 | 2019-11-28 | 2019-12-02 | 1398/09/07 | 1398/09/11
23S3-PC-270-IN-140 | 23S3-ECC-JCW-007 | 270-EC-JCW-IN-001 | 270 | JCW | IN | function test | 3 | 2019-11-30 | 2019-12-03 | 1398/09/09 | 1398/09/12
JACKET COOLING WATER MECHANICAL (270-EC-JCW-ME-001) | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-001 | 270 | JCW | ME |  | 8 | 2019-11-25 | 2019-12-03 | 1398/09/04 | 1398/09/12
23S3-PC-270-ME-100 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-001 | 270 | JCW | ME | check for pre box-up and punch clearance | 3 | 2019-11-25 | 2019-11-28 | 1398/09/04 | 1398/09/07
23S3-PC-270-ME-110 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-001 | 270 | JCW | ME | final boxup | 3 | 2019-11-27 | 2019-11-30 | 1398/09/06 | 1398/09/09
23S3-PC-270-ME-120 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-001 | 270 | JCW | ME | Motor and Pump installation final check and punch clearance | 4 | 2019-11-26 | 2019-11-30 | 1398/09/05 | 1398/09/09
23S3-PC-270-ME-130 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-001 | 270 | JCW | ME | Flange Parallel Check and adjastment | 5 | 2019-11-27 | 2019-12-02 | 1398/09/06 | 1398/09/11
23S3-PC-270-ME-140 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-001 | 270 | JCW | ME | Coupling pump and motor / load run test | 3 | 2019-11-30 | 2019-12-03 | 1398/09/09 | 1398/09/12
JACKET COOLING WATER MECHANICAL (270-EC-JCW-ME-002) | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-002 | 270 | JCW | ME |  | 13 | 2019-11-09 | 2019-11-22 | 1398/08/18 | 1398/09/01
23S3-PC-270-ME-150 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-002 | 270 | JCW | ME | Vendor at Site ( Disel Ban ) | 0 | 2019-11-09 |  | 1398/08/18
23S3-PC-270-ME-160 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-002 | 270 | JCW | ME | Disel installation final check and punch clearance | 5 | 2019-11-09 | 2019-11-14 | 1398/08/18 | 1398/08/23
23S3-PC-270-ME-170 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-002 | 270 | JCW | ME | check for pre box-up and punch clearance | 3 | 2019-11-13 | 2019-11-16 | 1398/08/22 | 1398/08/25
23S3-PC-270-ME-180 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-002 | 270 | JCW | ME | final boxup | 3 | 2019-11-13 | 2019-11-16 | 1398/08/22 | 1398/08/25
23S3-PC-270-ME-190 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-002 | 270 | JCW | ME | Pump installation final check and punch clearance | 3 | 2019-11-16 | 2019-11-19 | 1398/08/25 | 1398/08/28
23S3-PC-270-ME-200 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-002 | 270 | JCW | ME | Flange Parallel Check and adjastment | 5 | 2019-11-16 | 2019-11-21 | 1398/08/25 | 1398/08/30
23S3-PC-270-ME-210 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-002 | 270 | JCW | ME | Coupling pump and motor / load run test | 3 | 2019-11-19 | 2019-11-22 | 1398/08/28 | 1398/09/01
JACKET COOLING WATER MECHANICAL (270-EC-JCW-ME-003) | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-003 | 270 | JCW | ME |  | 8 | 2019-11-13 | 2019-11-21 | 1398/08/22 | 1398/08/30
23S3-PC-270-ME-260 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-003 | 270 | JCW | ME | check for pre box-up and punch clearance | 5 | 2019-11-13 | 2019-11-18 | 1398/08/22 | 1398/08/27
23S3-PC-270-ME-270 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-003 | 270 | JCW | ME | final boxup | 3 | 2019-11-18 | 2019-11-21 | 1398/08/27 | 1398/08/30
JACKET COOLING WATER PIPING (270-EC-JCW-PI-001) | 23S3-ECC-JCW-007 | 270-EC-JCW-PI-001 | 270 | JCW | PI |  | 7 | 2019-11-26 | 2019-12-03 | 1398/09/05 | 1398/09/12
23S3-PC-270-PI-100 | 23S3-ECC-JCW-007 | 270-EC-JCW-PI-001 | 270 | JCW | PI | Punch Clearance | 7 | 2019-11-26 | 2019-12-03 | 1398/09/05 | 1398/09/12
JACKET COOLING WATER ELECTRICAL (270-EC-JCW-EL-001) | 23S3-ECC-JCW-007 | 270-EC-JCW-EL-001 | 270 | JCW | EL |  | 4 | 2019-11-25 | 2019-11-29 | 1398/09/04 | 1398/09/08
23S3-PC-270-EL-580 | 23S3-ECC-JCW-007 | 270-EC-JCW-EL-001 | 270 | JCW | EL | gland and connection final inspection | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-270-EL-590 | 23S3-ECC-JCW-007 | 270-EC-JCW-EL-001 | 270 | JCW | EL | LCS final function test | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-270-EL-600 | 23S3-ECC-JCW-007 | 270-EC-JCW-EL-001 | 270 | JCW | EL | feeder final checking | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-270-EL-610 | 23S3-ECC-JCW-007 | 270-EC-JCW-EL-001 | 270 | JCW | EL | motor free run & Load test | 3 | 2019-11-26 | 2019-11-29 | 1398/09/05 | 1398/09/08
270-Water Handling Area (23S3-ECC-SCW-008) | 23S3-ECC-SCW-008 |  | 270 | SCW |  |  | 26 | 2019-11-07 | 2019-12-03 | 1398/08/16 | 1398/09/12
SECONDARY COOLING WATER ELECTRICAL (270-EC-SCW-EL-001) | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-001 | 270 | SCW | EL |  | 6 | 2019-11-25 | 2019-12-01 | 1398/09/04 | 1398/09/10
23S3-PC-270-EL-620 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-001 | 270 | SCW | EL | gland and connection final inspection | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-270-EL-630 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-001 | 270 | SCW | EL | LCS final function test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-270-EL-640 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-001 | 270 | SCW | EL | feeder final checking | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-270-EL-650 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-001 | 270 | SCW | EL | motor free run & load test | 3 | 2019-11-28 | 2019-12-01 | 1398/09/07 | 1398/09/10
SECONDARY COOLING WATER ELECTRICAL (270-EC-SCW-EL-002) | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-002 | 270 | SCW | EL |  | 6 | 2019-11-25 | 2019-12-01 | 1398/09/04 | 1398/09/10
23S3-PC-270-EL-660 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-002 | 270 | SCW | EL | gland and connection final inspection | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-270-EL-670 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-002 | 270 | SCW | EL | LCS final function test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-270-EL-680 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-002 | 270 | SCW | EL | feeder final checking | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-270-EL-690 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-002 | 270 | SCW | EL | motor free run & load test | 3 | 2019-11-28 | 2019-12-01 | 1398/09/07 | 1398/09/10
SECONDARY COOLING WATER ELECTRICAL (270-EC-SCW-EL-003) | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-003 | 270 | SCW | EL |  | 6 | 2019-11-25 | 2019-12-01 | 1398/09/04 | 1398/09/10
23S3-PC-270-EL-700 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-003 | 270 | SCW | EL | gland and connection final inspection | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-270-EL-710 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-003 | 270 | SCW | EL | LCS final function test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-270-EL-720 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-003 | 270 | SCW | EL | feeder final checking | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-270-EL-730 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-003 | 270 | SCW | EL | motor free run & load test | 3 | 2019-11-28 | 2019-12-01 | 1398/09/07 | 1398/09/10
SECONDARY COOLING WATER ELECTRICAL (270-EC-SCW-EL-004) | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-004 | 270 | SCW | EL |  | 6 | 2019-11-25 | 2019-12-01 | 1398/09/04 | 1398/09/10
23S3-PC-270-EL-740 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-004 | 270 | SCW | EL | gland and connection final inspection | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-270-EL-750 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-004 | 270 | SCW | EL | LCS final function test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-270-EL-760 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-004 | 270 | SCW | EL | feeder final checking | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-270-EL-770 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-004 | 270 | SCW | EL | motor free run & load test | 3 | 2019-11-28 | 2019-12-01 | 1398/09/07 | 1398/09/10
SECONDARY COOLING WATER INSTRUMENTATION (270-EC-SCW-IN-001) | 23S3-ECC-SCW-008 | 270-EC-SCW-IN-001 | 270 | SCW | IN |  | 10 | 2019-11-23 | 2019-12-03 | 1398/09/02 | 1398/09/12
23S3-PC-270-IN-150 | 23S3-ECC-SCW-008 | 270-EC-SCW-IN-001 | 270 | SCW | IN | Instrument Cable Check and continuity megger test | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
23S3-PC-270-IN-160 | 23S3-ECC-SCW-008 | 270-EC-SCW-IN-001 | 270 | SCW | IN | device calibration | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-270-IN-170 | 23S3-ECC-SCW-008 | 270-EC-SCW-IN-001 | 270 | SCW | IN | device installation final check and punch clearance | 5 | 2019-11-25 | 2019-11-30 | 1398/09/04 | 1398/09/09
23S3-PC-270-IN-180 | 23S3-ECC-SCW-008 | 270-EC-SCW-IN-001 | 270 | SCW | IN | IO and loop checking | 4 | 2019-11-28 | 2019-12-02 | 1398/09/07 | 1398/09/11
23S3-PC-270-IN-190 | 23S3-ECC-SCW-008 | 270-EC-SCW-IN-001 | 270 | SCW | IN | function test | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
SECONDARY COOLING WATER MACHINERY (270-EC-SCW-ME-001) | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-001 | 270 | SCW | ME |  | 13 | 2019-11-07 | 2019-11-20 | 1398/08/16 | 1398/08/29
23S3-PC-270-ME-280 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-001 | 270 | SCW | ME | check for pre box-up and punch clearance | 5 | 2019-11-07 | 2019-11-12 | 1398/08/16 | 1398/08/21
23S3-PC-270-ME-290 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-001 | 270 | SCW | ME | final boxup | 1 | 2019-11-12 | 2019-11-13 | 1398/08/21 | 1398/08/22
23S3-PC-270-ME-300 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-001 | 270 | SCW | ME | Motor and Pump installation final check and punch clearance | 4 | 2019-11-09 | 2019-11-13 | 1398/08/18 | 1398/08/22
23S3-PC-270-ME-310 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-001 | 270 | SCW | ME | Flange Parallel Check and adjastment | 5 | 2019-11-11 | 2019-11-16 | 1398/08/20 | 1398/08/25
23S3-PC-270-ME-330 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-001 | 270 | SCW | ME | Coupling pump and motor / load run test | 6 | 2019-11-14 | 2019-11-20 | 1398/08/23 | 1398/08/29
SECONDARY COOLING WATER MACHINERY (270-EC-SCW-ME-002) | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-002 | 270 | SCW | ME |  | 4 | 2019-11-13 | 2019-11-17 | 1398/08/22 | 1398/08/26
23S3-PC-270-ME-360 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-002 | 270 | SCW | ME | Motor and Pump installation final check and punch clearance | 1 | 2019-11-13 | 2019-11-14 | 1398/08/22 | 1398/08/23
23S3-PC-270-ME-370 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-002 | 270 | SCW | ME | Flange Parallel Check and adjastment | 1 | 2019-11-14 | 2019-11-15 | 1398/08/23 | 1398/08/24
23S3-PC-270-ME-390 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-002 | 270 | SCW | ME | Coupling pump and motor / load run test | 2 | 2019-11-15 | 2019-11-17 | 1398/08/24 | 1398/08/26
SECONDARY COOLING WATER MECHANICAL (270-EC-SCW-ME-003) | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-003 | 270 | SCW | ME |  | 6 | 2019-11-13 | 2019-11-19 | 1398/08/22 | 1398/08/28
23S3-PC-270-ME-400 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-003 | 270 | SCW | ME | check for pre box-up and punch clearance | 3 | 2019-11-13 | 2019-11-16 | 1398/08/22 | 1398/08/25
23S3-PC-270-ME-410 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-003 | 270 | SCW | ME | final boxup | 1 | 2019-11-16 | 2019-11-17 | 1398/08/25 | 1398/08/26
23S3-PC-270-ME-420 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-003 | 270 | SCW | ME | Motor and Fan installation final check and punch clearance | 2 | 2019-11-13 | 2019-11-15 | 1398/08/22 | 1398/08/24
23S3-PC-270-ME-440 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-003 | 270 | SCW | ME | Fan Adjustment | 3 | 2019-11-15 | 2019-11-18 | 1398/08/24 | 1398/08/27
23S3-PC-270-ME-450 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-003 | 270 | SCW | ME | Coupling Fan and motor / load run test | 1 | 2019-11-18 | 2019-11-19 | 1398/08/27 | 1398/08/28
SECONDARY COOLING WATER MECHANICAL (270-EC-SCW-ME-004) | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-004 | 270 | SCW | ME |  | 7 | 2019-11-13 | 2019-11-20 | 1398/08/22 | 1398/08/29
23S3-PC-270-ME-480 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-004 | 270 | SCW | ME | Motor and Pump installation final check and punch clearance | 2 | 2019-11-13 | 2019-11-15 | 1398/08/22 | 1398/08/24
23S3-PC-270-ME-490 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-004 | 270 | SCW | ME | Flange Parallel Check and adjastment | 3 | 2019-11-15 | 2019-11-18 | 1398/08/24 | 1398/08/27
23S3-PC-270-ME-510 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-004 | 270 | SCW | ME | Coupling pump and motor / load run test | 2 | 2019-11-18 | 2019-11-20 | 1398/08/27 | 1398/08/29
SECONDARY COOLING WATER MECHANICAL (270-EC-SCW-ME-005) | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-005 | 270 | SCW | ME |  | 8 | 2019-11-13 | 2019-11-21 | 1398/08/22 | 1398/08/30
23S3-PC-270-ME-520 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-005 | 270 | SCW | ME | check for pre box-up and punch clearance | 5 | 2019-11-13 | 2019-11-18 | 1398/08/22 | 1398/08/27
23S3-PC-270-ME-530 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-005 | 270 | SCW | ME | final boxup | 3 | 2019-11-18 | 2019-11-21 | 1398/08/27 | 1398/08/30
SECONDARY COOLING WATER PIPING (270-EC-SCW-PI-001) | 23S3-ECC-SCW-008 | 270-EC-SCW-PI-001 | 270 | SCW | PI |  | 3 | 2019-11-26 | 2019-11-29 | 1398/09/05 | 1398/09/08
23S3-PC-270-PI-110 | 23S3-ECC-SCW-008 | 270-EC-SCW-PI-001 | 270 | SCW | PI | Punch Clearance | 3 | 2019-11-26 | 2019-11-29 | 1398/09/05 | 1398/09/08
220-FSF Jacket Cooling water (23S3-ECC-JCW-026) | 23S3-ECC-JCW-026 |  | 220 | JCW |  |  | 18 | 2019-11-16 | 2019-12-04 | 1398/08/25 | 1398/09/13
FSF Cooling Water Instrument Devices (220-EC-JCW-IN-001) | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-001 | 220 | JCW | IN |  | 13 | 2019-11-20 | 2019-12-03 | 1398/08/29 | 1398/09/12
23S3-PC-220-IN-580 | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-001 | 220 | JCW | IN | device calibration | 2 | 2019-11-20 | 2019-11-22 | 1398/08/29 | 1398/09/01
23S3-PC-220-IN-600 | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-001 | 220 | JCW | IN | device installation final check and punch clearance | 5 | 2019-11-22 | 2019-11-27 | 1398/09/01 | 1398/09/06
23S3-PC-220-IN-610 | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-001 | 220 | JCW | IN | IO and loop checking | 7 | 2019-11-23 | 2019-11-30 | 1398/09/02 | 1398/09/09
23S3-PC-220-IN-620 | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-001 | 220 | JCW | IN | function test | 5 | 2019-11-28 | 2019-12-03 | 1398/09/07 | 1398/09/12
FSF Cooling Water Devices For LH/US & Inline (220-EC-JCW-IN-002) | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-002 | 220 | JCW | IN |  | 14 | 2019-11-20 | 2019-12-04 | 1398/08/29 | 1398/09/13
23S3-PC-220-IN-630 | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-002 | 220 | JCW | IN | device calibration | 2 | 2019-11-20 | 2019-11-22 | 1398/08/29 | 1398/09/01
23S3-PC-220-IN-650 | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-002 | 220 | JCW | IN | device installation final check and punch clearance | 5 | 2019-11-22 | 2019-11-27 | 1398/09/01 | 1398/09/06
23S3-PC-220-IN-660 | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-002 | 220 | JCW | IN | IO and loop checking | 8 | 2019-11-23 | 2019-12-01 | 1398/09/02 | 1398/09/10
23S3-PC-220-IN-670 | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-002 | 220 | JCW | IN | function test | 5 | 2019-11-29 | 2019-12-04 | 1398/09/08 | 1398/09/13
FSF Jacket Cooling Water Header (220-EC-JCW-ME-001) | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-001 | 220 | JCW | ME |  | 8 | 2019-11-16 | 2019-11-24 | 1398/08/25 | 1398/09/03
23S3-PC-220-ME-130 | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-001 | 220 | JCW | ME | Cooling header installation final check and punch clearance | 5 | 2019-11-16 | 2019-11-21 | 1398/08/25 | 1398/08/30
23S3-PC-220-ME-140 | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-001 | 220 | JCW | ME | check for pre box-up and punch clearance | 2 | 2019-11-21 | 2019-11-23 | 1398/08/30 | 1398/09/02
23S3-PC-220-ME-150 | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-001 | 220 | JCW | ME | final boxup | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
FSF Jacket Cooling Water Header (220-EC-JCW-ME-002) | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-002 | 220 | JCW | ME |  | 8 | 2019-11-16 | 2019-11-24 | 1398/08/25 | 1398/09/03
23S3-PC-220-ME-170 | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-002 | 220 | JCW | ME | Cooling header installation final check and punch clearance | 5 | 2019-11-16 | 2019-11-21 | 1398/08/25 | 1398/08/30
23S3-PC-220-ME-180 | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-002 | 220 | JCW | ME | check for pre box-up and punch clearance | 2 | 2019-11-21 | 2019-11-23 | 1398/08/30 | 1398/09/02
23S3-PC-220-ME-190 | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-002 | 220 | JCW | ME | final boxup | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
FSF Jacket Cooling Water Header (220-EC-JCW-ME-003) | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-003 | 220 | JCW | ME |  | 6 | 2019-11-16 | 2019-11-22 | 1398/08/25 | 1398/09/01
23S3-PC-220-ME-210 | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-003 | 220 | JCW | ME | Cooling header installation final check and punch clearance | 3 | 2019-11-16 | 2019-11-19 | 1398/08/25 | 1398/08/28
23S3-PC-220-ME-220 | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-003 | 220 | JCW | ME | check for pre box-up and punch clearance | 2 | 2019-11-19 | 2019-11-21 | 1398/08/28 | 1398/08/30
23S3-PC-220-ME-230 | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-003 | 220 | JCW | ME | final boxup | 1 | 2019-11-21 | 2019-11-22 | 1398/08/30 | 1398/09/01
FSF Cooling Water Piping System (220-EC-JCW-PI-001) | 23S3-ECC-JCW-026 | 220-EC-JCW-PI-001 | 220 | JCW | PI |  | 6 | 2019-11-25 | 2019-12-01 | 1398/09/04 | 1398/09/10
23S3-PC-220-PI-140 | 23S3-ECC-JCW-026 | 220-EC-JCW-PI-001 | 220 | JCW | PI | Punch Clearance | 6 | 2019-11-25 | 2019-12-01 | 1398/09/04 | 1398/09/10
FSF Cooling Water Piping System (220-EC-JCW-PI-002) | 23S3-ECC-JCW-026 | 220-EC-JCW-PI-002 | 220 | JCW | PI |  | 6 | 2019-11-25 | 2019-12-01 | 1398/09/04 | 1398/09/10
23S3-PC-220-PI-150 | 23S3-ECC-JCW-026 | 220-EC-JCW-PI-002 | 220 | JCW | PI | Punch Clearance | 6 | 2019-11-25 | 2019-12-01 | 1398/09/04 | 1398/09/10
220-CONCENTRATE BURNER COOLING WATER SYSTEM (23S3-ECC-CBC-027) | 23S3-ECC-CBC-027 |  | 220 | CBC |  |  | 9 | 2019-11-17 | 2019-11-26 | 1398/08/26 | 1398/09/05
Concentrate Burner Cooling water Electrical System (220-EC-CBC-EL-001) | 23S3-ECC-CBC-027 | 220-EC-CBC-EL-001 | 220 | CBC | EL |  | 1 | 2019-11-17 | 2019-11-18 | 1398/08/26 | 1398/08/27
23S3-PC-220-EL-340 | 23S3-ECC-CBC-027 | 220-EC-CBC-EL-001 | 220 | CBC | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-17 | 2019-11-18 | 1398/08/26 | 1398/08/27
23S3-PC-220-EL-350 | 23S3-ECC-CBC-027 | 220-EC-CBC-EL-001 | 220 | CBC | EL | motor continuity megger test | 1 | 2019-11-17 | 2019-11-18 | 1398/08/26 | 1398/08/27
23S3-PC-220-EL-360 | 23S3-ECC-CBC-027 | 220-EC-CBC-EL-001 | 220 | CBC | EL | gland and connection final inspection | 1 | 2019-11-17 | 2019-11-18 | 1398/08/26 | 1398/08/27
23S3-PC-220-EL-370 | 23S3-ECC-CBC-027 | 220-EC-CBC-EL-001 | 220 | CBC | EL | LCS final function test | 1 | 2019-11-17 | 2019-11-18 | 1398/08/26 | 1398/08/27
23S3-PC-220-EL-470 | 23S3-ECC-CBC-027 | 220-EC-CBC-EL-001 | 220 | CBC | EL | feeder final checking | 1 | 2019-11-17 | 2019-11-18 | 1398/08/26 | 1398/08/27
23S3-PC-220-EL-740 | 23S3-ECC-CBC-027 | 220-EC-CBC-EL-001 | 220 | CBC | EL | motor free run & load test | 1 | 2019-11-17 | 2019-11-18 | 1398/08/26 | 1398/08/27
Concentrate Burner Cooling water Instrument System (220-EC-CBC-IN-001) | 23S3-ECC-CBC-027 | 220-EC-CBC-IN-001 | 220 | CBC | IN |  | 8 | 2019-11-18 | 2019-11-26 | 1398/08/27 | 1398/09/05
23S3-PC-220-IN-680 | 23S3-ECC-CBC-027 | 220-EC-CBC-IN-001 | 220 | CBC | IN | device calibration | 2 | 2019-11-18 | 2019-11-20 | 1398/08/27 | 1398/08/29
23S3-PC-220-IN-690 | 23S3-ECC-CBC-027 | 220-EC-CBC-IN-001 | 220 | CBC | IN | Instrument Cable Check and continuity megger test | 2 | 2019-11-19 | 2019-11-21 | 1398/08/28 | 1398/08/30
23S3-PC-220-IN-700 | 23S3-ECC-CBC-027 | 220-EC-CBC-IN-001 | 220 | CBC | IN | device installation final check and punch clearance | 1 | 2019-11-21 | 2019-11-22 | 1398/08/30 | 1398/09/01
23S3-PC-220-IN-710 | 23S3-ECC-CBC-027 | 220-EC-CBC-IN-001 | 220 | CBC | IN | IO and loop checking | 2 | 2019-11-22 | 2019-11-24 | 1398/09/01 | 1398/09/03
23S3-PC-220-IN-720 | 23S3-ECC-CBC-027 | 220-EC-CBC-IN-001 | 220 | CBC | IN | function test | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
Concentrate Burner Cooling water Mechanical System (220-EC-CBC-ME-001) | 23S3-ECC-CBC-027 | 220-EC-CBC-ME-001 | 220 | CBC | ME |  | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
23S3-PC-220-ME-240 | 23S3-ECC-CBC-027 | 220-EC-CBC-ME-001 | 220 | CBC | ME | Motor and Pump installation final check and punch clearance | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-220-ME-250 | 23S3-ECC-CBC-027 | 220-EC-CBC-ME-001 | 220 | CBC | ME | Flange Parallel Check and adjastment | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
23S3-PC-220-ME-270 | 23S3-ECC-CBC-027 | 220-EC-CBC-ME-001 | 220 | CBC | ME | Coupling pump and motor / load run test | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
Concentrate Burner Cooling water Piping System (220-EC-CBC-PI-001) | 23S3-ECC-CBC-027 | 220-EC-CBC-PI-001 | 220 | CBC | PI |  | 2 | 2019-11-24 | 2019-11-26 | 1398/09/03 | 1398/09/05
23S3-PC-220-PI-160 | 23S3-ECC-CBC-027 | 220-EC-CBC-PI-001 | 220 | CBC | PI | Punch Clearance | 2 | 2019-11-24 | 2019-11-26 | 1398/09/03 | 1398/09/05
230-COOLING WATER TO LAUNDER COOLING ELEMENTS (23S3-ECC-WCS-035) | 23S3-ECC-WCS-035 |  | 230 | WCS |  |  | 5 | 2019-11-22 | 2019-11-27 | 1398/09/01 | 1398/09/06
COOLING WATER TO LAUNDER COOLING ELEMENTS INSTRUMENT SYSTEM (230-EC-WCS-IN-001) | 23S3-ECC-WCS-035 | 230-EC-WCS-IN-001 | 230 | WCS | IN |  | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-230-IN-100 | 23S3-ECC-WCS-035 | 230-EC-WCS-IN-001 | 230 | WCS | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-230-IN-110 | 23S3-ECC-WCS-035 | 230-EC-WCS-IN-001 | 230 | WCS | IN | device calibration | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-230-IN-120 | 23S3-ECC-WCS-035 | 230-EC-WCS-IN-001 | 230 | WCS | IN | device installation final check and punch clearance | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-230-IN-130 | 23S3-ECC-WCS-035 | 230-EC-WCS-IN-001 | 230 | WCS | IN | IO and loop checking | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-230-IN-140 | 23S3-ECC-WCS-035 | 230-EC-WCS-IN-001 | 230 | WCS | IN | function test | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
COOLING WATER TO LAUNDER COOLING ELEMENTS PIPING SYSTEM (230-EC-WCS-PI-001) | 23S3-ECC-WCS-035 | 230-EC-WCS-PI-001 | 230 | WCS | PI |  | 2 | 2019-11-25 | 2019-11-27 | 1398/09/04 | 1398/09/06
23S3-PC-230-PI-150 | 23S3-ECC-WCS-035 | 230-EC-WCS-PI-001 | 230 | WCS | PI | Punch Clearance | 2 | 2019-11-25 | 2019-11-27 | 1398/09/04 | 1398/09/06
220 -FSF MECHANICAL & MEASURMENT SYSTEM (23S3-ECC-FSF-025) | 23S3-ECC-FSF-025 |  | 220 | FSF |  |  | 10 | 2019-11-21 | 2019-12-01 | 1398/08/30 | 1398/09/10
FSF Instrument System (220-EC-FSF-IN-001) | 23S3-ECC-FSF-025 | 220-EC-FSF-IN-001 | 220 | FSF | IN |  | 6 | 2019-11-25 | 2019-12-01 | 1398/09/04 | 1398/09/10
23S3-PC-220-IN-730 | 23S3-ECC-FSF-025 | 220-EC-FSF-IN-001 | 220 | FSF | IN | Instrument Cable Check and continuity megger test | 3 | 2019-11-25 | 2019-11-28 | 1398/09/04 | 1398/09/07
23S3-PC-220-IN-740 | 23S3-ECC-FSF-025 | 220-EC-FSF-IN-001 | 220 | FSF | IN | device calibration | 2 | 2019-11-26 | 2019-11-28 | 1398/09/05 | 1398/09/07
23S3-PC-220-IN-750 | 23S3-ECC-FSF-025 | 220-EC-FSF-IN-001 | 220 | FSF | IN | device installation final check and punch clearance | 2 | 2019-11-27 | 2019-11-29 | 1398/09/06 | 1398/09/08
23S3-PC-220-IN-760 | 23S3-ECC-FSF-025 | 220-EC-FSF-IN-001 | 220 | FSF | IN | IO and loop checking | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
23S3-PC-220-IN-770 | 23S3-ECC-FSF-025 | 220-EC-FSF-IN-001 | 220 | FSF | IN | function test | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
FSF Mechanical System (220-EC-FSF-ME-001) | 23S3-ECC-FSF-025 | 220-EC-FSF-ME-001 | 220 | FSF | ME |  | 6 | 2019-11-21 | 2019-11-27 | 1398/08/30 | 1398/09/06
23S3-PC-220-ME-275 | 23S3-ECC-FSF-025 | 220-EC-FSF-ME-001 | 220 | FSF | ME | Vendor at Site ( Autotec Mechanic Supervisor ) | 0 | 2019-11-21 |  | 1398/08/30
23S3-PC-220-ME-280 | 23S3-ECC-FSF-025 | 220-EC-FSF-ME-001 | 220 | FSF | ME | check for pre box-up and punch clearance | 5 | 2019-11-21 | 2019-11-26 | 1398/08/30 | 1398/09/05
23S3-PC-220-ME-290 | 23S3-ECC-FSF-025 | 220-EC-FSF-ME-001 | 220 | FSF | ME | final boxup | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
220-FSF BURNER SYSTEM (23S3-ECC-BUN-024) | 23S3-ECC-BUN-024 |  | 220 | BUN |  |  | 13 | 2019-11-22 | 2019-12-05 | 1398/09/01 | 1398/09/14
Settler Roof Oxygen Burners (220-EC-BUN-ME-001) | 23S3-ECC-BUN-024 | 220-EC-BUN-ME-001 | 220 | BUN | ME |  | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
23S3-PC-220-ME-300 | 23S3-ECC-BUN-024 | 220-EC-BUN-ME-001 | 220 | BUN | ME | Vendor At Site ( Outotec Burner Supervisor ) | 0 | 2019-11-23 |  | 1398/09/02
23S3-PC-220-ME-305 | 23S3-ECC-BUN-024 | 220-EC-BUN-ME-001 | 220 | BUN | ME | Burner And Accessory installation final check and punch clearance | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-220-ME-310 | 23S3-ECC-BUN-024 | 220-EC-BUN-ME-001 | 220 | BUN | ME | Burner adjustment | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
23S3-PC-220-ME-320 | 23S3-ECC-BUN-024 | 220-EC-BUN-ME-001 | 220 | BUN | ME | All hose connection installation final check and punch clearance | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
Settler Roof Oxygen Burners (220-EC-BUN-IN-001) | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-001 | 220 | BUN | IN |  | 10 | 2019-11-23 | 2019-12-03 | 1398/09/02 | 1398/09/12
23S3-PC-220-IN-780 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-001 | 220 | BUN | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-220-IN-790 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-001 | 220 | BUN | IN | device calibration | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
23S3-PC-220-IN-800 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-001 | 220 | BUN | IN | device installation final check and punch clearance | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
23S3-PC-220-IN-810 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-001 | 220 | BUN | IN | IO and loop checking | 6 | 2019-11-26 | 2019-12-02 | 1398/09/05 | 1398/09/11
23S3-PC-220-IN-820 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-001 | 220 | BUN | IN | function test | 6 | 2019-11-27 | 2019-12-03 | 1398/09/06 | 1398/09/12
Settler Wall Fuel Burners (220-EC-BUN-ME-002) | 23S3-ECC-BUN-024 | 220-EC-BUN-ME-002 | 220 | BUN | ME |  | 5 | 2019-11-22 | 2019-11-27 | 1398/09/01 | 1398/09/06
23S3-PC-220-ME-330 | 23S3-ECC-BUN-024 | 220-EC-BUN-ME-002 | 220 | BUN | ME | Burner And Accessory installation final check and punch clearance | 3 | 2019-11-22 | 2019-11-25 | 1398/09/01 | 1398/09/04
23S3-PC-220-ME-340 | 23S3-ECC-BUN-024 | 220-EC-BUN-ME-002 | 220 | BUN | ME | Burner adjustment | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-220-ME-350 | 23S3-ECC-BUN-024 | 220-EC-BUN-ME-002 | 220 | BUN | ME | All hose connection installation final check and punch clearance | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
Settler Wall Fuel Burners (220-EC-BUN-IN-002) | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-002 | 220 | BUN | IN |  | 13 | 2019-11-22 | 2019-12-05 | 1398/09/01 | 1398/09/14
23S3-PC-220-IN-830 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-002 | 220 | BUN | IN | Instrument Cable Check and continuity megger test | 3 | 2019-11-22 | 2019-11-25 | 1398/09/01 | 1398/09/04
23S3-PC-220-IN-840 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-002 | 220 | BUN | IN | device calibration | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-220-IN-850 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-002 | 220 | BUN | IN | device installation final check and punch clearance | 3 | 2019-11-26 | 2019-11-29 | 1398/09/05 | 1398/09/08
23S3-PC-220-IN-860 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-002 | 220 | BUN | IN | IO and loop checking | 6 | 2019-11-28 | 2019-12-04 | 1398/09/07 | 1398/09/13
23S3-PC-220-IN-870 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-002 | 220 | BUN | IN | function test | 6 | 2019-11-29 | 2019-12-05 | 1398/09/08 | 1398/09/14
220-FSF COMBUSTION AIR FAN SYSTEM (23S3-ECC-CAF-017) | 23S3-ECC-CAF-017 |  | 220 | CAF |  |  | 7 | 2019-11-07 | 2019-11-13 | 1398/08/16 | 1398/08/22
Combusition Air Fan Electrical System (220-EC-CAF-EL-001) | 23S3-ECC-CAF-017 | 220-EC-CAF-EL-001 | 220 | CAF | EL |  | 5 | 2019-11-08 | 2019-11-13 | 1398/08/17 | 1398/08/22
23S3-PC-220-EL-380 | 23S3-ECC-CAF-017 | 220-EC-CAF-EL-001 | 220 | CAF | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-220-EL-390 | 23S3-ECC-CAF-017 | 220-EC-CAF-EL-001 | 220 | CAF | EL | motor continuity megger test | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-220-EL-400 | 23S3-ECC-CAF-017 | 220-EC-CAF-EL-001 | 220 | CAF | EL | gland and connection final inspection | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-220-EL-410 | 23S3-ECC-CAF-017 | 220-EC-CAF-EL-001 | 220 | CAF | EL | LCS final function test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
23S3-PC-220-EL-420 | 23S3-ECC-CAF-017 | 220-EC-CAF-EL-001 | 220 | CAF | EL | feeder final checking | 1 | 2019-11-11 | 2019-11-12 | 1398/08/20 | 1398/08/21
23S3-PC-220-EL-430 | 23S3-ECC-CAF-017 | 220-EC-CAF-EL-001 | 220 | CAF | EL | motor free run test | 1 | 2019-11-12 | 2019-11-13 | 1398/08/21 | 1398/08/22
Combusition Air Fan Instrument System (220-EC-CAF-IN-001) | 23S3-ECC-CAF-017 | 220-EC-CAF-IN-001 | 220 | CAF | IN |  | 5 | 2019-11-09 | 2019-11-13 | 1398/08/18 | 1398/08/22
23S3-PC-220-IN-880 | 23S3-ECC-CAF-017 | 220-EC-CAF-IN-001 | 220 | CAF | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-220-IN-890 | 23S3-ECC-CAF-017 | 220-EC-CAF-IN-001 | 220 | CAF | IN | device calibration | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-220-IN-900 | 23S3-ECC-CAF-017 | 220-EC-CAF-IN-001 | 220 | CAF | IN | device installation final check and punch clearance | 2 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
23S3-PC-220-IN-910 | 23S3-ECC-CAF-017 | 220-EC-CAF-IN-001 | 220 | CAF | IN | IO and loop checking | 1 | 2019-11-11 | 2019-11-12 | 1398/08/20 | 1398/08/21
23S3-PC-220-IN-920 | 23S3-ECC-CAF-017 | 220-EC-CAF-IN-001 | 220 | CAF | IN | function test | 1 | 2019-11-12 | 2019-11-13 | 1398/08/21 | 1398/08/22
Combusition Air Fan Mechanical System (220-EC-CAF-ME-001) | 23S3-ECC-CAF-017 | 220-EC-CAF-ME-001 | 220 | CAF | ME |  | 4 | 2019-11-07 | 2019-11-11 | 1398/08/16 | 1398/08/20
23S3-PC-220-ME-360 | 23S3-ECC-CAF-017 | 220-EC-CAF-ME-001 | 220 | CAF | ME | Motor and Fan installation final check and punch clearance | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-220-ME-370 | 23S3-ECC-CAF-017 | 220-EC-CAF-ME-001 | 220 | CAF | ME | Flange Parallel Check and adjastment | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-220-ME-380 | 23S3-ECC-CAF-017 | 220-EC-CAF-ME-001 | 220 | CAF | ME | duct work final check and punch clearance | 3 | 2019-11-08 | 2019-11-11 | 1398/08/17 | 1398/08/20
23S3-PC-220-ME-390 | 23S3-ECC-CAF-017 | 220-EC-CAF-ME-001 | 220 | CAF | ME | Coupling fan / load run test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
220-FSF BY-PASS DAMPER (23S3-ECC-BDP-028) | 23S3-ECC-BDP-028 |  | 220 | BDP |  |  | 2 | 2019-11-09 | 2019-11-11 | 1398/08/24 | 1398/08/26
By-Pass Damper Mechanical System (220-EC-BPD-ME-001) | 23S3-ECC-BDP-028 | 220-EC-BPD-ME-001 | 220 | BDP | ME |  | 2 | 2019-11-09 | 2019-11-11 | 1398/08/24 | 1398/08/26
23S3-PC-220-ME-410 | 23S3-ECC-BDP-028 | 220-EC-BPD-ME-001 | 220 | BDP | ME | final check and punch clearance | 1 | 2019-11-15 | 2019-11-16 | 1398/08/24 | 1398/08/25
23S3-PC-220-ME-420 | 23S3-ECC-BDP-028 | 220-EC-BPD-ME-001 | 220 | BDP | ME | final boxup | 1 | 2019-11-16 | 2019-11-17 | 1398/08/25 | 1398/08/26
225-WHB (MILESTONE) | WHB MILESTONE |  | 225 | MILESTONE |  |  | 0 | 2019-12-20 | 2019-12-20 | 1398/09/29 | 1398/09/29
23S3-PC-225-MLS-100 | WHB MILESTONE | WHB MILESTONE | 225 | MILESTONE |  | Vendor At Site ( Outotec Process Supervisor ) | 0 | 2019-12-20 |  | 1398/09/29
23S3-PC-225-MLS-110 | WHB MILESTONE | WHB MILESTONE | 225 | MILESTONE | EL | Electrical | 0 |  | 2019-12-20 |  | 1398/09/29
23S3-PC-225-MLS-120 | WHB MILESTONE | WHB MILESTONE | 225 | MILESTONE | IN | Instrument | 0 |  | 2019-12-20 |  | 1398/09/29
23S3-PC-225-MLS-130 | WHB MILESTONE | WHB MILESTONE | 225 | MILESTONE | ME | Mechanical | 0 |  | 2019-12-20 |  | 1398/09/29
23S3-PC-225-MLS-140 | WHB MILESTONE | WHB MILESTONE | 225 | MILESTONE | PI | Piping | 0 |  | 2019-12-20 |  | 1398/09/29
225-WHB BLOW DOWN AND BLEED WATER SYSTEM (23S3-ECC-BDW-030) | 23S3-ECC-BDW-030 |  | 225 | BDW |  |  | 6 | 2019-11-20 | 2019-11-26 | 1398/08/29 | 1398/09/05
FSF Off Gas Handling Bleed Electrical System (225-EC-BDW-EL-001) | 23S3-ECC-BDW-030 | 225-EC-BDW-EL-001 | 225 | BDW | EL |  | 2 | 2019-11-24 | 2019-11-26 | 1398/09/03 | 1398/09/05
23S3-PC-225-EL-300 | 23S3-ECC-BDW-030 | 225-EC-BDW-EL-001 | 225 | BDW | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
23S3-PC-225-EL-310 | 23S3-ECC-BDW-030 | 225-EC-BDW-EL-001 | 225 | BDW | EL | motor continuity megger test | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
23S3-PC-225-EL-320 | 23S3-ECC-BDW-030 | 225-EC-BDW-EL-001 | 225 | BDW | EL | gland and connection final inspection | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
23S3-PC-225-EL-330 | 23S3-ECC-BDW-030 | 225-EC-BDW-EL-001 | 225 | BDW | EL | LCS final function test | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-225-EL-460 | 23S3-ECC-BDW-030 | 225-EC-BDW-EL-001 | 225 | BDW | EL | feeder final checking | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-225-EL-470 | 23S3-ECC-BDW-030 | 225-EC-BDW-EL-001 | 225 | BDW | EL | motor free run & load test | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
FSF Off Gas Handling Bleed Instrument System (225-EC-BDW-IN-001) | 23S3-ECC-BDW-030 | 225-EC-BDW-IN-001 | 225 | BDW | IN |  | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-225-IN-100 | 23S3-ECC-BDW-030 | 225-EC-BDW-IN-001 | 225 | BDW | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-225-IN-110 | 23S3-ECC-BDW-030 | 225-EC-BDW-IN-001 | 225 | BDW | IN | device calibration | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-225-IN-120 | 23S3-ECC-BDW-030 | 225-EC-BDW-IN-001 | 225 | BDW | IN | device installation final check and punch clearance | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-225-IN-130 | 23S3-ECC-BDW-030 | 225-EC-BDW-IN-001 | 225 | BDW | IN | IO and loop checking | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-225-IN-140 | 23S3-ECC-BDW-030 | 225-EC-BDW-IN-001 | 225 | BDW | IN | function test | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
FSF Off Gas Handling Bleed Mechanical System (225-EC-BDW-ME-001) | 23S3-ECC-BDW-030 | 225-EC-BDW-ME-001 | 225 | BDW | ME |  | 4 | 2019-11-20 | 2019-11-24 | 1398/08/29 | 1398/09/03
23S3-PC-225-ME-100 | 23S3-ECC-BDW-030 | 225-EC-BDW-ME-001 | 225 | BDW | ME | Motor and Pump installation final check and punch clearance | 1 | 2019-11-20 | 2019-11-21 | 1398/08/29 | 1398/08/30
23S3-PC-225-ME-110 | 23S3-ECC-BDW-030 | 225-EC-BDW-ME-001 | 225 | BDW | ME | Flange Parallel Check and adjastment | 1 | 2019-11-21 | 2019-11-22 | 1398/08/30 | 1398/09/01
23S3-PC-225-ME-120 | 23S3-ECC-BDW-030 | 225-EC-BDW-ME-001 | 225 | BDW | ME | Pump Adjustment | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-225-ME-290 | 23S3-ECC-BDW-030 | 225-EC-BDW-ME-001 | 225 | BDW | ME | Coupling pump and motor / load run test | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
FSF Off Gas Handling Bleed Piping System (225-EC-BDW-PI-001) | 23S3-ECC-BDW-030 | 225-EC-BDW-PI-001 | 225 | BDW | PI |  | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
23S3-PC-225-PI-100 | 23S3-ECC-BDW-030 | 225-EC-BDW-PI-001 | 225 | BDW | PI | Punch Clearance | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
225-ESP (MILESTONE) | ESP MILESTONE |  | 225 | MILESTONE |  |  | 9 | 2019-11-21 | 2019-11-30 | 1398/08/30 | 1398/09/09
23S3-PC-225-MLS-150 | ESP MILESTONE | ESP MILESTONE | 225 | MILESTONE | EL | Electrical | 0 |  | 2019-11-30 |  | 1398/09/09
23S3-PC-225-MLS-160 | ESP MILESTONE | ESP MILESTONE | 225 | MILESTONE | IN | Instrument | 0 |  | 2019-11-28 |  | 1398/09/07
23S3-PC-225-MLS-170 | ESP MILESTONE | ESP MILESTONE | 225 | MILESTONE | ME | Mechanical | 0 |  | 2019-11-21 |  | 1398/08/30
23S3-PC-225-MLS-180 | ESP MILESTONE | ESP MILESTONE | 225 | MILESTONE | PI | Piping | 0 |  | 2019-11-25 |  | 1398/09/04
225-WHB &ESP MEASUREMENT AND DUCT WORK SYSTEM (23S3-ECC-OGF-034) | 23S3-ECC-OGF-034 |  | 225 | OGF |  |  | 16 | 2019-11-30 | 2019-12-16 | 1398/09/09 | 1398/09/25
FSF Gas Handling & Dust Collection Duct Work Electrical System (225-EC-OGF-EL-001) | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-001 | 225 | OGF | EL |  | 3 | 2019-12-02 | 2019-12-05 | 1398/09/11 | 1398/09/14
23S3-PC-225-EL-340 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-001 | 225 | OGF | EL | Electrical Cable Check and continuity megger test | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-225-EL-350 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-001 | 225 | OGF | EL | motor continuity megger test | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-225-EL-360 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-001 | 225 | OGF | EL | gland and connection final inspection | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-225-EL-370 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-001 | 225 | OGF | EL | LCS final function test | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-225-EL-380 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-001 | 225 | OGF | EL | feeder final checking | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-225-EL-390 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-001 | 225 | OGF | EL | Fan free run & load test | 1 | 2019-12-04 | 2019-12-05 | 1398/09/13 | 1398/09/14
FSF Gas Handling & Dust Collection Duct Work Electrical System (225-EC-OGF-EL-002) | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-002 | 225 | OGF | EL |  | 7 | 2019-12-07 | 2019-12-14 | 1398/09/16 | 1398/09/23
23S3-PC-225-EL-400 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-002 | 225 | OGF | EL | Electrical Cable Check and continuity megger test | 1 | 2019-12-07 | 2019-12-08 | 1398/09/16 | 1398/09/17
23S3-PC-225-EL-410 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-002 | 225 | OGF | EL | motor continuity megger test | 1 | 2019-12-08 | 2019-12-09 | 1398/09/17 | 1398/09/18
23S3-PC-225-EL-420 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-002 | 225 | OGF | EL | gland and connection final inspection | 1 | 2019-12-09 | 2019-12-10 | 1398/09/18 | 1398/09/19
23S3-PC-225-EL-430 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-002 | 225 | OGF | EL | LCS final function test | 1 | 2019-12-10 | 2019-12-11 | 1398/09/19 | 1398/09/20
23S3-PC-225-EL-440 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-002 | 225 | OGF | EL | feeder final checking | 1 | 2019-12-11 | 2019-12-12 | 1398/09/20 | 1398/09/21
23S3-PC-225-EL-450 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-002 | 225 | OGF | EL | Fan free run & load test | 2 | 2019-12-12 | 2019-12-14 | 1398/09/21 | 1398/09/23
FSF Gas Handling & Dust Collection Duct Work Instrument System (225-EC-OGF-IN-001) | 23S3-ECC-OGF-034 | 225-EC-OGF-IN-001 | 225 | OGF | IN |  | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
23S3-PC-225-IN-150 | 23S3-ECC-OGF-034 | 225-EC-OGF-IN-001 | 225 | OGF | IN | Instrument Cable Check and continuity megger test | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-225-IN-160 | 23S3-ECC-OGF-034 | 225-EC-OGF-IN-001 | 225 | OGF | IN | device calibration | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-225-IN-170 | 23S3-ECC-OGF-034 | 225-EC-OGF-IN-001 | 225 | OGF | IN | device installation final check and punch clearance | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-225-IN-180 | 23S3-ECC-OGF-034 | 225-EC-OGF-IN-001 | 225 | OGF | IN | IO and loop checking | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-225-IN-190 | 23S3-ECC-OGF-034 | 225-EC-OGF-IN-001 | 225 | OGF | IN | function test | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
FSF Gas Handling & Dust Collection Duct Work Mechanical System (225-EC-OGF-ME-001) | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-001 | 225 | OGF | ME |  | 5 | 2019-12-06 | 2019-12-11 | 1398/09/15 | 1398/09/20
23S3-PC-225-ME-150 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-001 | 225 | OGF | ME | duct work final check and punch clearance | 5 | 2019-12-06 | 2019-12-11 | 1398/09/15 | 1398/09/20
FSF Gas Handling & Dust Collection Duct Work Mechanical System (225-EC-OGF-ME-002) | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-002 | 225 | OGF | ME |  | 3 | 2019-11-30 | 2019-12-03 | 1398/09/09 | 1398/09/12
23S3-PC-225-ME-170 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-002 | 225 | OGF | ME | Motor and Fan installation final check and punch clearance | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-225-ME-180 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-002 | 225 | OGF | ME | Flange Parallel Check and adjastment | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-225-ME-190 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-002 | 225 | OGF | ME | Fan Adjustment | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
23S3-PC-225-ME-200 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-002 | 225 | OGF | ME | Coupling Fan and motor / load run test | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
FSF Gas Handling & Dust Collection Duct Work Mechanical System (225-EC-OGF-ME-003) | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-003 | 225 | OGF | ME |  | 16 | 2019-11-30 | 2019-12-16 | 1398/09/09 | 1398/09/25
23S3-PC-225-ME-210 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-003 | 225 | OGF | ME | Motor and Fan installation final check and punch clearance | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
23S3-PC-225-ME-220 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-003 | 225 | OGF | ME | Flange Parallel Check and adjastment | 3 | 2019-12-02 | 2019-12-05 | 1398/09/11 | 1398/09/14
23S3-PC-225-ME-230 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-003 | 225 | OGF | ME | Fan Adjustment | 2 | 2019-12-05 | 2019-12-07 | 1398/09/14 | 1398/09/16
23S3-PC-225-ME-240 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-003 | 225 | OGF | ME | Coupling Fan & Motor / load run test | 2 | 2019-12-14 | 2019-12-16 | 1398/09/23 | 1398/09/25
FSF Gas Handling & Dust Collection Duct Work Mechanical System (225-EC-OGF-ME-004) | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-004 | 225 | OGF | ME |  | 5 | 2019-12-06 | 2019-12-11 | 1398/09/15 | 1398/09/20
23S3-PC-225-ME-270 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-004 | 225 | OGF | ME | duct work final check and punch clearance | 5 | 2019-12-06 | 2019-12-11 | 1398/09/15 | 1398/09/20
220-PROCESS AIR FAN/OXYGEN ENRICHMENT (23S3-ECC-PAF-015) | 23S3-ECC-PAF-015 |  | 220 | PAF |  |  | 13 | 2019-11-23 | 2019-12-06 | 1398/09/02 | 1398/09/15
Process Air Fan/Oxygen Enrichment Electrical System (220-EC-PAF-EL-001) | 23S3-ECC-PAF-015 | 220-EC-PAF-EL-001 | 220 | PAF | EL |  | 2 | 2019-11-26 | 2019-11-28 | 1398/09/05 | 1398/09/07
23S3-PC-220-EL-500 | 23S3-ECC-PAF-015 | 220-EC-PAF-EL-001 | 220 | PAF | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-510 | 23S3-ECC-PAF-015 | 220-EC-PAF-EL-001 | 220 | PAF | EL | motor continuity megger test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-520 | 23S3-ECC-PAF-015 | 220-EC-PAF-EL-001 | 220 | PAF | EL | gland and connection final inspection | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-530 | 23S3-ECC-PAF-015 | 220-EC-PAF-EL-001 | 220 | PAF | EL | LCS final function test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-540 | 23S3-ECC-PAF-015 | 220-EC-PAF-EL-001 | 220 | PAF | EL | feeder final checking | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-550 | 23S3-ECC-PAF-015 | 220-EC-PAF-EL-001 | 220 | PAF | EL | Fan free run & load test | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
Process Air Fan/Oxygen Enrichment Instrument System (220-EC-PAF-IN-001) | 23S3-ECC-PAF-015 | 220-EC-PAF-IN-001 | 220 | PAF | IN |  | 7 | 2019-11-24 | 2019-12-01 | 1398/09/03 | 1398/09/10
23S3-PC-220-IN-930 | 23S3-ECC-PAF-015 | 220-EC-PAF-IN-001 | 220 | PAF | IN | Instrument Cable Check and continuity megger test | 2 | 2019-11-24 | 2019-11-26 | 1398/09/03 | 1398/09/05
23S3-PC-220-IN-940 | 23S3-ECC-PAF-015 | 220-EC-PAF-IN-001 | 220 | PAF | IN | device calibration | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-220-IN-950 | 23S3-ECC-PAF-015 | 220-EC-PAF-IN-001 | 220 | PAF | IN | device installation final check and punch clearance | 2 | 2019-11-26 | 2019-11-28 | 1398/09/05 | 1398/09/07
23S3-PC-220-IN-960 | 23S3-ECC-PAF-015 | 220-EC-PAF-IN-001 | 220 | PAF | IN | IO and loop checking | 3 | 2019-11-27 | 2019-11-30 | 1398/09/06 | 1398/09/09
23S3-PC-220-IN-970 | 23S3-ECC-PAF-015 | 220-EC-PAF-IN-001 | 220 | PAF | IN | function test | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
Process Air Fan/Oxygen Enrichment Mechanical System (220-EC-PAF-ME-001) | 23S3-ECC-PAF-015 | 220-EC-PAF-ME-001 | 220 | PAF | ME |  | 13 | 2019-11-23 | 2019-12-06 | 1398/09/02 | 1398/09/15
23S3-PC-220-ME-460 | 23S3-ECC-PAF-015 | 220-EC-PAF-ME-001 | 220 | PAF | ME | motor and fan installation final check and punch clearance | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-220-ME-470 | 23S3-ECC-PAF-015 | 220-EC-PAF-ME-001 | 220 | PAF | ME | duct work final check and punch clearance | 2 | 2019-11-23 | 2019-11-25 | 1398/09/02 | 1398/09/04
23S3-PC-220-ME-480 | 23S3-ECC-PAF-015 | 220-EC-PAF-ME-001 | 220 | PAF | ME | Flange Parallel Check and adjastment | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-220-ME-970 | 23S3-ECC-PAF-015 | 220-EC-PAF-ME-001 | 220 | PAF | ME | Fan Adjustment | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
23S3-PC-220-ME-980 | 23S3-ECC-PAF-015 | 220-EC-PAF-ME-001 | 220 | PAF | ME | Coupling Fan & Motor / load run test | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
23S3-PC-220-ME-990 | 23S3-ECC-PAF-015 | 220-EC-PAF-ME-001 | 220 | PAF | ME | check for pre box-up and punch clearance | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
23S3-PC-220-ME-995 | 23S3-ECC-PAF-015 | 220-EC-PAF-ME-001 | 220 | PAF | ME | final boxup | 2 | 2019-12-04 | 2019-12-06 | 1398/09/13 | 1398/09/15
220-CONCENTRATE BURNER WITH FEEDING (23S3-ECC-CBU-023) | 23S3-ECC-CBU-023 |  | 220 | CBU |  |  | 10 | 2019-11-24 | 2019-12-04 | 1398/09/03 | 1398/09/13
Concentrate Burner With Feeding Electrical System (220-EC-CBU-EL-001) | 23S3-ECC-CBU-023 | 220-EC-CBU-EL-001 | 220 | CBU | EL |  | 2 | 2019-11-26 | 2019-11-28 | 1398/09/05 | 1398/09/07
23S3-PC-220-EL-560 | 23S3-ECC-CBU-023 | 220-EC-CBU-EL-001 | 220 | CBU | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-570 | 23S3-ECC-CBU-023 | 220-EC-CBU-EL-001 | 220 | CBU | EL | motor continuity megger test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-580 | 23S3-ECC-CBU-023 | 220-EC-CBU-EL-001 | 220 | CBU | EL | gland and connection final inspection | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-590 | 23S3-ECC-CBU-023 | 220-EC-CBU-EL-001 | 220 | CBU | EL | LCS final function test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-600 | 23S3-ECC-CBU-023 | 220-EC-CBU-EL-001 | 220 | CBU | EL | feeder final checking | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-610 | 23S3-ECC-CBU-023 | 220-EC-CBU-EL-001 | 220 | CBU | EL | Fan free run & load test | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
Concentrate Burner With Feeding Instrument System (220-EC-CBU-IN-001) | 23S3-ECC-CBU-023 | 220-EC-CBU-IN-001 | 220 | CBU | IN |  | 10 | 2019-11-24 | 2019-12-04 | 1398/09/03 | 1398/09/13
23S3-PC-220-IN-0980 | 23S3-ECC-CBU-023 | 220-EC-CBU-IN-001 | 220 | CBU | IN | Instrument Cable Check and continuity megger test | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
23S3-PC-220-IN-0990 | 23S3-ECC-CBU-023 | 220-EC-CBU-IN-001 | 220 | CBU | IN | device calibration | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-IN-1000 | 23S3-ECC-CBU-023 | 220-EC-CBU-IN-001 | 220 | CBU | IN | device installation final check and punch clearance | 2 | 2019-11-27 | 2019-11-29 | 1398/09/06 | 1398/09/08
23S3-PC-220-IN-1010 | 23S3-ECC-CBU-023 | 220-EC-CBU-IN-001 | 220 | CBU | IN | IO and loop checking | 4 | 2019-11-29 | 2019-12-03 | 1398/09/08 | 1398/09/12
23S3-PC-220-IN-1020 | 23S3-ECC-CBU-023 | 220-EC-CBU-IN-001 | 220 | CBU | IN | function test | 5 | 2019-11-29 | 2019-12-04 | 1398/09/08 | 1398/09/13
Concentrate Burner With Feeding Mechanical System (220-EC-CBU-ME-001) | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-001 | 220 | CBU | ME |  | 6 | 2019-11-24 | 2019-11-30 | 1398/09/03 | 1398/09/09
23S3-PC-220-ME-490 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-001 | 220 | CBU | ME | Vendor at Site ( Outotec Mechanic & Process supervisor ) | 0 | 2019-11-24 |  | 1398/09/03
23S3-PC-220-ME-495 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-001 | 220 | CBU | ME | Burner And Accessory installation final check and punch clearance | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
23S3-PC-220-ME-500 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-001 | 220 | CBU | ME | Burner adjustment | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-220-ME-540 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-001 | 220 | CBU | ME | All hose connection installation final check and punch clearance | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
Concentrate Burner With Feeding Mechanical System (220-EC-CBU-ME-002) | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-002 | 220 | CBU | ME |  | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
23S3-PC-220-ME-550 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-002 | 220 | CBU | ME | Conveyor And Accessory installation final check and punch clearance | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
23S3-PC-220-ME-560 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-002 | 220 | CBU | ME | Conveyor adjustment | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
Concentrate Burner With Feeding Mechanical System (220-EC-CBU-ME-003) | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-003 | 220 | CBU | ME |  | 5 | 2019-11-24 | 2019-11-29 | 1398/09/03 | 1398/09/08
23S3-PC-220-ME-610 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-003 | 220 | CBU | ME | motor and fan installation final check and punch clearance | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
23S3-PC-220-ME-620 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-003 | 220 | CBU | ME | duct work final check and punch clearance | 2 | 2019-11-24 | 2019-11-26 | 1398/09/03 | 1398/09/05
23S3-PC-220-ME-630 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-003 | 220 | CBU | ME | Flange Parallel Check and adjastment | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-ME-640 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-003 | 220 | CBU | ME | Fan Adjustment | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-220-ME-650 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-003 | 220 | CBU | ME | Coupling the motor and no load run test | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
220-LOW PRESSURE OXYGEN SYSTEM (23S3-ECC-LPO-016) | 23S3-ECC-LPO-016 |  | 220 | LPO |  |  | 3 | 2019-11-30 | 2019-12-03 | 1398/09/09 | 1398/09/12
Low Pressure Oxygen Instrument System (220-EC-LPO-IN-001) | 23S3-ECC-LPO-016 | 220-EC-LPO-IN-001 | 220 | LPO | IN |  | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
23S3-PC-220-IN-1030 | 23S3-ECC-LPO-016 | 220-EC-LPO-IN-001 | 220 | LPO | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-220-IN-1040 | 23S3-ECC-LPO-016 | 220-EC-LPO-IN-001 | 220 | LPO | IN | device calibration | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-220-IN-1050 | 23S3-ECC-LPO-016 | 220-EC-LPO-IN-001 | 220 | LPO | IN | device installation final check and punch clearance | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-220-IN-1060 | 23S3-ECC-LPO-016 | 220-EC-LPO-IN-001 | 220 | LPO | IN | IO and loop checking | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-220-IN-1070 | 23S3-ECC-LPO-016 | 220-EC-LPO-IN-001 | 220 | LPO | IN | function test | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
Low Pressure Oxygen Mechanical System (220-EC-LPO-ME-001) | 23S3-ECC-LPO-016 | 220-EC-LPO-ME-001 | 220 | LPO | ME |  | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-220-ME-670 | 23S3-ECC-LPO-016 | 220-EC-LPO-ME-001 | 220 | LPO | ME | Lance And Accessory installation final check and punch clearance | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
Low Pressure Oxygen Piping System (220-EC-LPO-PI-001) | 23S3-ECC-LPO-016 | 220-EC-LPO-PI-001 | 220 | LPO | PI |  | 3 | 2019-11-30 | 2019-12-03 | 1398/09/09 | 1398/09/12
23S3-PC-220-PI-170 | 23S3-ECC-LPO-016 | 220-EC-LPO-PI-001 | 220 | LPO | PI | Punch Clearance | 3 | 2019-11-30 | 2019-12-03 | 1398/09/09 | 1398/09/12
220-FSF OXYGEN HIGH PRESSURE NET WORK (23S3-ECC-OHP-022) | 23S3-ECC-OHP-022 |  | 220 | OHP |  |  | 11 | 2019-11-23 | 2019-12-04 | 1398/09/02 | 1398/09/13
FSF Oxygen High Pressure Net Work Instrument System (220-EC-OHP-IN-001) | 23S3-ECC-OHP-022 | 220-EC-OHP-IN-001 | 220 | OHP | IN |  | 4 | 2019-11-30 | 2019-12-04 | 1398/09/09 | 1398/09/13
23S3-PC-220-IN-1080 | 23S3-ECC-OHP-022 | 220-EC-OHP-IN-001 | 220 | OHP | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-220-IN-1090 | 23S3-ECC-OHP-022 | 220-EC-OHP-IN-001 | 220 | OHP | IN | device calibration | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-220-IN-1100 | 23S3-ECC-OHP-022 | 220-EC-OHP-IN-001 | 220 | OHP | IN | device installation final check and punch clearance | 2 | 2019-12-01 | 2019-12-03 | 1398/09/10 | 1398/09/12
23S3-PC-220-IN-1110 | 23S3-ECC-OHP-022 | 220-EC-OHP-IN-001 | 220 | OHP | IN | IO and loop checking | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-220-IN-1120 | 23S3-ECC-OHP-022 | 220-EC-OHP-IN-001 | 220 | OHP | IN | function test | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
FSF Oxygen High Pressure Net Work Piping System (220-EC-OHP-PI-001) | 23S3-ECC-OHP-022 | 220-EC-OHP-PI-001 | 220 | OHP | PI |  | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
23S3-PC-220-PI-180 | 23S3-ECC-OHP-022 | 220-EC-OHP-PI-001 | 220 | OHP | PI | Punch Clearance | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
220-FSF VENTILATION DUKT WORK MODIFICATION (23S3-ECC-VDW-029) | 23S3-ECC-VDW-029 |  | 220 | VDW |  |  | 6 | 2019-11-23 | 2019-11-29 | 1398/09/02 | 1398/09/08
FSF ventilation Dukt Work Modification Instrument System (220-EC-VDW-IN-001) | 23S3-ECC-VDW-029 | 220-EC-VDW-IN-001 | 220 | VDW | IN |  | 3 | 2019-11-25 | 2019-11-28 | 1398/09/04 | 1398/09/07
23S3-PC-220-IN-1130 | 23S3-ECC-VDW-029 | 220-EC-VDW-IN-001 | 220 | VDW | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-220-IN-1140 | 23S3-ECC-VDW-029 | 220-EC-VDW-IN-001 | 220 | VDW | IN | device calibration | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-220-IN-1150 | 23S3-ECC-VDW-029 | 220-EC-VDW-IN-001 | 220 | VDW | IN | device installation final check and punch clearance | 2 | 2019-11-26 | 2019-11-28 | 1398/09/05 | 1398/09/07
23S3-PC-220-IN-1160 | 23S3-ECC-VDW-029 | 220-EC-VDW-IN-001 | 220 | VDW | IN | IO and loop checking | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-220-IN-1170 | 23S3-ECC-VDW-029 | 220-EC-VDW-IN-001 | 220 | VDW | IN | function test | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
FSF ventilation Dukt Work Modification Mechanical System (220-EC-VDW-ME-001) | 23S3-ECC-VDW-029 | 220-EC-VDW-ME-001 | 220 | VDW | ME |  | 6 | 2019-11-23 | 2019-11-29 | 1398/09/02 | 1398/09/08
23S3-PC-220-ME-680 | 23S3-ECC-VDW-029 | 220-EC-VDW-ME-001 | 220 | VDW | ME | duct work final check and punch clearance | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
23S3-PC-220-ME-690 | 23S3-ECC-VDW-029 | 220-EC-VDW-ME-001 | 220 | VDW | ME | check for pre box-up and punch clearance | 2 | 2019-11-26 | 2019-11-28 | 1398/09/05 | 1398/09/07
23S3-PC-220-ME-700 | 23S3-ECC-VDW-029 | 220-EC-VDW-ME-001 | 220 | VDW | ME | Final Box-up | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
220-Concentrate BIN & LIW Feeding (23S3-ECC-CBL-013) | 23S3-ECC-CBL-013 |  | 220 | CBL |  |  | 18 | 2019-11-24 | 2019-12-12 | 1398/09/03 | 1398/09/21
Concentrate BIN & LIW FeedingElectrical System (220-EC-CBL-EL-001) | 23S3-ECC-CBL-013 | 220-EC-CBL-EL-001 | 220 | CBL | EL |  | 3 | 2019-11-25 | 2019-11-28 | 1398/09/04 | 1398/09/07
23S3-PC-220-EL-620 | 23S3-ECC-CBL-013 | 220-EC-CBL-EL-001 | 220 | CBL | EL | Electrical Cable Check and continuity megger test | 2 | 2019-11-25 | 2019-11-27 | 1398/09/04 | 1398/09/06
23S3-PC-220-EL-630 | 23S3-ECC-CBL-013 | 220-EC-CBL-EL-001 | 220 | CBL | EL | motor continuity megger test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-640 | 23S3-ECC-CBL-013 | 220-EC-CBL-EL-001 | 220 | CBL | EL | gland and connection final inspection | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-650 | 23S3-ECC-CBL-013 | 220-EC-CBL-EL-001 | 220 | CBL | EL | LCS final function test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-660 | 23S3-ECC-CBL-013 | 220-EC-CBL-EL-001 | 220 | CBL | EL | feeder final checking | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-670 | 23S3-ECC-CBL-013 | 220-EC-CBL-EL-001 | 220 | CBL | EL | motor free run test | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
Concentrate BIN & LIW FeedingInstrument System (220-EC-CBL-IN-001) | 23S3-ECC-CBL-013 | 220-EC-CBL-IN-001 | 220 | CBL | IN |  | 10 | 2019-12-02 | 2019-12-12 | 1398/09/11 | 1398/09/21
23S3-PC-220-IN-1180 | 23S3-ECC-CBL-013 | 220-EC-CBL-IN-001 | 220 | CBL | IN | Instrument Cable Check and continuity megger test | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
23S3-PC-220-IN-1190 | 23S3-ECC-CBL-013 | 220-EC-CBL-IN-001 | 220 | CBL | IN | device calibration | 2 | 2019-12-03 | 2019-12-05 | 1398/09/12 | 1398/09/14
23S3-PC-220-IN-1200 | 23S3-ECC-CBL-013 | 220-EC-CBL-IN-001 | 220 | CBL | IN | device installation final check and punch clearance | 3 | 2019-12-04 | 2019-12-07 | 1398/09/13 | 1398/09/16
23S3-PC-220-IN-1210 | 23S3-ECC-CBL-013 | 220-EC-CBL-IN-001 | 220 | CBL | IN | IO and loop checking | 2 | 2019-12-06 | 2019-12-08 | 1398/09/15 | 1398/09/17
23S3-PC-220-IN-1220 | 23S3-ECC-CBL-013 | 220-EC-CBL-IN-001 | 220 | CBL | IN | function test | 5 | 2019-12-07 | 2019-12-12 | 1398/09/16 | 1398/09/21
Concentrate BIN & LIW FeedingMechanical System (220-EC-CBL-ME-001) | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-001 | 220 | CBL | ME |  | 12 | 2019-11-25 | 2019-12-07 | 1398/09/04 | 1398/09/16
23S3-PC-220-ME-710 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-001 | 220 | CBL | ME | duct work final check and punch clearance | 5 | 2019-11-25 | 2019-11-30 | 1398/09/04 | 1398/09/09
23S3-PC-220-ME-740 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-001 | 220 | CBL | ME | Motor and Fan installation final check and punch clearance | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-220-ME-750 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-001 | 220 | CBL | ME | Flange Parallel Check and adjastment | 2 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-220-ME-760 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-001 | 220 | CBL | ME | Valve Check | 5 | 2019-12-01 | 2019-12-06 | 1398/09/10 | 1398/09/15
23S3-PC-220-ME-770 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-001 | 220 | CBL | ME | Coupling fan / load run test | 1 | 2019-12-06 | 2019-12-07 | 1398/09/15 | 1398/09/16
Concentrate BIN & LIW FeedingMechanical System (220-EC-CBL-ME-002) | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-002 | 220 | CBL | ME |  | 7 | 2019-11-25 | 2019-12-02 | 1398/09/04 | 1398/09/11
23S3-PC-220-ME-780 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-002 | 220 | CBL | ME | check for pre box-up and punch clearance | 5 | 2019-11-25 | 2019-11-30 | 1398/09/04 | 1398/09/09
23S3-PC-220-ME-800 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-002 | 220 | CBL | ME | Valve Check | 3 | 2019-11-27 | 2019-11-30 | 1398/09/06 | 1398/09/09
23S3-PC-220-ME-810 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-002 | 220 | CBL | ME | Final Box-up | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
Concentrate BIN & LIW FeedingMechanical System (220-EC-CBL-ME-003) | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-003 | 220 | CBL | ME |  | 11 | 2019-11-25 | 2019-12-06 | 1398/09/04 | 1398/09/15
23S3-PC-220-ME-850 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-003 | 220 | CBL | ME | duct work final check and punch clearance | 3 | 2019-11-25 | 2019-11-28 | 1398/09/04 | 1398/09/07
23S3-PC-220-ME-860 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-003 | 220 | CBL | ME | check for pre box-up and punch clearance | 3 | 2019-11-28 | 2019-12-01 | 1398/09/07 | 1398/09/10
23S3-PC-220-ME-870 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-003 | 220 | CBL | ME | Final Box-up | 2 | 2019-12-01 | 2019-12-03 | 1398/09/10 | 1398/09/12
23S3-PC-220-ME-880 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-003 | 220 | CBL | ME | Motor and Fan installation final check and punch clearance | 3 | 2019-12-02 | 2019-12-05 | 1398/09/11 | 1398/09/14
23S3-PC-220-ME-890 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-003 | 220 | CBL | ME | Flange Parallel Check and adjastment | 2 | 2019-12-04 | 2019-12-06 | 1398/09/13 | 1398/09/15
23S3-PC-220-ME-900 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-003 | 220 | CBL | ME | Motor load run test | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
Concentrate BIN & LIW Feeding Piping System (220-EC-CBL-PI-001) | 23S3-ECC-CBL-013 | 220-EC-CBL-PI-001 | 220 | CBL | PI |  | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
23S3-PC-220-PI-200 | 23S3-ECC-CBL-013 | 220-EC-CBL-PI-001 | 220 | CBL | PI | Punch Clearance | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
220-FLUE DUST BIN & LIW FEEDING (23S3-ECC-FDL-014) | 23S3-ECC-FDL-014 |  | 220 | FDL |  |  | 11 | 2019-11-26 | 2019-12-06 | 1398/09/05 | 1398/09/15
Flue Dust Bin & Liw Feeding Electrical System (220-EC-FDL-EL-001) | 23S3-ECC-FDL-014 | 220-EC-FDL-EL-001 | 220 | FDL | EL |  | 8 | 2019-11-29 | 2019-12-06 | 1398/09/08 | 1398/09/15
23S3-PC-220-EL-680 | 23S3-ECC-FDL-014 | 220-EC-FDL-EL-001 | 220 | FDL | EL | Electrical Cable Check and continuity megger test | 2 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-220-EL-690 | 23S3-ECC-FDL-014 | 220-EC-FDL-EL-001 | 220 | FDL | EL | motor continuity megger test | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
23S3-PC-220-EL-700 | 23S3-ECC-FDL-014 | 220-EC-FDL-EL-001 | 220 | FDL | EL | gland and connection final inspection | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-220-EL-710 | 23S3-ECC-FDL-014 | 220-EC-FDL-EL-001 | 220 | FDL | EL | LCS final function test | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-220-EL-720 | 23S3-ECC-FDL-014 | 220-EC-FDL-EL-001 | 220 | FDL | EL | feeder final checking | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-220-EL-730 | 23S3-ECC-FDL-014 | 220-EC-FDL-EL-001 | 220 | FDL | EL | motor free run test | 2 | 2019-12-04 | 2019-12-06 | 1398/09/13 | 1398/09/15
Flue Dust Bin & Liw Feeding Instrument System (220-EC-FDL-IN-001) | 23S3-ECC-FDL-014 | 220-EC-FDL-IN-001 | 220 | FDL | IN |  | 6 | 2019-11-29 | 2019-12-04 | 1398/09/08 | 1398/09/13
23S3-PC-220-IN-1230 | 23S3-ECC-FDL-014 | 220-EC-FDL-IN-001 | 220 | FDL | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-220-IN-1240 | 23S3-ECC-FDL-014 | 220-EC-FDL-IN-001 | 220 | FDL | IN | device calibration | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-220-IN-1245 | 23S3-ECC-FDL-014 | 220-EC-FDL-IN-001 | 220 | FDL | IN | Vendor at Site | 0 | 2019-11-30 |  | 1398/09/09
23S3-PC-220-IN-1250 | 23S3-ECC-FDL-014 | 220-EC-FDL-IN-001 | 220 | FDL | IN | device installation final check and punch clearance | 2 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-220-IN-1260 | 23S3-ECC-FDL-014 | 220-EC-FDL-IN-001 | 220 | FDL | IN | IO and loop checking | 2 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-220-IN-1270 | 23S3-ECC-FDL-014 | 220-EC-FDL-IN-001 | 220 | FDL | IN | function test | 3 | 2019-12-01 | 2019-12-04 | 1398/09/10 | 1398/09/13
Flue Dust Bin & Liw Feeding Mechanical System (220-EC-FDL-ME-001) | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-001 | 220 | FDL | ME |  | 11 | 2019-11-26 | 2019-12-06 | 1398/09/05 | 1398/09/15
23S3-PC-220-ME-920 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-001 | 220 | FDL | ME | duct work final check and punch clearance | 3 | 2019-11-26 | 2019-11-29 | 1398/09/05 | 1398/09/08
23S3-PC-220-ME-921 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-001 | 220 | FDL | ME | check for pre box-up and punch clearance | 3 | 2019-11-27 | 2019-11-30 | 1398/09/06 | 1398/09/09
23S3-PC-220-ME-922 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-001 | 220 | FDL | ME | Final Box-up | 2 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-220-ME-923 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-001 | 220 | FDL | ME | Motor and Fan installation final check and punch clearance | 3 | 2019-11-29 | 2019-12-02 | 1398/09/08 | 1398/09/11
23S3-PC-220-ME-924 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-001 | 220 | FDL | ME | Flange Parallel Check and adjastment | 2 | 2019-12-01 | 2019-12-03 | 1398/09/10 | 1398/09/12
23S3-PC-220-ME-925 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-001 | 220 | FDL | ME | Coupling Motor and fan / load run test | 2 | 2019-12-03 | 2019-12-05 | 1398/09/12 | 1398/09/14
23S3-PC-220-ME-945 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-001 | 220 | FDL | ME | Valve Check | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
Flue Dust Bin & Liw Feeding Mechanical System (220-EC-FDL-ME-002) | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-002 | 220 | FDL | ME |  | 6 | 2019-11-26 | 2019-12-01 | 1398/09/05 | 1398/09/10
23S3-PC-220-ME-933 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-002 | 220 | FDL | ME | Motor and Fan installation final check and punch clearance | 3 | 2019-11-26 | 2019-11-29 | 1398/09/05 | 1398/09/08
23S3-PC-220-ME-934 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-002 | 220 | FDL | ME | Flange Parallel Check and adjastment | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
23S3-PC-220-ME-935 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-002 | 220 | FDL | ME | Coupling pump and fan / load run test | 2 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-220-ME-965 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-002 | 220 | FDL | ME | Valve Check | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
Flue Dust Bin & Liw Feeding Mechanical System (220-EC-FDL-ME-003) | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-003 | 220 | FDL | ME |  | 4 | 2019-11-26 | 2019-11-30 | 1398/09/05 | 1398/09/09
23S3-PC-220-ME-953 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-003 | 220 | FDL | ME | Conveyor installation final check and punch clearance | 2 | 2019-11-26 | 2019-11-28 | 1398/09/05 | 1398/09/07
23S3-PC-220-ME-954 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-003 | 220 | FDL | ME | Belt adjastment | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-220-ME-975 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-003 | 220 | FDL | ME | Motor load run test | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
Flue Dust Bin & Liw Feeding Piping System (220-EC-FDL-PI-001) | 23S3-ECC-FDL-014 | 220-EC-FDL-PI-001 | 220 | FDL | PI |  | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-PI-190 | 23S3-ECC-FDL-014 | 220-EC-FDL-PI-001 | 220 | FDL | PI | Punch Clearance | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
210-Steam Drying (23S3-ECC-STD-009) | 23S3-ECC-STD-009 |  | 210 | STD |  |  | 9 | 2019-11-26 | 2019-12-05 | 1398/09/05 | 1398/09/14
STEAM DRYER ELECTRICAL SYSTEM (210-EC-STD-EL-001) | 23S3-ECC-STD-009 | 210-EC-STD-EL-001 | 210 | STD | EL |  | 5 | 2019-11-26 | 2019-12-01 | 1398/09/05 | 1398/09/10
23S3-PC-210-EL-259 | 23S3-ECC-STD-009 | 210-EC-STD-EL-001 | 210 | STD | EL | Vendor at Site | 0 | 2019-11-26 |  | 1398/09/05
23S3-PC-210-EL-260 | 23S3-ECC-STD-009 | 210-EC-STD-EL-001 | 210 | STD | EL | Electrical Cable Check and continuity megger test | 3 | 2019-11-26 | 2019-11-29 | 1398/09/05 | 1398/09/08
23S3-PC-210-EL-261 | 23S3-ECC-STD-009 | 210-EC-STD-EL-001 | 210 | STD | EL | motor continuity megger test | 2 | 2019-11-27 | 2019-11-29 | 1398/09/06 | 1398/09/08
23S3-PC-210-EL-262 | 23S3-ECC-STD-009 | 210-EC-STD-EL-001 | 210 | STD | EL | gland and connection final inspection | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
23S3-PC-210-EL-263 | 23S3-ECC-STD-009 | 210-EC-STD-EL-001 | 210 | STD | EL | LCS final function test | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
23S3-PC-210-EL-264 | 23S3-ECC-STD-009 | 210-EC-STD-EL-001 | 210 | STD | EL | feeder final checking | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
23S3-PC-210-EL-265 | 23S3-ECC-STD-009 | 210-EC-STD-EL-001 | 210 | STD | EL | motor free run & load test | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
STEAM DRYER ELECTRICAL CRANE SYSTEM (210-EC-STD-EL-002) | 23S3-ECC-STD-009 | 210-EC-STD-EL-002 | 210 | STD | EL |  | 5 | 2019-11-26 | 2019-12-01 | 1398/09/05 | 1398/09/10
23S3-PC-210-EL-270 | 23S3-ECC-STD-009 | 210-EC-STD-EL-002 | 210 | STD | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-210-EL-280 | 23S3-ECC-STD-009 | 210-EC-STD-EL-002 | 210 | STD | EL | motor continuity megger test | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-210-EL-290 | 23S3-ECC-STD-009 | 210-EC-STD-EL-002 | 210 | STD | EL | gland and connection final inspection | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
23S3-PC-210-EL-310 | 23S3-ECC-STD-009 | 210-EC-STD-EL-002 | 210 | STD | EL | feeder final checking | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-210-EL-311 | 23S3-ECC-STD-009 | 210-EC-STD-EL-002 | 210 | STD | EL | motor free run & load test | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
STEAM DRYER INSTRUMENTATION SYSTEM (210-EC-STD-IN-001) | 23S3-ECC-STD-009 | 210-EC-STD-IN-001 | 210 | STD | IN |  | 8 | 2019-11-26 | 2019-12-04 | 1398/09/05 | 1398/09/13
23S3-PC-210-IN-100 | 23S3-ECC-STD-009 | 210-EC-STD-IN-001 | 210 | STD | IN | Instrument Cable Check and continuity megger test | 2 | 2019-11-26 | 2019-11-28 | 1398/09/05 | 1398/09/07
23S3-PC-210-IN-110 | 23S3-ECC-STD-009 | 210-EC-STD-IN-001 | 210 | STD | IN | device calibration | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-210-IN-120 | 23S3-ECC-STD-009 | 210-EC-STD-IN-001 | 210 | STD | IN | device installation final check and punch clearance | 3 | 2019-11-27 | 2019-11-30 | 1398/09/06 | 1398/09/09
23S3-PC-210-IN-130 | 23S3-ECC-STD-009 | 210-EC-STD-IN-001 | 210 | STD | IN | IO and loop checking | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
23S3-PC-210-IN-140 | 23S3-ECC-STD-009 | 210-EC-STD-IN-001 | 210 | STD | IN | function test | 3 | 2019-12-01 | 2019-12-04 | 1398/09/10 | 1398/09/13
STEAM DRYER MECHANICAL SYSTEM (210-EC-STD-ME-001) | 23S3-ECC-STD-009 | 210-EC-STD-ME-001 | 210 | STD | ME |  | 9 | 2019-11-26 | 2019-12-05 | 1398/09/05 | 1398/09/14
23S3-PC-210-ME-100 | 23S3-ECC-STD-009 | 210-EC-STD-ME-001 | 210 | STD | ME | check for pre box-up and punch clearance | 3 | 2019-11-26 | 2019-11-29 | 1398/09/05 | 1398/09/08
23S3-PC-210-ME-110 | 23S3-ECC-STD-009 | 210-EC-STD-ME-001 | 210 | STD | ME | final boxup | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-210-ME-120 | 23S3-ECC-STD-009 | 210-EC-STD-ME-001 | 210 | STD | ME | motor and Crain installation final check and punch clearance | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-210-ME-130 | 23S3-ECC-STD-009 | 210-EC-STD-ME-001 | 210 | STD | ME | Dryer and other accessories adjustment final check and punch clearance | 4 | 2019-11-30 | 2019-12-04 | 1398/09/09 | 1398/09/13
23S3-PC-210-ME-140 | 23S3-ECC-STD-009 | 210-EC-STD-ME-001 | 210 | STD | ME | Coupling the motor and no load run test | 1 | 2019-12-04 | 2019-12-05 | 1398/09/13 | 1398/09/14
210-Steam Drying (23S3-ECC-STO-010) | 23S3-ECC-STO-010 |  | 210 | STO |  |  | 9 | 2019-11-26 | 2019-12-05 | 1398/09/05 | 1398/09/14
STEAM DRYER OFFGAS INSTRUMENTATION SYSTEM (210-EC-STO-IN-001) | 23S3-ECC-STO-010 | 210-EC-STO-IN-001 | 210 | STO | IN |  | 6 | 2019-11-28 | 2019-12-04 | 1398/09/07 | 1398/09/13
23S3-PC-210-IN-150 | 23S3-ECC-STO-010 | 210-EC-STO-IN-001 | 210 | STO | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
23S3-PC-210-IN-160 | 23S3-ECC-STO-010 | 210-EC-STO-IN-001 | 210 | STO | IN | device calibration | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-210-IN-170 | 23S3-ECC-STO-010 | 210-EC-STO-IN-001 | 210 | STO | IN | device installation final check and punch clearance | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
23S3-PC-210-IN-180 | 23S3-ECC-STO-010 | 210-EC-STO-IN-001 | 210 | STO | IN | IO and loop checking | 2 | 2019-12-01 | 2019-12-03 | 1398/09/10 | 1398/09/12
23S3-PC-210-IN-190 | 23S3-ECC-STO-010 | 210-EC-STO-IN-001 | 210 | STO | IN | function test | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
STEAM DRYER OFFGAS ELECTRICAL SYSTEM (210-EC-STO-EL-001) | 23S3-ECC-STO-010 | 210-EC-STO-EL-001 | 210 | STO | EL |  | 8 | 2019-11-27 | 2019-12-05 | 1398/09/06 | 1398/09/14
23S3-PC-210-EL-320 | 23S3-ECC-STO-010 | 210-EC-STO-EL-001 | 210 | STO | EL | Electrical Cable Check and continuity megger test | 2 | 2019-11-27 | 2019-11-29 | 1398/09/06 | 1398/09/08
23S3-PC-210-EL-330 | 23S3-ECC-STO-010 | 210-EC-STO-EL-001 | 210 | STO | EL | motor continuity megger test | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-210-EL-340 | 23S3-ECC-STO-010 | 210-EC-STO-EL-001 | 210 | STO | EL | gland and connection final inspection | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-210-EL-350 | 23S3-ECC-STO-010 | 210-EC-STO-EL-001 | 210 | STO | EL | LCS final function test | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-210-EL-360 | 23S3-ECC-STO-010 | 210-EC-STO-EL-001 | 210 | STO | EL | feeder final checking | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-210-EL-361 | 23S3-ECC-STO-010 | 210-EC-STO-EL-001 | 210 | STO | EL | motor free run & load test | 2 | 2019-12-03 | 2019-12-05 | 1398/09/12 | 1398/09/14
STEAM DRYER OFFGAS ELECTRICAL SYSTEM (210-EC-STO-EL-002) | 23S3-ECC-STO-010 | 210-EC-STO-EL-002 | 210 | STO | EL |  | 6 | 2019-11-27 | 2019-12-03 | 1398/09/06 | 1398/09/12
23S3-PC-210-EL-370 | 23S3-ECC-STO-010 | 210-EC-STO-EL-002 | 210 | STO | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-210-EL-380 | 23S3-ECC-STO-010 | 210-EC-STO-EL-002 | 210 | STO | EL | motor continuity megger test | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
23S3-PC-210-EL-390 | 23S3-ECC-STO-010 | 210-EC-STO-EL-002 | 210 | STO | EL | gland and connection final inspection | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-210-EL-400 | 23S3-ECC-STO-010 | 210-EC-STO-EL-002 | 210 | STO | EL | LCS final function test | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-210-EL-410 | 23S3-ECC-STO-010 | 210-EC-STO-EL-002 | 210 | STO | EL | feeder final checking | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-210-EL-411 | 23S3-ECC-STO-010 | 210-EC-STO-EL-002 | 210 | STO | EL | motor free run & load test | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
STEAM DRYER OFFGAS MECHANICAL SYSTEM (210-EC-STO-ME-001) | 23S3-ECC-STO-010 | 210-EC-STO-ME-001 | 210 | STO | ME |  | 7 | 2019-11-27 | 2019-12-04 | 1398/09/06 | 1398/09/13
23S3-PC-210-ME-170 | 23S3-ECC-STO-010 | 210-EC-STO-ME-001 | 210 | STO | ME | duct work final check and punch clearance | 4 | 2019-11-27 | 2019-12-01 | 1398/09/06 | 1398/09/10
23S3-PC-210-ME-190 | 23S3-ECC-STO-010 | 210-EC-STO-ME-001 | 210 | STO | ME | final boxup | 3 | 2019-12-01 | 2019-12-04 | 1398/09/10 | 1398/09/13
STEAM DRYER OFFGAS MECHANICAL SYSTEM (210-EC-STO-ME-002) | 23S3-ECC-STO-010 | 210-EC-STO-ME-002 | 210 | STO | ME |  | 6 | 2019-11-26 | 2019-12-02 | 1398/09/05 | 1398/09/11
23S3-PC-210-ME-200 | 23S3-ECC-STO-010 | 210-EC-STO-ME-002 | 210 | STO | ME | check for pre box-up and punch clearance | 2 | 2019-11-26 | 2019-11-28 | 1398/09/05 | 1398/09/07
23S3-PC-210-ME-210 | 23S3-ECC-STO-010 | 210-EC-STO-ME-002 | 210 | STO | ME | final boxup | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
23S3-PC-210-ME-240 | 23S3-ECC-STO-010 | 210-EC-STO-ME-002 | 210 | STO | ME | accessories adjustment final check and punch clearance | 3 | 2019-11-29 | 2019-12-02 | 1398/09/08 | 1398/09/11
STEAM DRYER OFFGAS MECHANICAL SYSTEM (210-EC-STO-ME-003) | 23S3-ECC-STO-010 | 210-EC-STO-ME-003 | 210 | STO | ME |  | 7 | 2019-11-26 | 2019-12-03 | 1398/09/05 | 1398/09/12
23S3-PC-210-ME-250 | 23S3-ECC-STO-010 | 210-EC-STO-ME-003 | 210 | STO | ME | check for pre box-up and punch clearance | 3 | 2019-11-26 | 2019-11-29 | 1398/09/05 | 1398/09/08
23S3-PC-210-ME-260 | 23S3-ECC-STO-010 | 210-EC-STO-ME-003 | 210 | STO | ME | final boxup | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-210-ME-270 | 23S3-ECC-STO-010 | 210-EC-STO-ME-003 | 210 | STO | ME | motor and conveyor installation final check and punch clearance | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-210-ME-280 | 23S3-ECC-STO-010 | 210-EC-STO-ME-003 | 210 | STO | ME | belt and other accessories adjustment final check and punch clearance | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
23S3-PC-210-ME-290 | 23S3-ECC-STO-010 | 210-EC-STO-ME-003 | 210 | STO | ME | Coupling the motor and no load run test | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
STEAM DRYER OFFGAS MECHANICAL SYSTEM (210-EC-STO-ME-004) | 23S3-ECC-STO-010 | 210-EC-STO-ME-004 | 210 | STO | ME |  | 3 | 2019-11-27 | 2019-11-30 | 1398/09/06 | 1398/09/09
23S3-PC-210-ME-300 | 23S3-ECC-STO-010 | 210-EC-STO-ME-004 | 210 | STO | ME | motor and conveyer installation final check and punch clearance | 2 | 2019-11-27 | 2019-11-29 | 1398/09/06 | 1398/09/08
23S3-PC-210-ME-320 | 23S3-ECC-STO-010 | 210-EC-STO-ME-004 | 210 | STO | ME | Coupling the motor and no load run test | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
STEAM DRYER OFFGAS PIPING SYSTEM (210-EC-STO-PI-001) | 23S3-ECC-STO-010 | 210-EC-STO-PI-001 | 210 | STO | PI |  | 2 | 2019-11-27 | 2019-11-29 | 1398/09/06 | 1398/09/08
23S3-PC-210-PI-110 | 23S3-ECC-STO-010 | 210-EC-STO-PI-001 | 210 | STO | PI | Punch Clearance | 2 | 2019-11-27 | 2019-11-29 | 1398/09/06 | 1398/09/08
210-Steam Drying (23S3-ECC-DFM-011) | 23S3-ECC-DFM-011 |  | 210 | DFM |  |  | 15 | 2019-11-28 | 2019-12-13 | 1398/09/07 | 1398/09/22
DRED FEED MIXTURE INSTRUMENTATION SYSTEM (210-EC-DFM-IN-001) | 23S3-ECC-DFM-011 | 210-EC-DFM-IN-001 | 210 | DFM | IN |  | 8 | 2019-11-28 | 2019-12-06 | 1398/09/07 | 1398/09/15
23S3-PC-210-IN-200 | 23S3-ECC-DFM-011 | 210-EC-DFM-IN-001 | 210 | DFM | IN | Instrument Cable Check and continuity megger test | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
23S3-PC-210-IN-210 | 23S3-ECC-DFM-011 | 210-EC-DFM-IN-001 | 210 | DFM | IN | device calibration | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-210-IN-220 | 23S3-ECC-DFM-011 | 210-EC-DFM-IN-001 | 210 | DFM | IN | device installation final check and punch clearance | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-210-IN-230 | 23S3-ECC-DFM-011 | 210-EC-DFM-IN-001 | 210 | DFM | IN | IO and loop checking | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
23S3-PC-210-IN-240 | 23S3-ECC-DFM-011 | 210-EC-DFM-IN-001 | 210 | DFM | IN | function test | 2 | 2019-12-04 | 2019-12-06 | 1398/09/13 | 1398/09/15
DRED FEED MIXTURE PIPING SYSTEM (210-EC-DFM-PI-001) | 23S3-ECC-DFM-011 | 210-EC-DFM-PI-001 | 210 | DFM | PI |  | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
23S3-PC-210-PI-120 | 23S3-ECC-DFM-011 | 210-EC-DFM-PI-001 | 210 | DFM | PI | Punch Clearance | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
DRED FEED MIXTURE MECHANICAL SYSTEM (210-EC-DFM-ME-001) | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-001 | 210 | DFM | ME |  | 15 | 2019-11-28 | 2019-12-13 | 1398/09/07 | 1398/09/22
23S3-PC-210-ME-350 | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-001 | 210 | DFM | ME | conveyer installation final check and punch clearance | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
23S3-PC-210-ME-360 | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-001 | 210 | DFM | ME | accessories adjustment final check and punch clearance | 3 | 2019-11-30 | 2019-12-03 | 1398/09/09 | 1398/09/12
23S3-PC-210-ME-380 | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-001 | 210 | DFM | ME | check for pre box-up and punch clearance | 8 | 2019-12-02 | 2019-12-10 | 1398/09/11 | 1398/09/19
23S3-PC-210-ME-390 | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-001 | 210 | DFM | ME | final boxup | 4 | 2019-12-09 | 2019-12-13 | 1398/09/18 | 1398/09/22
DRED FEED MIXTURE MECHANICAL SYSTEM (210-EC-DFM-ME-002) | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-002 | 210 | DFM | ME |  | 3 | 2019-11-28 | 2019-12-01 | 1398/09/07 | 1398/09/10
23S3-PC-210-ME-400 | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-002 | 210 | DFM | ME | conveyer installation final check and punch clearance | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
23S3-PC-210-ME-410 | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-002 | 210 | DFM | ME | accessories adjustment final check and punch clearance | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
23S3-PC-210-ME-430 | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-002 | 210 | DFM | ME | check for pre box-up and punch clearance | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
23S3-PC-210-ME-440 | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-002 | 210 | DFM | ME | final boxup | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
210-Steam Drying (23S3-ECC-STC-012) | 23S3-ECC-STC-012 |  | 210 | STC |  |  | 7 | 2019-11-29 | 2019-12-06 | 1398/09/08 | 1398/09/15
STEAM AND CONDENSATE ELECTRICAL SYSTEM (210-EC-STC-EL-001) | 23S3-ECC-STC-012 | 210-EC-STC-EL-001 | 210 | STC | EL |  | 6 | 2019-11-29 | 2019-12-05 | 1398/09/08 | 1398/09/14
23S3-PC-210-EL-420 | 23S3-ECC-STC-012 | 210-EC-STC-EL-001 | 210 | STC | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-210-EL-430 | 23S3-ECC-STC-012 | 210-EC-STC-EL-001 | 210 | STC | EL | motor continuity megger test | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-210-EL-440 | 23S3-ECC-STC-012 | 210-EC-STC-EL-001 | 210 | STC | EL | gland and connection final inspection | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-210-EL-450 | 23S3-ECC-STC-012 | 210-EC-STC-EL-001 | 210 | STC | EL | LCS final function test | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-210-EL-460 | 23S3-ECC-STC-012 | 210-EC-STC-EL-001 | 210 | STC | EL | feeder final checking | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-210-EL-470 | 23S3-ECC-STC-012 | 210-EC-STC-EL-001 | 210 | STC | EL | motor free run test | 1 | 2019-12-04 | 2019-12-05 | 1398/09/13 | 1398/09/14
STEAM AND CONDENSATE INSTRUMENTATION SYSTEM (210-EC-STC-IN-001) | 23S3-ECC-STC-012 | 210-EC-STC-IN-001 | 210 | STC | IN |  | 7 | 2019-11-29 | 2019-12-06 | 1398/09/08 | 1398/09/15
23S3-PC-210-IN-250 | 23S3-ECC-STC-012 | 210-EC-STC-IN-001 | 210 | STC | IN | Instrument Cable Check and continuity megger test | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
23S3-PC-210-IN-260 | 23S3-ECC-STC-012 | 210-EC-STC-IN-001 | 210 | STC | IN | device calibration | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-210-IN-270 | 23S3-ECC-STC-012 | 210-EC-STC-IN-001 | 210 | STC | IN | device installation final check and punch clearance | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-210-IN-280 | 23S3-ECC-STC-012 | 210-EC-STC-IN-001 | 210 | STC | IN | IO and loop checking | 2 | 2019-12-03 | 2019-12-05 | 1398/09/12 | 1398/09/14
23S3-PC-210-IN-290 | 23S3-ECC-STC-012 | 210-EC-STC-IN-001 | 210 | STC | IN | function test | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
STEAM AND CONDENSATE MECHANICAL SYSTEM (210-EC-STC-ME-001) | 23S3-ECC-STC-012 | 210-EC-STC-ME-001 | 210 | STC | ME |  | 6 | 2019-11-29 | 2019-12-05 | 1398/09/08 | 1398/09/14
23S3-PC-210-ME-450 | 23S3-ECC-STC-012 | 210-EC-STC-ME-001 | 210 | STC | ME | Pump & Motor installation final check and punch clearance | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
23S3-PC-210-ME-470 | 23S3-ECC-STC-012 | 210-EC-STC-ME-001 | 210 | STC | ME | Coupling the motor and load run test | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-210-ME-480 | 23S3-ECC-STC-012 | 210-EC-STC-ME-001 | 210 | STC | ME | check for pre box-up and punch clearance | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
23S3-PC-210-ME-490 | 23S3-ECC-STC-012 | 210-EC-STC-ME-001 | 210 | STC | ME | final boxup | 1 | 2019-12-04 | 2019-12-05 | 1398/09/13 | 1398/09/14
STEAM PIPING SYSTEM (210-EC-STC-PI-001) | 23S3-ECC-STC-012 | 210-EC-STC-PI-001 | 210 | STC | PI |  | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
23S3-PC-210-PI-130 | 23S3-ECC-STC-012 | 210-EC-STC-PI-001 | 210 | STC | PI | Punch Clearance | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
CONDENSATE PIPING SYSTEM (210-EC-STC-PI-002) | 23S3-ECC-STC-012 | 210-EC-STC-PI-002 | 210 | STC | PI |  | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
23S3-PC-210-PI-140 | 23S3-ECC-STC-012 | 210-EC-STC-PI-002 | 210 | STC | PI | Punch Clearance | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
150-Concentrate Blending (23S3-ECC-FMB-001) | 23S3-ECC-FMB-001 |  | 150 | FMB |  |  | 9 | 2019-11-30 | 2019-12-09 | 1398/09/09 | 1398/09/18
FEED MATERIAL CONVEYING AND BLENDING MODIFICATION ELECTRICAL (150-EC-FMB-EL-001) | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-001 | 150 | FMB | EL |  | 7 | 2019-11-30 | 2019-12-07 | 1398/09/09 | 1398/09/16
23S3-PC-150-EL-180 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-001 | 150 | FMB | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-150-EL-190 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-001 | 150 | FMB | EL | motor continuity megger test | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-150-EL-200 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-001 | 150 | FMB | EL | gland and connection final inspection | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-150-EL-210 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-001 | 150 | FMB | EL | LCS final function test | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-150-EL-220 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-001 | 150 | FMB | EL | feeder final checking | 1 | 2019-12-04 | 2019-12-05 | 1398/09/13 | 1398/09/14
23S3-PC-150-EL-230 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-001 | 150 | FMB | EL | motor free run test | 2 | 2019-12-05 | 2019-12-07 | 1398/09/14 | 1398/09/16
FEED MATERIAL CONVEYING AND BLENDING MODIFICATION ELECTRICAL (150-EC-FMB-EL-002) | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-002 | 150 | FMB | EL |  | 6 | 2019-11-30 | 2019-12-06 | 1398/09/09 | 1398/09/15
23S3-PC-150-EL-240 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-002 | 150 | FMB | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-150-EL-250 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-002 | 150 | FMB | EL | motor continuity megger test | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-150-EL-260 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-002 | 150 | FMB | EL | gland and connection final inspection | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-150-EL-270 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-002 | 150 | FMB | EL | LCS final function test | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-150-EL-280 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-002 | 150 | FMB | EL | feeder final checking | 1 | 2019-12-04 | 2019-12-05 | 1398/09/13 | 1398/09/14
23S3-PC-150-EL-290 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-002 | 150 | FMB | EL | motor free run test | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
FEED MATERIAL CONVEYING AND BLENDING MODIFICATION INSTRUMENTATION (150-EC-FMB-IN-001) | 23S3-ECC-FMB-001 | 150-EC-FMB-IN-001 | 150 | FMB | IN |  | 8 | 2019-11-30 | 2019-12-08 | 1398/09/09 | 1398/09/17
23S3-PC-150-IN-100 | 23S3-ECC-FMB-001 | 150-EC-FMB-IN-001 | 150 | FMB | IN | Instrument Cable Check and continuity megger test | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
23S3-PC-150-IN-110 | 23S3-ECC-FMB-001 | 150-EC-FMB-IN-001 | 150 | FMB | IN | device calibration | 3 | 2019-12-01 | 2019-12-04 | 1398/09/10 | 1398/09/13
23S3-PC-150-IN-120 | 23S3-ECC-FMB-001 | 150-EC-FMB-IN-001 | 150 | FMB | IN | device installation final check and punch clearance | 3 | 2019-12-03 | 2019-12-06 | 1398/09/12 | 1398/09/15
23S3-PC-150-IN-130 | 23S3-ECC-FMB-001 | 150-EC-FMB-IN-001 | 150 | FMB | IN | IO and loop checking | 2 | 2019-12-05 | 2019-12-07 | 1398/09/14 | 1398/09/16
23S3-PC-150-IN-140 | 23S3-ECC-FMB-001 | 150-EC-FMB-IN-001 | 150 | FMB | IN | function test | 1 | 2019-12-07 | 2019-12-08 | 1398/09/16 | 1398/09/17
FEED MATERIAL CONVEYING AND BLENDING MODIFICATION MECHANICAL (150-EC-FMB-ME-001) | 23S3-ECC-FMB-001 | 150-EC-FMB-ME-001 | 150 | FMB | ME |  | 4 | 2019-11-30 | 2019-12-04 | 1398/09/09 | 1398/09/13
23S3-PC-150-ME-130 | 23S3-ECC-FMB-001 | 150-EC-FMB-ME-001 | 150 | FMB | ME | check for pre box-up and punch clearance | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
23S3-PC-150-ME-140 | 23S3-ECC-FMB-001 | 150-EC-FMB-ME-001 | 150 | FMB | ME | final boxup | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
FEED MATERIAL CONVEYING AND BLENDING MODIFICATION MECHANICAL (150-EC-FMB-ME-002) | 23S3-ECC-FMB-001 | 150-EC-FMB-ME-002 | 150 | FMB | ME |  | 9 | 2019-11-30 | 2019-12-09 | 1398/09/09 | 1398/09/18
23S3-PC-150-ME-150 | 23S3-ECC-FMB-001 | 150-EC-FMB-ME-002 | 150 | FMB | ME | motor and conveyer installation final check and punch clearance | 5 | 2019-11-30 | 2019-12-05 | 1398/09/09 | 1398/09/14
23S3-PC-150-ME-160 | 23S3-ECC-FMB-001 | 150-EC-FMB-ME-002 | 150 | FMB | ME | belt and other accessories adjustment final check and punch clearance | 5 | 2019-12-02 | 2019-12-07 | 1398/09/11 | 1398/09/16
23S3-PC-150-ME-170 | 23S3-ECC-FMB-001 | 150-EC-FMB-ME-002 | 150 | FMB | ME | Coupling the motor and no load run test | 3 | 2019-12-06 | 2019-12-09 | 1398/09/15 | 1398/09/18
150-Concentrate Blending (23S3-ECC-FMS-002) | 23S3-ECC-FMS-002 |  | 150 | FMS |  |  | 11 | 2019-12-01 | 2019-12-12 | 1398/09/10 | 1398/09/21
FEED MATERIAL CONVEYING AND BLENDING MODIFICATION ELECTRICAL (150-EC-FMS-EL-001) | 23S3-ECC-FMS-002 | 150-EC-FMS-EL-001 | 150 | FMS | EL |  | 6 | 2019-12-01 | 2019-12-07 | 1398/09/10 | 1398/09/16
23S3-PC-150-EL-300 | 23S3-ECC-FMS-002 | 150-EC-FMS-EL-001 | 150 | FMS | EL | Electrical Cable Check and continuity megger test | 2 | 2019-12-01 | 2019-12-03 | 1398/09/10 | 1398/09/12
23S3-PC-150-EL-310 | 23S3-ECC-FMS-002 | 150-EC-FMS-EL-001 | 150 | FMS | EL | motor continuity megger test | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
23S3-PC-150-EL-320 | 23S3-ECC-FMS-002 | 150-EC-FMS-EL-001 | 150 | FMS | EL | gland and connection final inspection | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-150-EL-330 | 23S3-ECC-FMS-002 | 150-EC-FMS-EL-001 | 150 | FMS | EL | LCS final function test | 2 | 2019-12-03 | 2019-12-05 | 1398/09/12 | 1398/09/14
23S3-PC-150-EL-340 | 23S3-ECC-FMS-002 | 150-EC-FMS-EL-001 | 150 | FMS | EL | feeder final checking | 2 | 2019-12-04 | 2019-12-06 | 1398/09/13 | 1398/09/15
23S3-PC-150-EL-350 | 23S3-ECC-FMS-002 | 150-EC-FMS-EL-001 | 150 | FMS | EL | motor free run test | 2 | 2019-12-05 | 2019-12-07 | 1398/09/14 | 1398/09/16
FEED MATERIAL CONVEYING AND BLENDING MODIFICATION INSTRUMENTATION (150-EC-FMS-IN-001) | 23S3-ECC-FMS-002 | 150-EC-FMS-IN-001 | 150 | FMS | IN |  | 11 | 2019-12-01 | 2019-12-12 | 1398/09/10 | 1398/09/21
23S3-PC-150-IN-150 | 23S3-ECC-FMS-002 | 150-EC-FMS-IN-001 | 150 | FMS | IN | Instrument Cable Check and continuity megger test | 2 | 2019-12-01 | 2019-12-03 | 1398/09/10 | 1398/09/12
23S3-PC-150-IN-160 | 23S3-ECC-FMS-002 | 150-EC-FMS-IN-001 | 150 | FMS | IN | device calibration | 3 | 2019-12-03 | 2019-12-06 | 1398/09/12 | 1398/09/15
23S3-PC-150-IN-170 | 23S3-ECC-FMS-002 | 150-EC-FMS-IN-001 | 150 | FMS | IN | device installation final check and punch clearance | 3 | 2019-12-06 | 2019-12-09 | 1398/09/15 | 1398/09/18
23S3-PC-150-IN-180 | 23S3-ECC-FMS-002 | 150-EC-FMS-IN-001 | 150 | FMS | IN | IO and loop checking | 2 | 2019-12-09 | 2019-12-11 | 1398/09/18 | 1398/09/20
23S3-PC-150-IN-190 | 23S3-ECC-FMS-002 | 150-EC-FMS-IN-001 | 150 | FMS | IN | function test | 1 | 2019-12-11 | 2019-12-12 | 1398/09/20 | 1398/09/21
FEED MATERIAL CONVEYING AND BLENDING MODIFICATION MACHINERY (150-EC-FMS-ME-001) | 23S3-ECC-FMS-002 | 150-EC-FMS-ME-001 | 150 | FMS | ME |  | 4 | 2019-12-01 | 2019-12-05 | 1398/09/10 | 1398/09/14
23S3-PC-150-ME-200 | 23S3-ECC-FMS-002 | 150-EC-FMS-ME-001 | 150 | FMS | ME | motor and conveyer installation final check and punch clearance | 3 | 2019-12-01 | 2019-12-04 | 1398/09/10 | 1398/09/13
23S3-PC-150-ME-210 | 23S3-ECC-FMS-002 | 150-EC-FMS-ME-001 | 150 | FMS | ME | belt and other accessories adjustment final check and punch clearance | 3 | 2019-12-01 | 2019-12-04 | 1398/09/10 | 1398/09/13
23S3-PC-150-ME-220 | 23S3-ECC-FMS-002 | 150-EC-FMS-ME-001 | 150 | FMS | ME | Coupling the motor and no load run test | 2 | 2019-12-03 | 2019-12-05 | 1398/09/12 | 1398/09/14
255-PS-DUST CONVEING (23S3-ECC-PSD-006) | 23S3-ECC-PSD-006 |  | 255 | PSD |  |  | 10 | 2019-12-01 | 2019-12-11 | 1398/09/10 | 1398/09/20
PS-DUST CONVEING ELECTRICAL SYSTEM (255-EC-PSD-EL-001) | 23S3-ECC-PSD-006 | 255-EC-PSD-EL-001 | 255 | PSD | EL |  | 7 | 2019-12-02 | 2019-12-09 | 1398/09/11 | 1398/09/18
23S3-PC-255-EL-100 | 23S3-ECC-PSD-006 | 255-EC-PSD-EL-001 | 255 | PSD | EL | Electrical Cable Check and continuity megger test | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-255-EL-110 | 23S3-ECC-PSD-006 | 255-EC-PSD-EL-001 | 255 | PSD | EL | motor continuity megger test | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-255-EL-120 | 23S3-ECC-PSD-006 | 255-EC-PSD-EL-001 | 255 | PSD | EL | gland and connection final inspection | 1 | 2019-12-04 | 2019-12-05 | 1398/09/13 | 1398/09/14
23S3-PC-255-EL-130 | 23S3-ECC-PSD-006 | 255-EC-PSD-EL-001 | 255 | PSD | EL | LCS final function test | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
23S3-PC-255-EL-140 | 23S3-ECC-PSD-006 | 255-EC-PSD-EL-001 | 255 | PSD | EL | feeder final checking | 1 | 2019-12-06 | 2019-12-07 | 1398/09/15 | 1398/09/16
23S3-PC-255-EL-150 | 23S3-ECC-PSD-006 | 255-EC-PSD-EL-001 | 255 | PSD | EL | motor free run test | 2 | 2019-12-07 | 2019-12-09 | 1398/09/16 | 1398/09/18
PS-DUST CONVEING INSTRUMENTATION (255-EC-PSD-IN-001) | 23S3-ECC-PSD-006 | 255-EC-PSD-IN-001 | 255 | PSD | IN |  | 6 | 2019-12-01 | 2019-12-07 | 1398/09/10 | 1398/09/16
23S3-PC-255-IN-100 | 23S3-ECC-PSD-006 | 255-EC-PSD-IN-001 | 255 | PSD | IN | Instrument Cable Check and continuity megger test | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-255-IN-110 | 23S3-ECC-PSD-006 | 255-EC-PSD-IN-001 | 255 | PSD | IN | device calibration | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-255-IN-120 | 23S3-ECC-PSD-006 | 255-EC-PSD-IN-001 | 255 | PSD | IN | device installation final check and punch clearance | 2 | 2019-12-03 | 2019-12-05 | 1398/09/12 | 1398/09/14
23S3-PC-255-IN-130 | 23S3-ECC-PSD-006 | 255-EC-PSD-IN-001 | 255 | PSD | IN | IO and loop checking | 2 | 2019-12-04 | 2019-12-06 | 1398/09/13 | 1398/09/15
23S3-PC-255-IN-140 | 23S3-ECC-PSD-006 | 255-EC-PSD-IN-001 | 255 | PSD | IN | function test | 1 | 2019-12-06 | 2019-12-07 | 1398/09/15 | 1398/09/16
PS-DUST CONVEING MECHANICAL (255-EC-PSD-ME-001) | 23S3-ECC-PSD-006 | 255-EC-PSD-ME-001 | 255 | PSD | ME |  | 9 | 2019-12-02 | 2019-12-11 | 1398/09/11 | 1398/09/20
23S3-PC-255-ME-100 | 23S3-ECC-PSD-006 | 255-EC-PSD-ME-001 | 255 | PSD | ME | belt and other accessories adjustment final check and punch clearance | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-255-ME-110 | 23S3-ECC-PSD-006 | 255-EC-PSD-ME-001 | 255 | PSD | ME | Chain and other accessories adjustment final check and punch clearance | 2 | 2019-12-03 | 2019-12-05 | 1398/09/12 | 1398/09/14
23S3-PC-255-ME-120 | 23S3-ECC-PSD-006 | 255-EC-PSD-ME-001 | 255 | PSD | ME | Coupling the motor and no load run test | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
23S3-PC-255-ME-230 | 23S3-ECC-PSD-006 | 255-EC-PSD-ME-001 | 255 | PSD | ME | check for pre box-up and punch clearance | 3 | 2019-12-06 | 2019-12-09 | 1398/09/15 | 1398/09/18
23S3-PC-255-ME-270 | 23S3-ECC-PSD-006 | 255-EC-PSD-ME-001 | 255 | PSD | ME | Final Box-up | 2 | 2019-12-09 | 2019-12-11 | 1398/09/18 | 1398/09/20
PS-DUST PNEUMATIC CONVEING PIPING (255-EC-PSD-PI-001) | 23S3-ECC-PSD-006 | 255-EC-PSD-PI-001 | 255 | PSD | PI |  | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
23S3-PC-225-PI-110 | 23S3-ECC-PSD-006 | 255-EC-PSD-PI-001 | 255 | PSD | PI | Punch Clearance | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
225-ESP DUST COLLECTION SYSTEM (23S3-ECC-ESP-032) | 23S3-ECC-ESP-032 |  | 225 | ESP |  |  | 12 | 2019-12-02 | 2019-12-14 | 1398/09/11 | 1398/09/23
ESP Dust Collection Electrical system (225-EC-ESP-EL-001) | 23S3-ECC-ESP-032 | 225-EC-ESP-EL-001 | 225 | ESP | EL |  | 8 | 2019-12-02 | 2019-12-10 | 1398/09/11 | 1398/09/19
23S3-PC-225-EL-500 | 23S3-ECC-ESP-032 | 225-EC-ESP-EL-001 | 225 | ESP | EL | Electrical Cable Check and continuity megger test | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
23S3-PC-225-EL-510 | 23S3-ECC-ESP-032 | 225-EC-ESP-EL-001 | 225 | ESP | EL | motor continuity megger test | 1 | 2019-12-04 | 2019-12-05 | 1398/09/13 | 1398/09/14
23S3-PC-225-EL-520 | 23S3-ECC-ESP-032 | 225-EC-ESP-EL-001 | 225 | ESP | EL | gland and connection final inspection | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
23S3-PC-225-EL-530 | 23S3-ECC-ESP-032 | 225-EC-ESP-EL-001 | 225 | ESP | EL | LCS final function test | 1 | 2019-12-06 | 2019-12-07 | 1398/09/15 | 1398/09/16
23S3-PC-225-EL-540 | 23S3-ECC-ESP-032 | 225-EC-ESP-EL-001 | 225 | ESP | EL | feeder final checking | 1 | 2019-12-07 | 2019-12-08 | 1398/09/16 | 1398/09/17
23S3-PC-225-EL-550 | 23S3-ECC-ESP-032 | 225-EC-ESP-EL-001 | 225 | ESP | EL | motor free run test | 3 | 2019-12-07 | 2019-12-10 | 1398/09/16 | 1398/09/19
ESP Dust Collection Mechanical system (225-EC-ESP-ME-001) | 23S3-ECC-ESP-032 | 225-EC-ESP-ME-001 | 225 | ESP | ME |  | 11 | 2019-12-03 | 2019-12-14 | 1398/09/12 | 1398/09/23
23S3-PC-255-ME-130 | 23S3-ECC-ESP-032 | 225-EC-ESP-ME-001 | 225 | ESP | ME | Motor & Conveyor Installation Final Check and Punch Clearance | 2 | 2019-12-03 | 2019-12-05 | 1398/09/12 | 1398/09/14
23S3-PC-255-ME-140 | 23S3-ECC-ESP-032 | 225-EC-ESP-ME-001 | 225 | ESP | ME | Motor & Crusher Installation Final Check and Punch Clearance | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
23S3-PC-255-ME-160 | 23S3-ECC-ESP-032 | 225-EC-ESP-ME-001 | 225 | ESP | ME | Air Lock Feeder Installation Final Check and Punch Clearance | 1 | 2019-12-06 | 2019-12-07 | 1398/09/15 | 1398/09/16
23S3-PC-255-ME-170 | 23S3-ECC-ESP-032 | 225-EC-ESP-ME-001 | 225 | ESP | ME | Flange Parallel Check and adjastment | 3 | 2019-12-06 | 2019-12-09 | 1398/09/15 | 1398/09/18
23S3-PC-255-ME-180 | 23S3-ECC-ESP-032 | 225-EC-ESP-ME-001 | 225 | ESP | ME | duct work final check and punch clearance | 5 | 2019-12-07 | 2019-12-12 | 1398/09/16 | 1398/09/21
23S3-PC-255-ME-190 | 23S3-ECC-ESP-032 | 225-EC-ESP-ME-001 | 225 | ESP | ME | Coupling pump and fan / load run test | 4 | 2019-12-10 | 2019-12-14 | 1398/09/19 | 1398/09/23
225-ESP DUST CONVEYING SYSTEM (23S3-ECC-DUC-033) | 23S3-ECC-DUC-033 |  | 225 | DUC |  |  | 7 | 2019-12-04 | 2019-12-11 | 1398/09/13 | 1398/09/20
ESP Dust Conveying Instrument System (225-DUC-IN-001) | 23S3-ECC-DUC-033 | 225-DUC-IN-001 | 225 | DUC | IN |  | 5 | 2019-12-04 | 2019-12-09 | 1398/09/13 | 1398/09/18
23S3-PC-255-IN-200 | 23S3-ECC-DUC-033 | 225-DUC-IN-001 | 225 | DUC | IN | Instrument Cable Check and continuity megger test | 1 | 2019-12-04 | 2019-12-05 | 1398/09/13 | 1398/09/14
23S3-PC-255-IN-210 | 23S3-ECC-DUC-033 | 225-DUC-IN-001 | 225 | DUC | IN | device calibration | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
23S3-PC-255-IN-220 | 23S3-ECC-DUC-033 | 225-DUC-IN-001 | 225 | DUC | IN | device installation final check and punch clearance | 1 | 2019-12-06 | 2019-12-07 | 1398/09/15 | 1398/09/16
23S3-PC-255-IN-230 | 23S3-ECC-DUC-033 | 225-DUC-IN-001 | 225 | DUC | IN | IO and loop checking | 1 | 2019-12-07 | 2019-12-08 | 1398/09/16 | 1398/09/17
23S3-PC-255-IN-240 | 23S3-ECC-DUC-033 | 225-DUC-IN-001 | 225 | DUC | IN | function test | 1 | 2019-12-08 | 2019-12-09 | 1398/09/17 | 1398/09/18
ESP Dust Conveying Mechanical System (225-DUC-ME-001) | 23S3-ECC-DUC-033 | 225-DUC-ME-001 | 225 | DUC | ME |  | 6 | 2019-12-05 | 2019-12-11 | 1398/09/14 | 1398/09/20
23S3-PC-255-ME-200 | 23S3-ECC-DUC-033 | 225-DUC-ME-001 | 225 | DUC | ME | duct work final check and punch clearance | 3 | 2019-12-05 | 2019-12-08 | 1398/09/14 | 1398/09/17
23S3-PC-255-ME-210 | 23S3-ECC-DUC-033 | 225-DUC-ME-001 | 225 | DUC | ME | check for pre box-up and punch clearance | 2 | 2019-12-08 | 2019-12-10 | 1398/09/17 | 1398/09/19
23S3-PC-255-ME-220 | 23S3-ECC-DUC-033 | 225-DUC-ME-001 | 225 | DUC | ME | Final Box-up | 1 | 2019-12-10 | 2019-12-11 | 1398/09/19 | 1398/09/20
ESP Dust Conveying Mechanical System (225-DUC-ME-002) | 23S3-ECC-DUC-033 | 225-DUC-ME-002 | 225 | DUC | ME |  | 6 | 2019-12-04 | 2019-12-10 | 1398/09/13 | 1398/09/19
23S3-PC-255-ME-240 | 23S3-ECC-DUC-033 | 225-DUC-ME-002 | 225 | DUC | ME | duct work final check and punch clearance | 3 | 2019-12-04 | 2019-12-07 | 1398/09/13 | 1398/09/16
23S3-PC-255-ME-250 | 23S3-ECC-DUC-033 | 225-DUC-ME-002 | 225 | DUC | ME | check for pre box-up and punch clearance | 2 | 2019-12-07 | 2019-12-09 | 1398/09/16 | 1398/09/18
23S3-PC-255-ME-260 | 23S3-ECC-DUC-033 | 225-DUC-ME-002 | 225 | DUC | ME | Final Box-up | 1 | 2019-12-09 | 2019-12-10 | 1398/09/18 | 1398/09/19
ESP Dust Conveying Piping System (225-DUC-PI-001) | 23S3-ECC-DUC-033 | 225-DUC-PI-001 | 225 | DUC | PI |  | 2 | 2019-12-04 | 2019-12-06 | 1398/09/13 | 1398/09/15
23S3-PC-225-PI-120 | 23S3-ECC-DUC-033 | 225-DUC-PI-001 | 225 | DUC | PI | Punch Clearance | 2 | 2019-12-04 | 2019-12-06 | 1398/09/13 | 1398/09/15
225-FSF SULPHATATION SYSTEM (23S3-ECC-SUL-031) | 23S3-ECC-SUL-031 |  | 225 | SUL |  |  | 5 | 2019-12-05 | 2019-12-10 | 1398/09/14 | 1398/09/19
FSF Sulphatation Instrument System (225-EC-SUL-IN-001) | 23S3-ECC-SUL-031 | 225-EC-SUL-IN-001 | 225 | SUL | IN |  | 5 | 2019-12-05 | 2019-12-10 | 1398/09/14 | 1398/09/19
23S3-PC-255-IN-250 | 23S3-ECC-SUL-031 | 225-EC-SUL-IN-001 | 225 | SUL | IN | Instrument Cable Check and continuity megger test | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
23S3-PC-255-IN-260 | 23S3-ECC-SUL-031 | 225-EC-SUL-IN-001 | 225 | SUL | IN | device calibration | 1 | 2019-12-06 | 2019-12-07 | 1398/09/15 | 1398/09/16
23S3-PC-255-IN-270 | 23S3-ECC-SUL-031 | 225-EC-SUL-IN-001 | 225 | SUL | IN | device installation final check and punch clearance | 1 | 2019-12-07 | 2019-12-08 | 1398/09/16 | 1398/09/17
23S3-PC-255-IN-280 | 23S3-ECC-SUL-031 | 225-EC-SUL-IN-001 | 225 | SUL | IN | IO and loop checking | 1 | 2019-12-08 | 2019-12-09 | 1398/09/17 | 1398/09/18
23S3-PC-255-IN-290 | 23S3-ECC-SUL-031 | 225-EC-SUL-IN-001 | 225 | SUL | IN | function test | 1 | 2019-12-09 | 2019-12-10 | 1398/09/18 | 1398/09/19
FSF Sulphatation Mechanical System (225-EC-SUL-ME-001) | 23S3-ECC-SUL-031 | 225-EC-SUL-ME-001 | 225 | SUL | ME |  | 3 | 2019-12-05 | 2019-12-08 | 1398/09/14 | 1398/09/17
23S3-PC-255-ME-280 | 23S3-ECC-SUL-031 | 225-EC-SUL-ME-001 | 225 | SUL | ME | duct work final check and punch clearance | 3 | 2019-12-05 | 2019-12-08 | 1398/09/14 | 1398/09/17
230-HIGH PRESSURE OXYGEN TO SLAG TAPHOLES (23S3-ECC-OXG-036) | 23S3-ECC-OXG-036 |  | 230 | OXG |  |  | 7 | 2019-12-06 | 2019-12-13 | 1398/09/15 | 1398/09/22
HIGH PRESSURE OXYGEN TO SLAG TAPHOLES PIPING SYSTEM (230-EC-OXG-PI-001) | 23S3-ECC-OXG-036 | 230-EC-OXG-PI-001 | 230 | OXG | PI |  | 7 | 2019-12-06 | 2019-12-13 | 1398/09/15 | 1398/09/22
23S3-PC-230-PI-100 | 23S3-ECC-OXG-036 | 230-EC-OXG-PI-001 | 230 | OXG | PI | Punch Clearance | 2 | 2019-12-06 | 2019-12-08 | 1398/09/15 | 1398/09/17
23S3-PC-230-PI-110 | 23S3-ECC-OXG-036 | 230-EC-OXG-PI-001 | 230 | OXG | PI | Chemical Cleaning | 5 | 2019-12-08 | 2019-12-13 | 1398/09/17 | 1398/09/22
250-OXYGEN DISTRIBUTION SYSTEM (23S3-ECC-OXE-005) | 23S3-ECC-OXE-005 |  | 250 | OXE |  |  | 5 | 2019-12-08 | 2019-12-13 | 1398/09/17 | 1398/09/22
OXYGEN DISTRIBUTION INSTRUMENTATION SYSTEM (250-EC-OXE-IN-001) | 23S3-ECC-OXE-005 | 250-EC-OXE-IN-001 | 250 | OXE | IN |  | 5 | 2019-12-08 | 2019-12-13 | 1398/09/17 | 1398/09/22
23S3-PC-250-IN-100 | 23S3-ECC-OXE-005 | 250-EC-OXE-IN-001 | 250 | OXE | IN | Instrument Cable Check and continuity megger test | 1 | 2019-12-08 | 2019-12-09 | 1398/09/17 | 1398/09/18
23S3-PC-250-IN-110 | 23S3-ECC-OXE-005 | 250-EC-OXE-IN-001 | 250 | OXE | IN | device calibration | 1 | 2019-12-09 | 2019-12-10 | 1398/09/18 | 1398/09/19
23S3-PC-250-IN-120 | 23S3-ECC-OXE-005 | 250-EC-OXE-IN-001 | 250 | OXE | IN | device installation final check and punch clearance | 1 | 2019-12-10 | 2019-12-11 | 1398/09/19 | 1398/09/20
23S3-PC-250-IN-130 | 23S3-ECC-OXE-005 | 250-EC-OXE-IN-001 | 250 | OXE | IN | IO and loop checking | 1 | 2019-12-11 | 2019-12-12 | 1398/09/20 | 1398/09/21
23S3-PC-250-IN-140 | 23S3-ECC-OXE-005 | 250-EC-OXE-IN-001 | 250 | OXE | IN | function test | 1 | 2019-12-12 | 2019-12-13 | 1398/09/21 | 1398/09/22
OXYGEN DISTRIBUTION SYSTEM DUCT WORK (250-EC-OXE-ME-001) | 23S3-ECC-OXE-005 | 250-EC-OXE-ME-001 | 250 | OXE | ME |  | 4 | 2019-12-09 | 2019-12-13 | 1398/09/18 | 1398/09/22
23S3-PC-250-ME-100 | 23S3-ECC-OXE-005 | 250-EC-OXE-ME-001 | 250 | OXE | ME | duct work final check and punch clearance | 3 | 2019-12-09 | 2019-12-12 | 1398/09/18 | 1398/09/21
23S3-PC-250-ME-120 | 23S3-ECC-OXE-005 | 250-EC-OXE-ME-001 | 250 | OXE | ME | Final Box-up | 1 | 2019-12-12 | 2019-12-13 | 1398/09/21 | 1398/09/22
OXYGEN DISTRIBUTION PIPING SYSTEM (250-EC-OXE-PI-001) | 23S3-ECC-OXE-005 | 250-EC-OXE-PI-001 | 250 | OXE | PI |  | 4 | 2019-12-09 | 2019-12-13 | 1398/09/18 | 1398/09/22
23S3-PC-250-PI-100 | 23S3-ECC-OXE-005 | 250-EC-OXE-PI-001 | 250 | OXE | PI | Punch Clearance | 2 | 2019-12-09 | 2019-12-11 | 1398/09/18 | 1398/09/20
23S3-PC-250-PI-110 | 23S3-ECC-OXE-005 | 250-EC-OXE-PI-001 | 250 | OXE | PI | Chemical Cleaning | 2 | 2019-12-11 | 2019-12-13 | 1398/09/20 | 1398/09/22
230-VENTATION GAS HANDLING (23S3-ECC-VGH-004) | 23S3-ECC-VGH-004 |  | 230 | VGH |  |  | 9 | 2019-12-10 | 2019-12-19 | 1398/09/19 | 1398/09/28
VENTATION GAS HANDLING ELECTRICAL (230-EC-VGH-EL-001) | 23S3-ECC-VGH-004 | 230-EC-VGH-EL-001 | 230 | VGH | EL |  | 5 | 2019-12-10 | 2019-12-15 | 1398/09/19 | 1398/09/24
23S3-PC-230-EL-180 | 23S3-ECC-VGH-004 | 230-EC-VGH-EL-001 | 230 | VGH | EL | Electrical Cable Check and continuity megger test | 1 | 2019-12-10 | 2019-12-11 | 1398/09/19 | 1398/09/20
23S3-PC-230-EL-190 | 23S3-ECC-VGH-004 | 230-EC-VGH-EL-001 | 230 | VGH | EL | gland and connection final inspection | 1 | 2019-12-11 | 2019-12-12 | 1398/09/20 | 1398/09/21
23S3-PC-230-EL-200 | 23S3-ECC-VGH-004 | 230-EC-VGH-EL-001 | 230 | VGH | EL | motor continuity megger test | 1 | 2019-12-12 | 2019-12-13 | 1398/09/21 | 1398/09/22
23S3-PC-230-EL-210 | 23S3-ECC-VGH-004 | 230-EC-VGH-EL-001 | 230 | VGH | EL | feeder final checking | 1 | 2019-12-13 | 2019-12-14 | 1398/09/22 | 1398/09/23
23S3-PC-230-EL-220 | 23S3-ECC-VGH-004 | 230-EC-VGH-EL-001 | 230 | VGH | EL | motor load run test | 1 | 2019-12-14 | 2019-12-15 | 1398/09/23 | 1398/09/24
VENTILATION GAS HANDELING INSTRUMENTATION (230-EC-VGH-IN-001) | 23S3-ECC-VGH-004 | 230-EC-VGH-IN-001 | 230 | VGH | IN |  | 5 | 2019-12-11 | 2019-12-16 | 1398/09/20 | 1398/09/25
23S3-PC-230-IN-150 | 23S3-ECC-VGH-004 | 230-EC-VGH-IN-001 | 230 | VGH | IN | Instrument Cable Check and continuity megger test | 1 | 2019-12-11 | 2019-12-12 | 1398/09/20 | 1398/09/21
23S3-PC-230-IN-160 | 23S3-ECC-VGH-004 | 230-EC-VGH-IN-001 | 230 | VGH | IN | device calibration | 1 | 2019-12-12 | 2019-12-13 | 1398/09/21 | 1398/09/22
23S3-PC-230-IN-170 | 23S3-ECC-VGH-004 | 230-EC-VGH-IN-001 | 230 | VGH | IN | device installation final check and punch clearance | 1 | 2019-12-13 | 2019-12-14 | 1398/09/22 | 1398/09/23
23S3-PC-230-IN-180 | 23S3-ECC-VGH-004 | 230-EC-VGH-IN-001 | 230 | VGH | IN | IO and loop checking | 1 | 2019-12-14 | 2019-12-15 | 1398/09/23 | 1398/09/24
23S3-PC-230-IN-190 | 23S3-ECC-VGH-004 | 230-EC-VGH-IN-001 | 230 | VGH | IN | function test | 1 | 2019-12-15 | 2019-12-16 | 1398/09/24 | 1398/09/25
VENTILATION GAS HANDELING MACHINERY (230-EC-VGH-ME-001) | 23S3-ECC-VGH-004 | 230-EC-VGH-ME-001 | 230 | VGH | ME |  | 6 | 2019-12-13 | 2019-12-19 | 1398/09/22 | 1398/09/28
23S3-PC-230-ME-100 | 23S3-ECC-VGH-004 | 230-EC-VGH-ME-001 | 230 | VGH | ME | Motor installation final check and punch clearance | 2 | 2019-12-13 | 2019-12-15 | 1398/09/22 | 1398/09/24
23S3-PC-230-ME-110 | 23S3-ECC-VGH-004 | 230-EC-VGH-ME-001 | 230 | VGH | ME | Flange Parallel Check and adjastment | 2 | 2019-12-15 | 2019-12-17 | 1398/09/24 | 1398/09/26
23S3-PC-230-ME-120 | 23S3-ECC-VGH-004 | 230-EC-VGH-ME-001 | 230 | VGH | ME | Final Box-up | 2 | 2019-12-17 | 2019-12-19 | 1398/09/26 | 1398/09/28
VENTILATION GAS HANDELING MECHANICAL (230-EC-VGH-ME-002) | 23S3-ECC-VGH-004 | 230-EC-VGH-ME-002 | 230 | VGH | ME |  | 6 | 2019-12-13 | 2019-12-19 | 1398/09/22 | 1398/09/28
23S3-PC-230-ME-130 | 23S3-ECC-VGH-004 | 230-EC-VGH-ME-002 | 230 | VGH | ME | Check For Pre-Box up | 4 | 2019-12-13 | 2019-12-17 | 1398/09/22 | 1398/09/26
23S3-PC-230-ME-150 | 23S3-ECC-VGH-004 | 230-EC-VGH-ME-002 | 230 | VGH | ME | Final Box-up | 2 | 2019-12-17 | 2019-12-19 | 1398/09/26 | 1398/09/28
By Pass Damper Bridge Crain System (220-EC-CRN-047) | 220-EC-CRN-047 |  | 220 | CRN |  |  | 10 | 2019-12-18 | 2019-12-28 | 1398/09/27 | 1398/10/07
FSF CRANE ELECTRICAL SYSTEM (220-EC-BPD-EL-001) | 220-EC-CRN-047 | 220-EC-BPD-EL-001 | 220 | CRN | EL |  | 5 | 2019-12-23 | 2019-12-28 | 1398/10/02 | 1398/10/07
23S3-PC-220-EL-440 | 220-EC-CRN-047 | 220-EC-BPD-EL-001 | 220 | CRN | EL | Electrical Cable Check and continuity megger test | 1 | 2019-12-23 | 2019-12-24 | 1398/10/02 | 1398/10/03
23S3-PC-220-EL-450 | 220-EC-CRN-047 | 220-EC-BPD-EL-001 | 220 | CRN | EL | motor continuity megger test | 1 | 2019-12-24 | 2019-12-25 | 1398/10/03 | 1398/10/04
23S3-PC-220-EL-460 | 220-EC-CRN-047 | 220-EC-BPD-EL-001 | 220 | CRN | EL | gland and connection final inspection | 1 | 2019-12-25 | 2019-12-26 | 1398/10/04 | 1398/10/05
23S3-PC-220-EL-480 | 220-EC-CRN-047 | 220-EC-BPD-EL-001 | 220 | CRN | EL | feeder final checking | 1 | 2019-12-26 | 2019-12-27 | 1398/10/05 | 1398/10/06
23S3-PC-220-EL-490 | 220-EC-CRN-047 | 220-EC-BPD-EL-001 | 220 | CRN | EL | motor load run test | 1 | 2019-12-27 | 2019-12-28 | 1398/10/06 | 1398/10/07
FSF CRANE MECHANICAL SYSTEM (220-EC-BPD-ME-001) | 220-EC-CRN-047 | 220-EC-BPD-ME-001 | 220 | CRN | ME |  | 2 | 2019-12-18 | 2019-12-20 | 1398/09/27 | 1398/09/29
23S3-PC-220-ME-440 | 220-EC-CRN-047 | 220-EC-BPD-ME-001 | 220 | CRN | ME | final check and punch clearance | 1 | 2019-12-18 | 2019-12-19 | 1398/09/27 | 1398/09/28
23S3-PC-220-ME-450 | 220-EC-CRN-047 | 220-EC-BPD-ME-001 | 220 | CRN | ME | final boxup | 1 | 2019-12-19 | 2019-12-20 | 1398/09/28 | 1398/09/29

## لیست ECهای کانی مس 980827
Activity ID | ECC NO. | EC NO. | Area | ECC | Discipline | Activity Name | Duration | Start | Finish | Start | Finish
021-LV Switchgear System (23S3-ECC-MCC-037) | 23S3-ECC-MCC-037 |  | 021 | MCC |  |  | 4 | 2019-11-06 | 2019-11-10 | 1398/08/15 | 1398/08/19
LV Switchgear System (21-EC-LVS-EL-001) | 23S3-ECC-MCC-037 | 021-EC-LVS-EL-001 | 021 | MCC | EL |  | 3 | 2019-11-06 | 2019-11-09 | 1398/08/15 | 1398/08/18
23S3-PC-021-EL-100 | 23S3-ECC-MCC-037 | 021-EC-LVS-EL-001 | 021 | MCC | EL | Panel installation final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-021-EL-105 | 23S3-ECC-MCC-037 | 021-EC-LVS-EL-001 | 021 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-021-EL-110 | 23S3-ECC-MCC-037 | 021-EC-LVS-EL-001 | 021 | MCC | EL | Earthing check, test and punch clearance | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-021-EL-120 | 23S3-ECC-MCC-037 | 021-EC-LVS-EL-001 | 021 | MCC | EL | CT/PT check and test | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-021-EL-130 | 23S3-ECC-MCC-037 | 021-EC-LVS-EL-001 | 021 | MCC | EL | Relay setting test | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
UPS & Battery System (21-EC-UPS-EL-002) | 23S3-ECC-MCC-037 | 021-EC-UPS-EL-002 | 021 | MCC | EL |  | 4 | 2019-11-06 | 2019-11-10 | 1398/08/15 | 1398/08/19
23S3-PC-021-EL-150 | 23S3-ECC-MCC-037 | 021-EC-UPS-EL-002 | 021 | MCC | EL | Panel installation final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-021-EL-155 | 23S3-ECC-MCC-037 | 021-EC-UPS-EL-002 | 021 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-021-EL-160 | 23S3-ECC-MCC-037 | 021-EC-UPS-EL-002 | 021 | MCC | EL | Earthing / lightening check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-021-EL-165 | 23S3-ECC-MCC-037 | 021-EC-UPS-EL-002 | 021 | MCC | EL | UPS check and punch clearance | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-021-EL-170 | 23S3-ECC-MCC-037 | 021-EC-UPS-EL-002 | 021 | MCC | EL | Relay setting test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
Heat tracing System (21-EC-HET-EL-003) | 23S3-ECC-MCC-037 | 021-EC-HET-EL-003 | 021 | MCC | EL |  | 3 | 2019-11-06 | 2019-11-09 | 1398/08/15 | 1398/08/18
23S3-PC-021-EL-200 | 23S3-ECC-MCC-037 | 021-EC-HET-EL-003 | 021 | MCC | EL | Panel installation and final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-021-EL-205 | 23S3-ECC-MCC-037 | 021-EC-HET-EL-003 | 021 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-021-EL-210 | 23S3-ECC-MCC-037 | 021-EC-HET-EL-003 | 021 | MCC | EL | Earthing / lightening check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
150-LV Switchgear System (23S3-ECC-MCC-038) | 23S3-ECC-MCC-038 |  | 150 | MCC |  |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
LV Switchgear System (150-EC-LVS-EL-001) | 23S3-ECC-MCC-038 | 150-EC-LVS-EL-001 | 150 | MCC | EL |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
23S3-PC-150-EL-100 | 23S3-ECC-MCC-038 | 150-EC-LVS-EL-001 | 150 | MCC | EL | Panel installation and final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-150-EL-105 | 23S3-ECC-MCC-038 | 150-EC-LVS-EL-001 | 150 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-150-EL-110 | 23S3-ECC-MCC-038 | 150-EC-LVS-EL-001 | 150 | MCC | EL | Earthing / lightening check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-150-EL-120 | 23S3-ECC-MCC-038 | 150-EC-LVS-EL-001 | 150 | MCC | EL | CT/PT check and test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-150-EL-130 | 23S3-ECC-MCC-038 | 150-EC-LVS-EL-001 | 150 | MCC | EL | Relay setting test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
200-LV Switchgear System (23S3-ECC-MCC-039) | 23S3-ECC-MCC-039 |  | 200 | MCC |  |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
LV Switchgear System (200-EC-LVS-EL-002) | 23S3-ECC-MCC-039 | 200-EC-LVS-EL-002 | 200 | MCC | EL |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
23S3-PC-200-EL-100 | 23S3-ECC-MCC-039 | 200-EC-LVS-EL-002 | 200 | MCC | EL | Panel installation and final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-200-EL-105 | 23S3-ECC-MCC-039 | 200-EC-LVS-EL-002 | 200 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-200-EL-110 | 23S3-ECC-MCC-039 | 200-EC-LVS-EL-002 | 200 | MCC | EL | Earthing / lightening check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-200-EL-120 | 23S3-ECC-MCC-039 | 200-EC-LVS-EL-002 | 200 | MCC | EL | CT/PT check and test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-200-EL-130 | 23S3-ECC-MCC-039 | 200-EC-LVS-EL-002 | 200 | MCC | EL | Relay setting test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
210-LV Switchgear System (23S3-ECC-MCC-040) | 23S3-ECC-MCC-040 |  | 210 | MCC |  |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
Earthing & Lightning (210-EC-EAT-EL-001) | 23S3-ECC-MCC-040 | 210-EC-EAT-EL-001 | 210 | MCC | EL |  | 4 | 2019-11-06 | 2019-11-10 | 1398/08/15 | 1398/08/19
23S3-PC-210-EL-100 | 23S3-ECC-MCC-040 | 210-EC-EAT-EL-001 | 210 | MCC | EL | Panel installation and final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-210-EL-105 | 23S3-ECC-MCC-040 | 210-EC-EAT-EL-001 | 210 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-210-EL-110 | 23S3-ECC-MCC-040 | 210-EC-EAT-EL-001 | 210 | MCC | EL | Earthing / lightening check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-210-EL-120 | 23S3-ECC-MCC-040 | 210-EC-EAT-EL-001 | 210 | MCC | EL | Relay setting test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
LV Switchgear System (210-EC-LVS-EL-002) | 23S3-ECC-MCC-040 | 210-EC-LVS-EL-002 | 210 | MCC | EL |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
23S3-PC-210-EL-140 | 23S3-ECC-MCC-040 | 210-EC-LVS-EL-002 | 210 | MCC | EL | Panel installation and final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-210-EL-145 | 23S3-ECC-MCC-040 | 210-EC-LVS-EL-002 | 210 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-210-EL-150 | 23S3-ECC-MCC-040 | 210-EC-LVS-EL-002 | 210 | MCC | EL | Earthing / lightening check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-210-EL-160 | 23S3-ECC-MCC-040 | 210-EC-LVS-EL-002 | 210 | MCC | EL | CT/PT check and test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-210-EL-170 | 23S3-ECC-MCC-040 | 210-EC-LVS-EL-002 | 210 | MCC | EL | Relay setting test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
220-LV Switchgear System (23S3-ECC-MCC-041) | 23S3-ECC-MCC-041 |  | 220 | MCC |  |  | 9 | 2019-11-06 | 2019-11-15 | 1398/08/15 | 1398/08/24
LV Switchgear System (220-EC-LVS-EL-001) | 23S3-ECC-MCC-041 | 220-EC-LVS-EL-001 | 220 | MCC | EL |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
23S3-PC-220-EL-100 | 23S3-ECC-MCC-041 | 220-EC-LVS-EL-001 | 220 | MCC | EL | Panel installation and final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-220-EL-105 | 23S3-ECC-MCC-041 | 220-EC-LVS-EL-001 | 220 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-220-EL-110 | 23S3-ECC-MCC-041 | 220-EC-LVS-EL-001 | 220 | MCC | EL | Earthing / lightening check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-220-EL-120 | 23S3-ECC-MCC-041 | 220-EC-LVS-EL-001 | 220 | MCC | EL | CT/PT check and test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-220-EL-130 | 23S3-ECC-MCC-041 | 220-EC-LVS-EL-001 | 220 | MCC | EL | Relay setting test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
LV TRANSFORMER SYSTEM (220-EC-TR-EL-002) | 23S3-ECC-MCC-041 | 220-EC-TR-EL-002 | 220 | MCC | EL |  | 7 | 2019-11-06 | 2019-11-13 | 1398/08/15 | 1398/08/22
23S3-PC-220-EL-150 | 23S3-ECC-MCC-041 | 220-EC-TR-EL-002 | 220 | MCC | EL | Transformer Installation final Check | 3 | 2019-11-06 | 2019-11-09 | 1398/08/15 | 1398/08/18
23S3-PC-220-EL-155 | 23S3-ECC-MCC-041 | 220-EC-TR-EL-002 | 220 | MCC | EL | Earthing check, test and punch clearance | 2 | 2019-11-09 | 2019-11-11 | 1398/08/18 | 1398/08/20
23S3-PC-220-EL-160 | 23S3-ECC-MCC-041 | 220-EC-TR-EL-002 | 220 | MCC | EL | CT/PT check and test | 1 | 2019-11-11 | 2019-11-12 | 1398/08/20 | 1398/08/21
23S3-PC-220-EL-170 | 23S3-ECC-MCC-041 | 220-EC-TR-EL-002 | 220 | MCC | EL | Relay setting test | 1 | 2019-11-12 | 2019-11-13 | 1398/08/21 | 1398/08/22
Earthing & Lightning (220-EC-EAT-EL-003) | 23S3-ECC-MCC-041 | 220-EC-EAT-EL-003 | 220 | MCC | EL |  | 3 | 2019-11-12 | 2019-11-15 | 1398/08/21 | 1398/08/24
23S3-PC-220-EL-190 | 23S3-ECC-MCC-041 | 220-EC-EAT-EL-003 | 220 | MCC | EL | Relay setting test | 1 | 2019-11-12 | 2019-11-13 | 1398/08/21 | 1398/08/22
23S3-PC-220-EL-200 | 23S3-ECC-MCC-041 | 220-EC-EAT-EL-003 | 220 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-13 | 2019-11-14 | 1398/08/22 | 1398/08/23
23S3-PC-220-EL-210 | 23S3-ECC-MCC-041 | 220-EC-EAT-EL-003 | 220 | MCC | EL | Earthing / lightening check, test and punch clearance | 1 | 2019-11-14 | 2019-11-15 | 1398/08/23 | 1398/08/24
225-LV Switchgear System (23S3-ECC-MCC-042) | 23S3-ECC-MCC-042 |  | 225 | MCC |  |  | 9 | 2019-11-06 | 2019-11-15 | 1398/08/15 | 1398/08/24
LV TRANSFORMER SYSTEM (225-EC-TR-EL-001) | 23S3-ECC-MCC-042 | 225-EC-TR-EL-001 | 225 | MCC | EL |  | 7 | 2019-11-08 | 2019-11-15 | 1398/08/17 | 1398/08/24
23S3-PC-225-EL-100 | 23S3-ECC-MCC-042 | 225-EC-TR-EL-001 | 225 | MCC | EL | Transformer Installation final Check | 3 | 2019-11-08 | 2019-11-11 | 1398/08/17 | 1398/08/20
23S3-PC-225-EL-105 | 23S3-ECC-MCC-042 | 225-EC-TR-EL-001 | 225 | MCC | EL | Earthing check, test and punch clearance | 2 | 2019-11-11 | 2019-11-13 | 1398/08/20 | 1398/08/22
23S3-PC-225-EL-110 | 23S3-ECC-MCC-042 | 225-EC-TR-EL-001 | 225 | MCC | EL | CT/PT check and test | 1 | 2019-11-13 | 2019-11-14 | 1398/08/22 | 1398/08/23
23S3-PC-225-EL-120 | 23S3-ECC-MCC-042 | 225-EC-TR-EL-001 | 225 | MCC | EL | Relay setting test | 1 | 2019-11-14 | 2019-11-15 | 1398/08/23 | 1398/08/24
LV Switchgear System (225-EC-LVS-EL-002) | 23S3-ECC-MCC-042 | 225-EC-LVS-EL-002 | 225 | MCC | EL |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
23S3-PC-225-EL-140 | 23S3-ECC-MCC-042 | 225-EC-LVS-EL-002 | 225 | MCC | EL | Panel installation and final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-225-EL-145 | 23S3-ECC-MCC-042 | 225-EC-LVS-EL-002 | 225 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-225-EL-150 | 23S3-ECC-MCC-042 | 225-EC-LVS-EL-002 | 225 | MCC | EL | Earthing check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-225-EL-160 | 23S3-ECC-MCC-042 | 225-EC-LVS-EL-002 | 225 | MCC | EL | CT/PT check and test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-225-EL-170 | 23S3-ECC-MCC-042 | 225-EC-LVS-EL-002 | 225 | MCC | EL | Relay setting test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
230-LV Switchgear System (23S3-ECC-MCC-043) | 23S3-ECC-MCC-043 |  | 230 | MCC |  |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
LV Switchgear System (230-EC-LVS-EL-001) | 23S3-ECC-MCC-043 | 230-EC-LVS-EL-001 | 230 | MCC | EL |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
23S3-PC-230-EL-100 | 23S3-ECC-MCC-043 | 230-EC-LVS-EL-001 | 230 | MCC | EL | Panel installation and final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-230-EL-105 | 23S3-ECC-MCC-043 | 230-EC-LVS-EL-001 | 230 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-230-EL-110 | 23S3-ECC-MCC-043 | 230-EC-LVS-EL-001 | 230 | MCC | EL | Earthing check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-230-EL-120 | 23S3-ECC-MCC-043 | 230-EC-LVS-EL-001 | 230 | MCC | EL | CT/PT check and test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-230-EL-130 | 23S3-ECC-MCC-043 | 230-EC-LVS-EL-001 | 230 | MCC | EL | Relay setting test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
270-LV Switchgear System (23S3-ECC-MCC-044) | 23S3-ECC-MCC-044 |  | 270 | MCC |  |  | 18 | 2019-11-06 | 2019-11-24 | 1398/08/15 | 1398/09/03
LV TRANSFORMER SYSTEM (270-EC-TR-EL-001) | 23S3-ECC-MCC-044 | 270-EC-TR-EL-001 | 270 | MCC | EL |  | 6 | 2019-11-07 | 2019-11-13 | 1398/08/16 | 1398/08/22
23S3-PC-270-EL-100 | 23S3-ECC-MCC-044 | 270-EC-TR-EL-001 | 270 | MCC | EL | Transformer Installation final Check /oil circulation | 2 | 2019-11-07 | 2019-11-09 | 1398/08/16 | 1398/08/18
23S3-PC-270-EL-110 | 23S3-ECC-MCC-044 | 270-EC-TR-EL-001 | 270 | MCC | EL | Panel installation final check and punch clearance | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-270-EL-120 | 23S3-ECC-MCC-044 | 270-EC-TR-EL-001 | 270 | MCC | EL | Earthing check, test and punch clearance | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
23S3-PC-270-EL-130 | 23S3-ECC-MCC-044 | 270-EC-TR-EL-001 | 270 | MCC | EL | CT/PT check and test | 1 | 2019-11-11 | 2019-11-12 | 1398/08/20 | 1398/08/21
23S3-PC-270-EL-140 | 23S3-ECC-MCC-044 | 270-EC-TR-EL-001 | 270 | MCC | EL | Relay setting test | 1 | 2019-11-12 | 2019-11-13 | 1398/08/21 | 1398/08/22
LV Switchgear System (270-EC-LVS-EL-002) | 23S3-ECC-MCC-044 | 270-EC-LVS-EL-002 | 270 | MCC | EL |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
23S3-PC-270-EL-180 | 23S3-ECC-MCC-044 | 270-EC-LVS-EL-002 | 270 | MCC | EL | Panel installation final check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-270-EL-185 | 23S3-ECC-MCC-044 | 270-EC-LVS-EL-002 | 270 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-270-EL-190 | 23S3-ECC-MCC-044 | 270-EC-LVS-EL-002 | 270 | MCC | EL | Earthing check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-270-EL-200 | 23S3-ECC-MCC-044 | 270-EC-LVS-EL-002 | 270 | MCC | EL | CT/PT check and test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-270-EL-210 | 23S3-ECC-MCC-044 | 270-EC-LVS-EL-002 | 270 | MCC | EL | Relay setting test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
Earthing & Lightning (270-EC-EAT-EL-003) | 23S3-ECC-MCC-044 | 270-EC-EAT-EL-003 | 270 | MCC | EL |  | 6 | 2019-11-13 | 2019-11-19 | 1398/08/22 | 1398/08/28
23S3-PC-270-EL-220 | 23S3-ECC-MCC-044 | 270-EC-EAT-EL-003 | 270 | MCC | EL | Cable Puling Check and megger test | 2 | 2019-11-13 | 2019-11-15 | 1398/08/22 | 1398/08/24
23S3-PC-270-EL-230 | 23S3-ECC-MCC-044 | 270-EC-EAT-EL-003 | 270 | MCC | EL | Earthing check, test and punch clearance | 2 | 2019-11-15 | 2019-11-17 | 1398/08/24 | 1398/08/26
23S3-PC-270-EL-240 | 23S3-ECC-MCC-044 | 270-EC-EAT-EL-003 | 270 | MCC | EL | Relay setting test | 2 | 2019-11-17 | 2019-11-19 | 1398/08/26 | 1398/08/28
F&G System (270-EC-F&G-EL-004) | 23S3-ECC-MCC-044 | 270-EC-F&G-EL-004 | 270 | MCC | EL |  | 6 | 2019-11-16 | 2019-11-22 | 1398/08/25 | 1398/09/01
23S3-PC-270-EL-250 | 23S3-ECC-MCC-044 | 270-EC-F&G-EL-004 | 270 | MCC | EL | Cable Puling Check and megger test | 2 | 2019-11-16 | 2019-11-18 | 1398/08/25 | 1398/08/27
23S3-PC-270-EL-260 | 23S3-ECC-MCC-044 | 270-EC-F&G-EL-004 | 270 | MCC | EL | Earthing check, test and punch clearance | 2 | 2019-11-18 | 2019-11-20 | 1398/08/27 | 1398/08/29
23S3-PC-270-EL-270 | 23S3-ECC-MCC-044 | 270-EC-F&G-EL-004 | 270 | MCC | EL | Relay setting test | 2 | 2019-11-20 | 2019-11-22 | 1398/08/29 | 1398/09/01
Heat tracing System (270-EC-HET-EL-005) | 23S3-ECC-MCC-044 | 270-EC-HET-EL-005 | 270 | MCC | EL |  | 4 | 2019-11-20 | 2019-11-24 | 1398/08/29 | 1398/09/03
23S3-PC-270-EL-460 | 23S3-ECC-MCC-044 | 270-EC-HET-EL-005 | 270 | MCC | EL | Cable Puling Check and megger test | 2 | 2019-11-20 | 2019-11-22 | 1398/08/29 | 1398/09/01
23S3-PC-270-EL-490 | 23S3-ECC-MCC-044 | 270-EC-HET-EL-005 | 270 | MCC | EL | Earthing check, test and punch clearance | 2 | 2019-11-22 | 2019-11-24 | 1398/09/01 | 1398/09/03
Lighting and Small Power System (270-EC-LIT-EL-006) | 23S3-ECC-MCC-044 | 270-EC-LIT-EL-006 | 270 | MCC | EL |  | 7 | 2019-11-14 | 2019-11-21 | 1398/08/23 | 1398/08/30
23S3-PC-270-EL-500 | 23S3-ECC-MCC-044 | 270-EC-LIT-EL-006 | 270 | MCC | EL | Panel installation final check and punch clearance | 4 | 2019-11-14 | 2019-11-18 | 1398/08/23 | 1398/08/27
23S3-PC-270-EL-510 | 23S3-ECC-MCC-044 | 270-EC-LIT-EL-006 | 270 | MCC | EL | Cable Puling Check and megger test | 3 | 2019-11-17 | 2019-11-20 | 1398/08/26 | 1398/08/29
23S3-PC-270-EL-520 | 23S3-ECC-MCC-044 | 270-EC-LIT-EL-006 | 270 | MCC | EL | Earthing check, test and punch clearance | 2 | 2019-11-19 | 2019-11-21 | 1398/08/28 | 1398/08/30
200-MV PANEL SYSTEM (23S3-ECC-MCC-045) | 23S3-ECC-MCC-045 |  | 200 | MCC |  |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
MV PANEL ELECTRICAL SYSTEM (200-EC-MV-EL-001) | 23S3-ECC-MCC-045 | 200-EC-MV-EL-001 | 200 | MCC | EL |  | 5 | 2019-11-06 | 2019-11-11 | 1398/08/15 | 1398/08/20
23S3-PC-200-EL-190 | 23S3-ECC-MCC-045 | 200-EC-MV-EL-001 | 200 | MCC | EL | Panel installation and check and punch clearance | 1 | 2019-11-06 | 2019-11-07 | 1398/08/15 | 1398/08/16
23S3-PC-200-EL-195 | 23S3-ECC-MCC-045 | 200-EC-MV-EL-001 | 200 | MCC | EL | Cable Puling Check and megger test | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-200-EL-200 | 23S3-ECC-MCC-045 | 200-EC-MV-EL-001 | 200 | MCC | EL | Earthing check, test and punch clearance | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-200-EL-210 | 23S3-ECC-MCC-045 | 200-EC-MV-EL-001 | 200 | MCC | EL | CT/PT check and test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-200-EL-220 | 23S3-ECC-MCC-045 | 200-EC-MV-EL-001 | 200 | MCC | EL | Relay setting test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
220-MAIN CONTROL ROOM (23S3-ECC-ITR-046) | 23S3-ECC-ITR-046 |  | 220 | ITR |  |  | 26 | 2019-11-07 | 2019-12-03 | 1398/08/16 | 1398/09/12
Plant Control System - DCS (220-EC-ITR-IN-001) | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN |  | 26 | 2019-11-07 | 2019-12-03 | 1398/08/16 | 1398/09/12
23S3-PC-220-IN-340 | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN | Cabinet installation check and punch clearance | 3 | 2019-11-07 | 2019-11-10 | 1398/08/16 | 1398/08/19
23S3-PC-220-IN-345 | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN | PDP panel installation check and punch clearance | 2 | 2019-11-10 | 2019-11-12 | 1398/08/19 | 1398/08/21
23S3-PC-220-IN-350 | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN | PDP panel Energizing | 1 | 2019-11-12 | 2019-11-13 | 1398/08/21 | 1398/08/22
23S3-PC-220-IN-352 | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN | Vendor At Site ( PLT ) | 0 | 2019-11-13 |  | 1398/08/22
23S3-PC-220-IN-355 | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN | Logic Check and Function Test ( Area 270 ) | 5 | 2019-11-13 | 2019-11-18 | 1398/08/22 | 1398/08/27
23S3-PC-220-IN-360 | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN | Logic Check and Function Test ( Area 220 ) | 5 | 2019-11-15 | 2019-11-20 | 1398/08/24 | 1398/08/29
23S3-PC-220-IN-365 | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN | Logic Check and Function Test ( Area 150,210,200,225,230 ) | 7 | 2019-11-18 | 2019-11-25 | 1398/08/27 | 1398/09/04
23S3-PC-220-IN-370 | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN | Alarm and Trip Setting Configuration | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
23S3-PC-220-IN-375 | 23S3-ECC-ITR-046 | 220-EC-ITR-IN-001 | 220 | ITR | IN | Control system and software loading and feedback check and redinees for Function test | 20 | 2019-11-13 | 2019-12-03 | 1398/08/22 | 1398/09/12
200 - PLANT AIR COMPRESSED SYSTEM (23S3-ECC-PLA-003) | 23S3-ECC-PLA-003 |  | 200 | PLA |  |  | 16 | 2019-11-07 | 2019-11-23 | 1398/08/16 | 1398/09/02
PLANT AIR COMPRESSED ELECTRICAL SYSTEM (200-EC-PLA-EL-001) | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-001 | 200 | PLA | EL |  | 8 | 2019-11-07 | 2019-11-15 | 1398/08/16 | 1398/08/24
23S3-PC-200-EL-260 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-001 | 200 | PLA | EL | Electrical Cable Check and continuity megger test | 3 | 2019-11-07 | 2019-11-10 | 1398/08/16 | 1398/08/19
23S3-PC-200-EL-270 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-001 | 200 | PLA | EL | motor continuity megger test | 2 | 2019-11-08 | 2019-11-10 | 1398/08/17 | 1398/08/19
23S3-PC-200-EL-280 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-001 | 200 | PLA | EL | gland and connection final inspection | 2 | 2019-11-09 | 2019-11-11 | 1398/08/18 | 1398/08/20
23S3-PC-200-EL-290 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-001 | 200 | PLA | EL | Local panel final function test | 2 | 2019-11-10 | 2019-11-12 | 1398/08/19 | 1398/08/21
23S3-PC-200-EL-300 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-001 | 200 | PLA | EL | feeder final checking | 2 | 2019-11-11 | 2019-11-13 | 1398/08/20 | 1398/08/22
23S3-PC-200-EL-305 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-001 | 200 | PLA | EL | Vendor At Site ( Novin Hava ) | 0 | 2019-11-13 |  | 1398/08/22
23S3-PC-200-EL-310 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-001 | 200 | PLA | EL | motor free run and load run test | 2 | 2019-11-13 | 2019-11-15 | 1398/08/22 | 1398/08/24
PLANT AIR COMPRESSED ELECTRICAL SYSTEM (200-EC-PLA-EL-002) | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-002 | 200 | PLA | EL |  | 8 | 2019-11-07 | 2019-11-15 | 1398/08/16 | 1398/08/24
23S3-PC-200-EL-320 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-002 | 200 | PLA | EL | Electrical Cable Check and continuity megger test | 3 | 2019-11-07 | 2019-11-10 | 1398/08/16 | 1398/08/19
23S3-PC-200-EL-330 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-002 | 200 | PLA | EL | motor continuity megger test | 2 | 2019-11-08 | 2019-11-10 | 1398/08/17 | 1398/08/19
23S3-PC-200-EL-340 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-002 | 200 | PLA | EL | gland and connection final inspection | 2 | 2019-11-09 | 2019-11-11 | 1398/08/18 | 1398/08/20
23S3-PC-200-EL-350 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-002 | 200 | PLA | EL | Local panel final function test | 2 | 2019-11-10 | 2019-11-12 | 1398/08/19 | 1398/08/21
23S3-PC-200-EL-360 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-002 | 200 | PLA | EL | feeder final checking | 2 | 2019-11-11 | 2019-11-13 | 1398/08/20 | 1398/08/22
23S3-PC-200-EL-370 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-002 | 200 | PLA | EL | motor free run and load run test | 2 | 2019-11-13 | 2019-11-15 | 1398/08/22 | 1398/08/24
PLANT AIR COMPRESSED ELECTRICAL SYSTEM (200-EC-PLA-EL-003) | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-003 | 200 | PLA | EL |  | 8 | 2019-11-07 | 2019-11-15 | 1398/08/16 | 1398/08/24
23S3-PC-200-EL-380 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-003 | 200 | PLA | EL | Electrical Cable Check and continuity megger test | 3 | 2019-11-07 | 2019-11-10 | 1398/08/16 | 1398/08/19
23S3-PC-200-EL-390 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-003 | 200 | PLA | EL | motor continuity megger test | 2 | 2019-11-08 | 2019-11-10 | 1398/08/17 | 1398/08/19
23S3-PC-200-EL-400 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-003 | 200 | PLA | EL | gland and connection final inspection | 2 | 2019-11-09 | 2019-11-11 | 1398/08/18 | 1398/08/20
23S3-PC-200-EL-410 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-003 | 200 | PLA | EL | Local panel final function test | 2 | 2019-11-10 | 2019-11-12 | 1398/08/19 | 1398/08/21
23S3-PC-200-EL-420 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-003 | 200 | PLA | EL | feeder final checking | 2 | 2019-11-11 | 2019-11-13 | 1398/08/20 | 1398/08/22
23S3-PC-200-EL-430 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-003 | 200 | PLA | EL | motor free run and load run test | 2 | 2019-11-13 | 2019-11-15 | 1398/08/22 | 1398/08/24
PLANT AIR COMPRESSED CRANE ELECTRICAL SYSTEM (200-EC-PLA-EL-004) | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-004 | 200 | PLA | EL |  | 7 | 2019-11-07 | 2019-11-14 | 1398/08/16 | 1398/08/23
23S3-PC-200-EL-440 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-004 | 200 | PLA | EL | Electrical Cable Check and continuity megger test | 3 | 2019-11-07 | 2019-11-10 | 1398/08/16 | 1398/08/19
23S3-PC-200-EL-450 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-004 | 200 | PLA | EL | motor continuity megger test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-200-EL-460 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-004 | 200 | PLA | EL | gland and connection final inspection | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
23S3-PC-200-EL-480 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-004 | 200 | PLA | EL | feeder final checking | 1 | 2019-11-12 | 2019-11-13 | 1398/08/21 | 1398/08/22
23S3-PC-200-EL-490 | 23S3-ECC-PLA-003 | 200-EC-PLA-EL-004 | 200 | PLA | EL | motor free run and load run test | 1 | 2019-11-13 | 2019-11-14 | 1398/08/22 | 1398/08/23
PLANT AIR COMPRESSED INSTRUMENT SYSTEM (200-EC-PLA-IN-001) | 23S3-ECC-PLA-003 | 200-EC-PLA-IN-001 | 200 | PLA | IN |  | 13 | 2019-11-10 | 2019-11-23 | 1398/08/19 | 1398/09/02
23S3-PC-200-IN-100 | 23S3-ECC-PLA-003 | 200-EC-PLA-IN-001 | 200 | PLA | IN | device calibration | 3 | 2019-11-10 | 2019-11-13 | 1398/08/19 | 1398/08/22
23S3-PC-200-IN-110 | 23S3-ECC-PLA-003 | 200-EC-PLA-IN-001 | 200 | PLA | IN | Instrument Cable Check and continuity megger test | 5 | 2019-11-11 | 2019-11-16 | 1398/08/20 | 1398/08/25
23S3-PC-200-IN-120 | 23S3-ECC-PLA-003 | 200-EC-PLA-IN-001 | 200 | PLA | IN | device installation final check and punch clearance | 3 | 2019-11-13 | 2019-11-16 | 1398/08/22 | 1398/08/25
23S3-PC-200-IN-130 | 23S3-ECC-PLA-003 | 200-EC-PLA-IN-001 | 200 | PLA | IN | IO and loop checking | 4 | 2019-11-15 | 2019-11-19 | 1398/08/24 | 1398/08/28
23S3-PC-200-IN-140 | 23S3-ECC-PLA-003 | 200-EC-PLA-IN-001 | 200 | PLA | IN | function test | 4 | 2019-11-19 | 2019-11-23 | 1398/08/28 | 1398/09/02
PLANT AIR COMPRESSED MECHANICAL SYSTEM (200-EC-PLA-ME-001) | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-001 | 200 | PLA | ME |  | 5 | 2019-11-10 | 2019-11-16 | 1398/08/19 | 1398/08/25
23S3-PC-200-ME-100 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-001 | 200 | PLA | ME | Motor and Compressor installation final check and punch clearance | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
23S3-PC-200-ME-110 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-001 | 200 | PLA | ME | Flange Parallel Check and adjastment | 1 | 2019-11-11 | 2019-11-12 | 1398/08/20 | 1398/08/21
23S3-PC-200-ME-120 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-001 | 200 | PLA | ME | Coupling Compressor and motor / load run test | 1 | 2019-11-15 | 2019-11-16 | 1398/08/24 | 1398/08/25
23S3-PC-200-ME-130 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-001 | 200 | PLA | ME | check for pre box-up and punch clearance | 3 | 2019-11-10 | 2019-11-13 | 1398/08/19 | 1398/08/22
23S3-PC-200-ME-150 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-001 | 200 | PLA | ME | final boxup | 1 | 2019-11-13 | 2019-11-14 | 1398/08/22 | 1398/08/23
PLANT AIR COMPRESSED MECHANICAL SYSTEM (200-EC-PLA-ME-002) | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-002 | 200 | PLA | ME |  | 5 | 2019-11-10 | 2019-11-16 | 1398/08/19 | 1398/08/25
23S3-PC-200-ME-160 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-002 | 200 | PLA | ME | Motor and Compressor installation final check and punch clearance | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
23S3-PC-200-ME-170 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-002 | 200 | PLA | ME | Flange Parallel Check and adjastment | 1 | 2019-11-11 | 2019-11-12 | 1398/08/20 | 1398/08/21
23S3-PC-200-ME-180 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-002 | 200 | PLA | ME | Coupling Compressor and motor / load run test | 1 | 2019-11-15 | 2019-11-16 | 1398/08/24 | 1398/08/25
23S3-PC-200-ME-190 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-002 | 200 | PLA | ME | check for pre box-up and punch clearance | 3 | 2019-11-10 | 2019-11-13 | 1398/08/19 | 1398/08/22
23S3-PC-200-ME-210 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-002 | 200 | PLA | ME | final boxup | 1 | 2019-11-13 | 2019-11-14 | 1398/08/22 | 1398/08/23
PLANT AIR COMPRESSED MECHANICAL SYSTEM (200-EC-PLA-ME-003) | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-003 | 200 | PLA | ME |  | 5 | 2019-11-10 | 2019-11-16 | 1398/08/19 | 1398/08/25
23S3-PC-200-ME-220 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-003 | 200 | PLA | ME | Motor and Compressor installation final check and punch clearance | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
23S3-PC-200-ME-230 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-003 | 200 | PLA | ME | Flange Parallel Check and adjastment | 1 | 2019-11-11 | 2019-11-12 | 1398/08/20 | 1398/08/21
23S3-PC-200-ME-240 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-003 | 200 | PLA | ME | Coupling Compressor and motor / load run test | 1 | 2019-11-15 | 2019-11-16 | 1398/08/24 | 1398/08/25
23S3-PC-200-ME-250 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-003 | 200 | PLA | ME | check for pre box-up and punch clearance | 3 | 2019-11-11 | 2019-11-14 | 1398/08/20 | 1398/08/23
23S3-PC-200-ME-270 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-003 | 200 | PLA | ME | final boxup | 1 | 2019-11-14 | 2019-11-15 | 1398/08/23 | 1398/08/24
PLANT AIR COMPRESSED CRANE MECHANICAL SYSTEM (200-EC-PLA-ME-004) | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-004 | 200 | PLA | ME |  | 2 | 2019-11-15 | 2019-11-17 | 1398/08/24 | 1398/08/26
23S3-PC-200-ME-320 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-004 | 200 | PLA | ME | Punch Clearance | 1 | 2019-11-15 | 2019-11-16 | 1398/08/24 | 1398/08/25
23S3-PC-200-ME-330 | 23S3-ECC-PLA-003 | 200-EC-PLA-ME-004 | 200 | PLA | ME | Load Test | 1 | 2019-11-16 | 2019-11-17 | 1398/08/25 | 1398/08/26
PLANT AIR COMPRESSED PIPING SYSTEM (200-EC-PLA-PI-001) | 23S3-ECC-PLA-003 | 200-EC-PLA-PI-001 | 200 | PLA | PI |  | 3 | 2019-11-10 | 2019-11-13 | 1398/08/19 | 1398/08/22
23S3-PC-200-PI-100 | 23S3-ECC-PLA-003 | 200-EC-PLA-PI-001 | 200 | PLA | PI | Punch Clearance | 3 | 2019-11-10 | 2019-11-13 | 1398/08/19 | 1398/08/22
220-FSF PLANT AIR DISTRIBUTION NET WORK (23S3-ECC-PLA-018) | 23S3-ECC-PLA-018 |  | 220 | PLA |  |  | 8 | 2019-11-19 | 2019-11-27 | 1398/08/28 | 1398/09/06
FSF Plant Air Distribution Net Work Instrument System (220-EC-PLA-IN-001) | 23S3-ECC-PLA-018 | 220-EC-PLA-IN-001 | 220 | PLA | IN |  | 6 | 2019-11-19 | 2019-11-25 | 1398/08/28 | 1398/09/04
23S3-PC-220-IN-380 | 23S3-ECC-PLA-018 | 220-EC-PLA-IN-001 | 220 | PLA | IN | device calibration | 1 | 2019-11-19 | 2019-11-20 | 1398/08/28 | 1398/08/29
23S3-PC-220-IN-390 | 23S3-ECC-PLA-018 | 220-EC-PLA-IN-001 | 220 | PLA | IN | Instrument Cable Check and continuity megger test | 2 | 2019-11-20 | 2019-11-22 | 1398/08/29 | 1398/09/01
23S3-PC-220-IN-400 | 23S3-ECC-PLA-018 | 220-EC-PLA-IN-001 | 220 | PLA | IN | device installation final check and punch clearance | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-220-IN-410 | 23S3-ECC-PLA-018 | 220-EC-PLA-IN-001 | 220 | PLA | IN | IO and loop checking | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-220-IN-420 | 23S3-ECC-PLA-018 | 220-EC-PLA-IN-001 | 220 | PLA | IN | function test | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
FSF Plant Air Distribution Net Work Mechanic System (220-EC-PLA-ME-001) | 23S3-ECC-PLA-018 | 220-EC-PLA-ME-001 | 220 | PLA | ME |  | 2 | 2019-11-23 | 2019-11-25 | 1398/09/02 | 1398/09/04
23S3-PC-220-ME-100 | 23S3-ECC-PLA-018 | 220-EC-PLA-ME-001 | 220 | PLA | ME | check for pre box-up and punch clearance | 2 | 2019-11-23 | 2019-11-25 | 1398/09/02 | 1398/09/04
23S3-PC-220-ME-110 | 23S3-ECC-PLA-018 | 220-EC-PLA-ME-001 | 220 | PLA | ME | final boxup | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
FSF Plant Air Distribution Net Work Piping System (220-EC-PLA-PI-001) | 23S3-ECC-PLA-018 | 220-EC-PLA-PI-001 | 220 | PLA | PI |  | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
23S3-PC-220-PI-100 | 23S3-ECC-PLA-018 | 220-EC-PLA-PI-001 | 220 | PLA | PI | Punch Clearance | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
220-FSF INSTRUMENT AIR DISTRIBUTION NET WORK (23S3-ECC-INA-019) | 23S3-ECC-INA-019 |  | 220 | INA |  |  | 8 | 2019-11-19 | 2019-11-27 | 1398/08/28 | 1398/09/06
FSF Instrument Air Distribution Net Work Instrument System (220-EC-INA-IN-001) | 23S3-ECC-INA-019 | 220-EC-INA-IN-001 | 220 | INA | IN |  | 6 | 2019-11-19 | 2019-11-25 | 1398/08/28 | 1398/09/04
23S3-PC-220-IN-430 | 23S3-ECC-INA-019 | 220-EC-INA-IN-001 | 220 | INA | IN | device calibration | 1 | 2019-11-19 | 2019-11-20 | 1398/08/28 | 1398/08/29
23S3-PC-220-IN-440 | 23S3-ECC-INA-019 | 220-EC-INA-IN-001 | 220 | INA | IN | Instrument Cable Check and continuity megger test | 2 | 2019-11-20 | 2019-11-22 | 1398/08/29 | 1398/09/01
23S3-PC-220-IN-450 | 23S3-ECC-INA-019 | 220-EC-INA-IN-001 | 220 | INA | IN | device installation final check and punch clearance | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-220-IN-460 | 23S3-ECC-INA-019 | 220-EC-INA-IN-001 | 220 | INA | IN | IO and loop checking | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-220-IN-470 | 23S3-ECC-INA-019 | 220-EC-INA-IN-001 | 220 | INA | IN | function test | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
FSF Instrument Air Distribution Net Work Piping System (220-EC-INA-PI-001) | 23S3-ECC-INA-019 | 220-EC-INA-PI-001 | 220 | INA | PI |  | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
23S3-PC-220-PI-110 | 23S3-ECC-INA-019 | 220-EC-INA-PI-001 | 220 | INA | PI | Punch Clearance | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
220-FSF LIGHT FUEL OIL DISTRIBUTION NET WORK (23S3-ECC-LFO-021) | 23S3-ECC-LFO-021 |  | 220 | LFO |  |  | 6 | 2019-11-20 | 2019-11-26 | 1398/08/29 | 1398/09/05
FSFLight Fuel Oil Distribution Net Work Instrument System (220-EC-LFO-IN-001) | 23S3-ECC-LFO-021 | 220-EC-LFO-IN-001 | 220 | LFO | IN |  | 4 | 2019-11-20 | 2019-11-24 | 1398/08/29 | 1398/09/03
23S3-PC-220-IN-480 | 23S3-ECC-LFO-021 | 220-EC-LFO-IN-001 | 220 | LFO | IN | device calibration | 1 | 2019-11-20 | 2019-11-21 | 1398/08/29 | 1398/08/30
23S3-PC-220-IN-490 | 23S3-ECC-LFO-021 | 220-EC-LFO-IN-001 | 220 | LFO | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-21 | 2019-11-22 | 1398/08/30 | 1398/09/01
23S3-PC-220-IN-500 | 23S3-ECC-LFO-021 | 220-EC-LFO-IN-001 | 220 | LFO | IN | device installation final check and punch clearance | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-220-IN-510 | 23S3-ECC-LFO-021 | 220-EC-LFO-IN-001 | 220 | LFO | IN | IO and loop checking | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-220-IN-520 | 23S3-ECC-LFO-021 | 220-EC-LFO-IN-001 | 220 | LFO | IN | function test | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
FSFLight Fuel Oil Distribution Net Work Piping System (220-EC-LFO-PI-001) | 23S3-ECC-LFO-021 | 220-EC-LFO-PI-001 | 220 | LFO | PI |  | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
23S3-PC-220-PI-120 | 23S3-ECC-LFO-021 | 220-EC-LFO-PI-001 | 220 | LFO | PI | Punch Clearance | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
220-FSF FUEL GAS DISTRIBUTION NET WORK (23S3-ECC-FNG-020) | 23S3-ECC-FNG-020 |  | 220 | FNG |  |  | 6 | 2019-11-20 | 2019-11-26 | 1398/08/29 | 1398/09/05
FSF Fuel Gas Distribution Net Work Instrument System (220-EC-FNG-IN-001) | 23S3-ECC-FNG-020 | 220-EC-FNG-IN-001 | 220 | FNG | IN |  | 4 | 2019-11-20 | 2019-11-24 | 1398/08/29 | 1398/09/03
23S3-PC-220-IN-530 | 23S3-ECC-FNG-020 | 220-EC-FNG-IN-001 | 220 | FNG | IN | device calibration | 1 | 2019-11-20 | 2019-11-21 | 1398/08/29 | 1398/08/30
23S3-PC-220-IN-540 | 23S3-ECC-FNG-020 | 220-EC-FNG-IN-001 | 220 | FNG | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-21 | 2019-11-22 | 1398/08/30 | 1398/09/01
23S3-PC-220-IN-550 | 23S3-ECC-FNG-020 | 220-EC-FNG-IN-001 | 220 | FNG | IN | device installation final check and punch clearance | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-220-IN-560 | 23S3-ECC-FNG-020 | 220-EC-FNG-IN-001 | 220 | FNG | IN | IO and loop checking | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-220-IN-570 | 23S3-ECC-FNG-020 | 220-EC-FNG-IN-001 | 220 | FNG | IN | function test | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
FSF Fuel Gas Distribution Net Work Piping System (220-EC-FNG-PI-001) | 23S3-ECC-FNG-020 | 220-EC-FNG-PI-001 | 220 | FNG | PI |  | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
23S3-PC-220-PI-130 | 23S3-ECC-FNG-020 | 220-EC-FNG-PI-001 | 220 | FNG | PI | Punch Clearance | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
270-Water Handling Area (23S3-ECC-JCW-007) | 23S3-ECC-JCW-007 |  | 270 | JCW |  |  | 24 | 2019-11-09 | 2019-12-03 | 1398/08/18 | 1398/09/12
JACKET COOLING WATER INSTRUMENTATION (270-EC-JCW-IN-001) | 23S3-ECC-JCW-007 | 270-EC-JCW-IN-001 | 270 | JCW | IN |  | 10 | 2019-11-23 | 2019-12-03 | 1398/09/02 | 1398/09/12
23S3-PC-270-IN-100 | 23S3-ECC-JCW-007 | 270-EC-JCW-IN-001 | 270 | JCW | IN | Instrument Cable Check and continuity megger test | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
23S3-PC-270-IN-110 | 23S3-ECC-JCW-007 | 270-EC-JCW-IN-001 | 270 | JCW | IN | device calibration | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-270-IN-120 | 23S3-ECC-JCW-007 | 270-EC-JCW-IN-001 | 270 | JCW | IN | device installation final check and punch clearance | 5 | 2019-11-25 | 2019-11-30 | 1398/09/04 | 1398/09/09
23S3-PC-270-IN-130 | 23S3-ECC-JCW-007 | 270-EC-JCW-IN-001 | 270 | JCW | IN | IO and loop checking | 4 | 2019-11-28 | 2019-12-02 | 1398/09/07 | 1398/09/11
23S3-PC-270-IN-140 | 23S3-ECC-JCW-007 | 270-EC-JCW-IN-001 | 270 | JCW | IN | function test | 3 | 2019-11-30 | 2019-12-03 | 1398/09/09 | 1398/09/12
JACKET COOLING WATER MECHANICAL (270-EC-JCW-ME-001) | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-001 | 270 | JCW | ME |  | 8 | 2019-11-25 | 2019-12-03 | 1398/09/04 | 1398/09/12
23S3-PC-270-ME-100 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-001 | 270 | JCW | ME | check for pre box-up and punch clearance | 3 | 2019-11-25 | 2019-11-28 | 1398/09/04 | 1398/09/07
23S3-PC-270-ME-110 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-001 | 270 | JCW | ME | final boxup | 3 | 2019-11-27 | 2019-11-30 | 1398/09/06 | 1398/09/09
23S3-PC-270-ME-120 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-001 | 270 | JCW | ME | Motor and Pump installation final check and punch clearance | 4 | 2019-11-26 | 2019-11-30 | 1398/09/05 | 1398/09/09
23S3-PC-270-ME-130 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-001 | 270 | JCW | ME | Flange Parallel Check and adjastment | 5 | 2019-11-27 | 2019-12-02 | 1398/09/06 | 1398/09/11
23S3-PC-270-ME-140 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-001 | 270 | JCW | ME | Coupling pump and motor / load run test | 3 | 2019-11-30 | 2019-12-03 | 1398/09/09 | 1398/09/12
JACKET COOLING WATER MECHANICAL (270-EC-JCW-ME-002) | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-002 | 270 | JCW | ME |  | 13 | 2019-11-09 | 2019-11-22 | 1398/08/18 | 1398/09/01
23S3-PC-270-ME-150 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-002 | 270 | JCW | ME | Vendor at Site ( Disel Ban ) | 0 | 2019-11-09 |  | 1398/08/18
23S3-PC-270-ME-160 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-002 | 270 | JCW | ME | Disel installation final check and punch clearance | 5 | 2019-11-09 | 2019-11-14 | 1398/08/18 | 1398/08/23
23S3-PC-270-ME-170 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-002 | 270 | JCW | ME | check for pre box-up and punch clearance | 3 | 2019-11-13 | 2019-11-16 | 1398/08/22 | 1398/08/25
23S3-PC-270-ME-180 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-002 | 270 | JCW | ME | final boxup | 3 | 2019-11-13 | 2019-11-16 | 1398/08/22 | 1398/08/25
23S3-PC-270-ME-190 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-002 | 270 | JCW | ME | Pump installation final check and punch clearance | 3 | 2019-11-16 | 2019-11-19 | 1398/08/25 | 1398/08/28
23S3-PC-270-ME-200 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-002 | 270 | JCW | ME | Flange Parallel Check and adjastment | 5 | 2019-11-16 | 2019-11-21 | 1398/08/25 | 1398/08/30
23S3-PC-270-ME-210 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-002 | 270 | JCW | ME | Coupling pump and motor / load run test | 3 | 2019-11-19 | 2019-11-22 | 1398/08/28 | 1398/09/01
JACKET COOLING WATER MECHANICAL (270-EC-JCW-ME-003) | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-003 | 270 | JCW | ME |  | 8 | 2019-11-13 | 2019-11-21 | 1398/08/22 | 1398/08/30
23S3-PC-270-ME-260 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-003 | 270 | JCW | ME | check for pre box-up and punch clearance | 5 | 2019-11-13 | 2019-11-18 | 1398/08/22 | 1398/08/27
23S3-PC-270-ME-270 | 23S3-ECC-JCW-007 | 270-EC-JCW-ME-003 | 270 | JCW | ME | final boxup | 3 | 2019-11-18 | 2019-11-21 | 1398/08/27 | 1398/08/30
JACKET COOLING WATER PIPING (270-EC-JCW-PI-001) | 23S3-ECC-JCW-007 | 270-EC-JCW-PI-001 | 270 | JCW | PI |  | 7 | 2019-11-26 | 2019-12-03 | 1398/09/05 | 1398/09/12
23S3-PC-270-PI-100 | 23S3-ECC-JCW-007 | 270-EC-JCW-PI-001 | 270 | JCW | PI | Punch Clearance | 7 | 2019-11-26 | 2019-12-03 | 1398/09/05 | 1398/09/12
JACKET COOLING WATER ELECTRICAL (270-EC-JCW-EL-001) | 23S3-ECC-JCW-007 | 270-EC-JCW-EL-001 | 270 | JCW | EL |  | 4 | 2019-11-25 | 2019-11-29 | 1398/09/04 | 1398/09/08
23S3-PC-270-EL-580 | 23S3-ECC-JCW-007 | 270-EC-JCW-EL-001 | 270 | JCW | EL | gland and connection final inspection | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-270-EL-590 | 23S3-ECC-JCW-007 | 270-EC-JCW-EL-001 | 270 | JCW | EL | LCS final function test | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-270-EL-600 | 23S3-ECC-JCW-007 | 270-EC-JCW-EL-001 | 270 | JCW | EL | feeder final checking | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-270-EL-610 | 23S3-ECC-JCW-007 | 270-EC-JCW-EL-001 | 270 | JCW | EL | motor free run & Load test | 3 | 2019-11-26 | 2019-11-29 | 1398/09/05 | 1398/09/08
270-Water Handling Area (23S3-ECC-SCW-008) | 23S3-ECC-SCW-008 |  | 270 | SCW |  |  | 26 | 2019-11-07 | 2019-12-03 | 1398/08/16 | 1398/09/12
SECONDARY COOLING WATER ELECTRICAL (270-EC-SCW-EL-001) | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-001 | 270 | SCW | EL |  | 6 | 2019-11-25 | 2019-12-01 | 1398/09/04 | 1398/09/10
23S3-PC-270-EL-620 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-001 | 270 | SCW | EL | gland and connection final inspection | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-270-EL-630 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-001 | 270 | SCW | EL | LCS final function test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-270-EL-640 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-001 | 270 | SCW | EL | feeder final checking | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-270-EL-650 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-001 | 270 | SCW | EL | motor free run & load test | 3 | 2019-11-28 | 2019-12-01 | 1398/09/07 | 1398/09/10
SECONDARY COOLING WATER ELECTRICAL (270-EC-SCW-EL-002) | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-002 | 270 | SCW | EL |  | 6 | 2019-11-25 | 2019-12-01 | 1398/09/04 | 1398/09/10
23S3-PC-270-EL-660 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-002 | 270 | SCW | EL | gland and connection final inspection | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-270-EL-670 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-002 | 270 | SCW | EL | LCS final function test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-270-EL-680 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-002 | 270 | SCW | EL | feeder final checking | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-270-EL-690 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-002 | 270 | SCW | EL | motor free run & load test | 3 | 2019-11-28 | 2019-12-01 | 1398/09/07 | 1398/09/10
SECONDARY COOLING WATER ELECTRICAL (270-EC-SCW-EL-003) | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-003 | 270 | SCW | EL |  | 6 | 2019-11-25 | 2019-12-01 | 1398/09/04 | 1398/09/10
23S3-PC-270-EL-700 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-003 | 270 | SCW | EL | gland and connection final inspection | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-270-EL-710 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-003 | 270 | SCW | EL | LCS final function test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-270-EL-720 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-003 | 270 | SCW | EL | feeder final checking | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-270-EL-730 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-003 | 270 | SCW | EL | motor free run & load test | 3 | 2019-11-28 | 2019-12-01 | 1398/09/07 | 1398/09/10
SECONDARY COOLING WATER ELECTRICAL (270-EC-SCW-EL-004) | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-004 | 270 | SCW | EL |  | 6 | 2019-11-25 | 2019-12-01 | 1398/09/04 | 1398/09/10
23S3-PC-270-EL-740 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-004 | 270 | SCW | EL | gland and connection final inspection | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-270-EL-750 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-004 | 270 | SCW | EL | LCS final function test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-270-EL-760 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-004 | 270 | SCW | EL | feeder final checking | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-270-EL-770 | 23S3-ECC-SCW-008 | 270-EC-SCW-EL-004 | 270 | SCW | EL | motor free run & load test | 3 | 2019-11-28 | 2019-12-01 | 1398/09/07 | 1398/09/10
SECONDARY COOLING WATER INSTRUMENTATION (270-EC-SCW-IN-001) | 23S3-ECC-SCW-008 | 270-EC-SCW-IN-001 | 270 | SCW | IN |  | 10 | 2019-11-23 | 2019-12-03 | 1398/09/02 | 1398/09/12
23S3-PC-270-IN-150 | 23S3-ECC-SCW-008 | 270-EC-SCW-IN-001 | 270 | SCW | IN | Instrument Cable Check and continuity megger test | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
23S3-PC-270-IN-160 | 23S3-ECC-SCW-008 | 270-EC-SCW-IN-001 | 270 | SCW | IN | device calibration | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-270-IN-170 | 23S3-ECC-SCW-008 | 270-EC-SCW-IN-001 | 270 | SCW | IN | device installation final check and punch clearance | 5 | 2019-11-25 | 2019-11-30 | 1398/09/04 | 1398/09/09
23S3-PC-270-IN-180 | 23S3-ECC-SCW-008 | 270-EC-SCW-IN-001 | 270 | SCW | IN | IO and loop checking | 4 | 2019-11-28 | 2019-12-02 | 1398/09/07 | 1398/09/11
23S3-PC-270-IN-190 | 23S3-ECC-SCW-008 | 270-EC-SCW-IN-001 | 270 | SCW | IN | function test | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
SECONDARY COOLING WATER MACHINERY (270-EC-SCW-ME-001) | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-001 | 270 | SCW | ME |  | 13 | 2019-11-07 | 2019-11-20 | 1398/08/16 | 1398/08/29
23S3-PC-270-ME-280 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-001 | 270 | SCW | ME | check for pre box-up and punch clearance | 5 | 2019-11-07 | 2019-11-12 | 1398/08/16 | 1398/08/21
23S3-PC-270-ME-290 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-001 | 270 | SCW | ME | final boxup | 1 | 2019-11-12 | 2019-11-13 | 1398/08/21 | 1398/08/22
23S3-PC-270-ME-300 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-001 | 270 | SCW | ME | Motor and Pump installation final check and punch clearance | 4 | 2019-11-09 | 2019-11-13 | 1398/08/18 | 1398/08/22
23S3-PC-270-ME-310 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-001 | 270 | SCW | ME | Flange Parallel Check and adjastment | 5 | 2019-11-11 | 2019-11-16 | 1398/08/20 | 1398/08/25
23S3-PC-270-ME-330 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-001 | 270 | SCW | ME | Coupling pump and motor / load run test | 6 | 2019-11-14 | 2019-11-20 | 1398/08/23 | 1398/08/29
SECONDARY COOLING WATER MACHINERY (270-EC-SCW-ME-002) | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-002 | 270 | SCW | ME |  | 4 | 2019-11-13 | 2019-11-17 | 1398/08/22 | 1398/08/26
23S3-PC-270-ME-360 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-002 | 270 | SCW | ME | Motor and Pump installation final check and punch clearance | 1 | 2019-11-13 | 2019-11-14 | 1398/08/22 | 1398/08/23
23S3-PC-270-ME-370 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-002 | 270 | SCW | ME | Flange Parallel Check and adjastment | 1 | 2019-11-14 | 2019-11-15 | 1398/08/23 | 1398/08/24
23S3-PC-270-ME-390 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-002 | 270 | SCW | ME | Coupling pump and motor / load run test | 2 | 2019-11-15 | 2019-11-17 | 1398/08/24 | 1398/08/26
SECONDARY COOLING WATER MECHANICAL (270-EC-SCW-ME-003) | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-003 | 270 | SCW | ME |  | 6 | 2019-11-13 | 2019-11-19 | 1398/08/22 | 1398/08/28
23S3-PC-270-ME-400 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-003 | 270 | SCW | ME | check for pre box-up and punch clearance | 3 | 2019-11-13 | 2019-11-16 | 1398/08/22 | 1398/08/25
23S3-PC-270-ME-410 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-003 | 270 | SCW | ME | final boxup | 1 | 2019-11-16 | 2019-11-17 | 1398/08/25 | 1398/08/26
23S3-PC-270-ME-420 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-003 | 270 | SCW | ME | Motor and Fan installation final check and punch clearance | 2 | 2019-11-13 | 2019-11-15 | 1398/08/22 | 1398/08/24
23S3-PC-270-ME-440 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-003 | 270 | SCW | ME | Fan Adjustment | 3 | 2019-11-15 | 2019-11-18 | 1398/08/24 | 1398/08/27
23S3-PC-270-ME-450 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-003 | 270 | SCW | ME | Coupling Fan and motor / load run test | 1 | 2019-11-18 | 2019-11-19 | 1398/08/27 | 1398/08/28
SECONDARY COOLING WATER MECHANICAL (270-EC-SCW-ME-004) | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-004 | 270 | SCW | ME |  | 7 | 2019-11-13 | 2019-11-20 | 1398/08/22 | 1398/08/29
23S3-PC-270-ME-480 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-004 | 270 | SCW | ME | Motor and Pump installation final check and punch clearance | 2 | 2019-11-13 | 2019-11-15 | 1398/08/22 | 1398/08/24
23S3-PC-270-ME-490 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-004 | 270 | SCW | ME | Flange Parallel Check and adjastment | 3 | 2019-11-15 | 2019-11-18 | 1398/08/24 | 1398/08/27
23S3-PC-270-ME-510 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-004 | 270 | SCW | ME | Coupling pump and motor / load run test | 2 | 2019-11-18 | 2019-11-20 | 1398/08/27 | 1398/08/29
SECONDARY COOLING WATER MECHANICAL (270-EC-SCW-ME-005) | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-005 | 270 | SCW | ME |  | 8 | 2019-11-13 | 2019-11-21 | 1398/08/22 | 1398/08/30
23S3-PC-270-ME-520 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-005 | 270 | SCW | ME | check for pre box-up and punch clearance | 5 | 2019-11-13 | 2019-11-18 | 1398/08/22 | 1398/08/27
23S3-PC-270-ME-530 | 23S3-ECC-SCW-008 | 270-EC-SCW-ME-005 | 270 | SCW | ME | final boxup | 3 | 2019-11-18 | 2019-11-21 | 1398/08/27 | 1398/08/30
SECONDARY COOLING WATER PIPING (270-EC-SCW-PI-001) | 23S3-ECC-SCW-008 | 270-EC-SCW-PI-001 | 270 | SCW | PI |  | 3 | 2019-11-26 | 2019-11-29 | 1398/09/05 | 1398/09/08
23S3-PC-270-PI-110 | 23S3-ECC-SCW-008 | 270-EC-SCW-PI-001 | 270 | SCW | PI | Punch Clearance | 3 | 2019-11-26 | 2019-11-29 | 1398/09/05 | 1398/09/08
220-FSF Jacket Cooling water (23S3-ECC-JCW-026) | 23S3-ECC-JCW-026 |  | 220 | JCW |  |  | 18 | 2019-11-16 | 2019-12-04 | 1398/08/25 | 1398/09/13
FSF Cooling Water Instrument Devices (220-EC-JCW-IN-001) | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-001 | 220 | JCW | IN |  | 13 | 2019-11-20 | 2019-12-03 | 1398/08/29 | 1398/09/12
23S3-PC-220-IN-580 | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-001 | 220 | JCW | IN | device calibration | 2 | 2019-11-20 | 2019-11-22 | 1398/08/29 | 1398/09/01
23S3-PC-220-IN-600 | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-001 | 220 | JCW | IN | device installation final check and punch clearance | 5 | 2019-11-22 | 2019-11-27 | 1398/09/01 | 1398/09/06
23S3-PC-220-IN-610 | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-001 | 220 | JCW | IN | IO and loop checking | 7 | 2019-11-23 | 2019-11-30 | 1398/09/02 | 1398/09/09
23S3-PC-220-IN-620 | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-001 | 220 | JCW | IN | function test | 5 | 2019-11-28 | 2019-12-03 | 1398/09/07 | 1398/09/12
FSF Cooling Water Devices For LH/US & Inline (220-EC-JCW-IN-002) | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-002 | 220 | JCW | IN |  | 14 | 2019-11-20 | 2019-12-04 | 1398/08/29 | 1398/09/13
23S3-PC-220-IN-630 | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-002 | 220 | JCW | IN | device calibration | 2 | 2019-11-20 | 2019-11-22 | 1398/08/29 | 1398/09/01
23S3-PC-220-IN-650 | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-002 | 220 | JCW | IN | device installation final check and punch clearance | 5 | 2019-11-22 | 2019-11-27 | 1398/09/01 | 1398/09/06
23S3-PC-220-IN-660 | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-002 | 220 | JCW | IN | IO and loop checking | 8 | 2019-11-23 | 2019-12-01 | 1398/09/02 | 1398/09/10
23S3-PC-220-IN-670 | 23S3-ECC-JCW-026 | 220-EC-JCW-IN-002 | 220 | JCW | IN | function test | 5 | 2019-11-29 | 2019-12-04 | 1398/09/08 | 1398/09/13
FSF Jacket Cooling Water Header (220-EC-JCW-ME-001) | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-001 | 220 | JCW | ME |  | 8 | 2019-11-16 | 2019-11-24 | 1398/08/25 | 1398/09/03
23S3-PC-220-ME-130 | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-001 | 220 | JCW | ME | Cooling header installation final check and punch clearance | 5 | 2019-11-16 | 2019-11-21 | 1398/08/25 | 1398/08/30
23S3-PC-220-ME-140 | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-001 | 220 | JCW | ME | check for pre box-up and punch clearance | 2 | 2019-11-21 | 2019-11-23 | 1398/08/30 | 1398/09/02
23S3-PC-220-ME-150 | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-001 | 220 | JCW | ME | final boxup | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
FSF Jacket Cooling Water Header (220-EC-JCW-ME-002) | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-002 | 220 | JCW | ME |  | 8 | 2019-11-16 | 2019-11-24 | 1398/08/25 | 1398/09/03
23S3-PC-220-ME-170 | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-002 | 220 | JCW | ME | Cooling header installation final check and punch clearance | 5 | 2019-11-16 | 2019-11-21 | 1398/08/25 | 1398/08/30
23S3-PC-220-ME-180 | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-002 | 220 | JCW | ME | check for pre box-up and punch clearance | 2 | 2019-11-21 | 2019-11-23 | 1398/08/30 | 1398/09/02
23S3-PC-220-ME-190 | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-002 | 220 | JCW | ME | final boxup | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
FSF Jacket Cooling Water Header (220-EC-JCW-ME-003) | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-003 | 220 | JCW | ME |  | 6 | 2019-11-16 | 2019-11-22 | 1398/08/25 | 1398/09/01
23S3-PC-220-ME-210 | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-003 | 220 | JCW | ME | Cooling header installation final check and punch clearance | 3 | 2019-11-16 | 2019-11-19 | 1398/08/25 | 1398/08/28
23S3-PC-220-ME-220 | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-003 | 220 | JCW | ME | check for pre box-up and punch clearance | 2 | 2019-11-19 | 2019-11-21 | 1398/08/28 | 1398/08/30
23S3-PC-220-ME-230 | 23S3-ECC-JCW-026 | 220-EC-JCW-ME-003 | 220 | JCW | ME | final boxup | 1 | 2019-11-21 | 2019-11-22 | 1398/08/30 | 1398/09/01
FSF Cooling Water Piping System (220-EC-JCW-PI-001) | 23S3-ECC-JCW-026 | 220-EC-JCW-PI-001 | 220 | JCW | PI |  | 6 | 2019-11-25 | 2019-12-01 | 1398/09/04 | 1398/09/10
23S3-PC-220-PI-140 | 23S3-ECC-JCW-026 | 220-EC-JCW-PI-001 | 220 | JCW | PI | Punch Clearance | 6 | 2019-11-25 | 2019-12-01 | 1398/09/04 | 1398/09/10
FSF Cooling Water Piping System (220-EC-JCW-PI-002) | 23S3-ECC-JCW-026 | 220-EC-JCW-PI-002 | 220 | JCW | PI |  | 6 | 2019-11-25 | 2019-12-01 | 1398/09/04 | 1398/09/10
23S3-PC-220-PI-150 | 23S3-ECC-JCW-026 | 220-EC-JCW-PI-002 | 220 | JCW | PI | Punch Clearance | 6 | 2019-11-25 | 2019-12-01 | 1398/09/04 | 1398/09/10
220-CONCENTRATE BURNER COOLING WATER SYSTEM (23S3-ECC-CBC-027) | 23S3-ECC-CBC-027 |  | 220 | CBC |  |  | 9 | 2019-11-17 | 2019-11-26 | 1398/08/26 | 1398/09/05
Concentrate Burner Cooling water Electrical System (220-EC-CBC-EL-001) | 23S3-ECC-CBC-027 | 220-EC-CBC-EL-001 | 220 | CBC | EL |  | 1 | 2019-11-17 | 2019-11-18 | 1398/08/26 | 1398/08/27
23S3-PC-220-EL-340 | 23S3-ECC-CBC-027 | 220-EC-CBC-EL-001 | 220 | CBC | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-17 | 2019-11-18 | 1398/08/26 | 1398/08/27
23S3-PC-220-EL-350 | 23S3-ECC-CBC-027 | 220-EC-CBC-EL-001 | 220 | CBC | EL | motor continuity megger test | 1 | 2019-11-17 | 2019-11-18 | 1398/08/26 | 1398/08/27
23S3-PC-220-EL-360 | 23S3-ECC-CBC-027 | 220-EC-CBC-EL-001 | 220 | CBC | EL | gland and connection final inspection | 1 | 2019-11-17 | 2019-11-18 | 1398/08/26 | 1398/08/27
23S3-PC-220-EL-370 | 23S3-ECC-CBC-027 | 220-EC-CBC-EL-001 | 220 | CBC | EL | LCS final function test | 1 | 2019-11-17 | 2019-11-18 | 1398/08/26 | 1398/08/27
23S3-PC-220-EL-470 | 23S3-ECC-CBC-027 | 220-EC-CBC-EL-001 | 220 | CBC | EL | feeder final checking | 1 | 2019-11-17 | 2019-11-18 | 1398/08/26 | 1398/08/27
23S3-PC-220-EL-740 | 23S3-ECC-CBC-027 | 220-EC-CBC-EL-001 | 220 | CBC | EL | motor free run & load test | 1 | 2019-11-17 | 2019-11-18 | 1398/08/26 | 1398/08/27
Concentrate Burner Cooling water Instrument System (220-EC-CBC-IN-001) | 23S3-ECC-CBC-027 | 220-EC-CBC-IN-001 | 220 | CBC | IN |  | 8 | 2019-11-18 | 2019-11-26 | 1398/08/27 | 1398/09/05
23S3-PC-220-IN-680 | 23S3-ECC-CBC-027 | 220-EC-CBC-IN-001 | 220 | CBC | IN | device calibration | 2 | 2019-11-18 | 2019-11-20 | 1398/08/27 | 1398/08/29
23S3-PC-220-IN-690 | 23S3-ECC-CBC-027 | 220-EC-CBC-IN-001 | 220 | CBC | IN | Instrument Cable Check and continuity megger test | 2 | 2019-11-19 | 2019-11-21 | 1398/08/28 | 1398/08/30
23S3-PC-220-IN-700 | 23S3-ECC-CBC-027 | 220-EC-CBC-IN-001 | 220 | CBC | IN | device installation final check and punch clearance | 1 | 2019-11-21 | 2019-11-22 | 1398/08/30 | 1398/09/01
23S3-PC-220-IN-710 | 23S3-ECC-CBC-027 | 220-EC-CBC-IN-001 | 220 | CBC | IN | IO and loop checking | 2 | 2019-11-22 | 2019-11-24 | 1398/09/01 | 1398/09/03
23S3-PC-220-IN-720 | 23S3-ECC-CBC-027 | 220-EC-CBC-IN-001 | 220 | CBC | IN | function test | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
Concentrate Burner Cooling water Mechanical System (220-EC-CBC-ME-001) | 23S3-ECC-CBC-027 | 220-EC-CBC-ME-001 | 220 | CBC | ME |  | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
23S3-PC-220-ME-240 | 23S3-ECC-CBC-027 | 220-EC-CBC-ME-001 | 220 | CBC | ME | Motor and Pump installation final check and punch clearance | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-220-ME-250 | 23S3-ECC-CBC-027 | 220-EC-CBC-ME-001 | 220 | CBC | ME | Flange Parallel Check and adjastment | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
23S3-PC-220-ME-270 | 23S3-ECC-CBC-027 | 220-EC-CBC-ME-001 | 220 | CBC | ME | Coupling pump and motor / load run test | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
Concentrate Burner Cooling water Piping System (220-EC-CBC-PI-001) | 23S3-ECC-CBC-027 | 220-EC-CBC-PI-001 | 220 | CBC | PI |  | 2 | 2019-11-24 | 2019-11-26 | 1398/09/03 | 1398/09/05
23S3-PC-220-PI-160 | 23S3-ECC-CBC-027 | 220-EC-CBC-PI-001 | 220 | CBC | PI | Punch Clearance | 2 | 2019-11-24 | 2019-11-26 | 1398/09/03 | 1398/09/05
230-COOLING WATER TO LAUNDER COOLING ELEMENTS (23S3-ECC-WCS-035) | 23S3-ECC-WCS-035 |  | 230 | WCS |  |  | 5 | 2019-11-22 | 2019-11-27 | 1398/09/01 | 1398/09/06
COOLING WATER TO LAUNDER COOLING ELEMENTS INSTRUMENT SYSTEM (230-EC-WCS-IN-001) | 23S3-ECC-WCS-035 | 230-EC-WCS-IN-001 | 230 | WCS | IN |  | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-230-IN-100 | 23S3-ECC-WCS-035 | 230-EC-WCS-IN-001 | 230 | WCS | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-230-IN-110 | 23S3-ECC-WCS-035 | 230-EC-WCS-IN-001 | 230 | WCS | IN | device calibration | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-230-IN-120 | 23S3-ECC-WCS-035 | 230-EC-WCS-IN-001 | 230 | WCS | IN | device installation final check and punch clearance | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-230-IN-130 | 23S3-ECC-WCS-035 | 230-EC-WCS-IN-001 | 230 | WCS | IN | IO and loop checking | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-230-IN-140 | 23S3-ECC-WCS-035 | 230-EC-WCS-IN-001 | 230 | WCS | IN | function test | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
COOLING WATER TO LAUNDER COOLING ELEMENTS PIPING SYSTEM (230-EC-WCS-PI-001) | 23S3-ECC-WCS-035 | 230-EC-WCS-PI-001 | 230 | WCS | PI |  | 2 | 2019-11-25 | 2019-11-27 | 1398/09/04 | 1398/09/06
23S3-PC-230-PI-150 | 23S3-ECC-WCS-035 | 230-EC-WCS-PI-001 | 230 | WCS | PI | Punch Clearance | 2 | 2019-11-25 | 2019-11-27 | 1398/09/04 | 1398/09/06
220 -FSF MECHANICAL & MEASURMENT SYSTEM (23S3-ECC-FSF-025) | 23S3-ECC-FSF-025 |  | 220 | FSF |  |  | 10 | 2019-11-21 | 2019-12-01 | 1398/08/30 | 1398/09/10
FSF Instrument System (220-EC-FSF-IN-001) | 23S3-ECC-FSF-025 | 220-EC-FSF-IN-001 | 220 | FSF | IN |  | 6 | 2019-11-25 | 2019-12-01 | 1398/09/04 | 1398/09/10
23S3-PC-220-IN-730 | 23S3-ECC-FSF-025 | 220-EC-FSF-IN-001 | 220 | FSF | IN | Instrument Cable Check and continuity megger test | 3 | 2019-11-25 | 2019-11-28 | 1398/09/04 | 1398/09/07
23S3-PC-220-IN-740 | 23S3-ECC-FSF-025 | 220-EC-FSF-IN-001 | 220 | FSF | IN | device calibration | 2 | 2019-11-26 | 2019-11-28 | 1398/09/05 | 1398/09/07
23S3-PC-220-IN-750 | 23S3-ECC-FSF-025 | 220-EC-FSF-IN-001 | 220 | FSF | IN | device installation final check and punch clearance | 2 | 2019-11-27 | 2019-11-29 | 1398/09/06 | 1398/09/08
23S3-PC-220-IN-760 | 23S3-ECC-FSF-025 | 220-EC-FSF-IN-001 | 220 | FSF | IN | IO and loop checking | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
23S3-PC-220-IN-770 | 23S3-ECC-FSF-025 | 220-EC-FSF-IN-001 | 220 | FSF | IN | function test | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
FSF Mechanical System (220-EC-FSF-ME-001) | 23S3-ECC-FSF-025 | 220-EC-FSF-ME-001 | 220 | FSF | ME |  | 6 | 2019-11-21 | 2019-11-27 | 1398/08/30 | 1398/09/06
23S3-PC-220-ME-275 | 23S3-ECC-FSF-025 | 220-EC-FSF-ME-001 | 220 | FSF | ME | Vendor at Site ( Autotec Mechanic Supervisor ) | 0 | 2019-11-21 |  | 1398/08/30
23S3-PC-220-ME-280 | 23S3-ECC-FSF-025 | 220-EC-FSF-ME-001 | 220 | FSF | ME | check for pre box-up and punch clearance | 5 | 2019-11-21 | 2019-11-26 | 1398/08/30 | 1398/09/05
23S3-PC-220-ME-290 | 23S3-ECC-FSF-025 | 220-EC-FSF-ME-001 | 220 | FSF | ME | final boxup | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
220-FSF BURNER SYSTEM (23S3-ECC-BUN-024) | 23S3-ECC-BUN-024 |  | 220 | BUN |  |  | 13 | 2019-11-22 | 2019-12-05 | 1398/09/01 | 1398/09/14
Settler Roof Oxygen Burners (220-EC-BUN-ME-001) | 23S3-ECC-BUN-024 | 220-EC-BUN-ME-001 | 220 | BUN | ME |  | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
23S3-PC-220-ME-300 | 23S3-ECC-BUN-024 | 220-EC-BUN-ME-001 | 220 | BUN | ME | Vendor At Site ( Outotec Burner Supervisor ) | 0 | 2019-11-23 |  | 1398/09/02
23S3-PC-220-ME-305 | 23S3-ECC-BUN-024 | 220-EC-BUN-ME-001 | 220 | BUN | ME | Burner And Accessory installation final check and punch clearance | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-220-ME-310 | 23S3-ECC-BUN-024 | 220-EC-BUN-ME-001 | 220 | BUN | ME | Burner adjustment | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
23S3-PC-220-ME-320 | 23S3-ECC-BUN-024 | 220-EC-BUN-ME-001 | 220 | BUN | ME | All hose connection installation final check and punch clearance | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
Settler Roof Oxygen Burners (220-EC-BUN-IN-001) | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-001 | 220 | BUN | IN |  | 10 | 2019-11-23 | 2019-12-03 | 1398/09/02 | 1398/09/12
23S3-PC-220-IN-780 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-001 | 220 | BUN | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-220-IN-790 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-001 | 220 | BUN | IN | device calibration | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
23S3-PC-220-IN-800 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-001 | 220 | BUN | IN | device installation final check and punch clearance | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
23S3-PC-220-IN-810 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-001 | 220 | BUN | IN | IO and loop checking | 6 | 2019-11-26 | 2019-12-02 | 1398/09/05 | 1398/09/11
23S3-PC-220-IN-820 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-001 | 220 | BUN | IN | function test | 6 | 2019-11-27 | 2019-12-03 | 1398/09/06 | 1398/09/12
Settler Wall Fuel Burners (220-EC-BUN-ME-002) | 23S3-ECC-BUN-024 | 220-EC-BUN-ME-002 | 220 | BUN | ME |  | 5 | 2019-11-22 | 2019-11-27 | 1398/09/01 | 1398/09/06
23S3-PC-220-ME-330 | 23S3-ECC-BUN-024 | 220-EC-BUN-ME-002 | 220 | BUN | ME | Burner And Accessory installation final check and punch clearance | 3 | 2019-11-22 | 2019-11-25 | 1398/09/01 | 1398/09/04
23S3-PC-220-ME-340 | 23S3-ECC-BUN-024 | 220-EC-BUN-ME-002 | 220 | BUN | ME | Burner adjustment | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-220-ME-350 | 23S3-ECC-BUN-024 | 220-EC-BUN-ME-002 | 220 | BUN | ME | All hose connection installation final check and punch clearance | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
Settler Wall Fuel Burners (220-EC-BUN-IN-002) | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-002 | 220 | BUN | IN |  | 13 | 2019-11-22 | 2019-12-05 | 1398/09/01 | 1398/09/14
23S3-PC-220-IN-830 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-002 | 220 | BUN | IN | Instrument Cable Check and continuity megger test | 3 | 2019-11-22 | 2019-11-25 | 1398/09/01 | 1398/09/04
23S3-PC-220-IN-840 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-002 | 220 | BUN | IN | device calibration | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-220-IN-850 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-002 | 220 | BUN | IN | device installation final check and punch clearance | 3 | 2019-11-26 | 2019-11-29 | 1398/09/05 | 1398/09/08
23S3-PC-220-IN-860 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-002 | 220 | BUN | IN | IO and loop checking | 6 | 2019-11-28 | 2019-12-04 | 1398/09/07 | 1398/09/13
23S3-PC-220-IN-870 | 23S3-ECC-BUN-024 | 220-EC-BUN-IN-002 | 220 | BUN | IN | function test | 6 | 2019-11-29 | 2019-12-05 | 1398/09/08 | 1398/09/14
220-FSF COMBUSTION AIR FAN SYSTEM (23S3-ECC-CAF-017) | 23S3-ECC-CAF-017 |  | 220 | CAF |  |  | 7 | 2019-11-07 | 2019-11-13 | 1398/08/16 | 1398/08/22
Combusition Air Fan Electrical System (220-EC-CAF-EL-001) | 23S3-ECC-CAF-017 | 220-EC-CAF-EL-001 | 220 | CAF | EL |  | 5 | 2019-11-08 | 2019-11-13 | 1398/08/17 | 1398/08/22
23S3-PC-220-EL-380 | 23S3-ECC-CAF-017 | 220-EC-CAF-EL-001 | 220 | CAF | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-220-EL-390 | 23S3-ECC-CAF-017 | 220-EC-CAF-EL-001 | 220 | CAF | EL | motor continuity megger test | 1 | 2019-11-08 | 2019-11-09 | 1398/08/17 | 1398/08/18
23S3-PC-220-EL-400 | 23S3-ECC-CAF-017 | 220-EC-CAF-EL-001 | 220 | CAF | EL | gland and connection final inspection | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-220-EL-410 | 23S3-ECC-CAF-017 | 220-EC-CAF-EL-001 | 220 | CAF | EL | LCS final function test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
23S3-PC-220-EL-420 | 23S3-ECC-CAF-017 | 220-EC-CAF-EL-001 | 220 | CAF | EL | feeder final checking | 1 | 2019-11-11 | 2019-11-12 | 1398/08/20 | 1398/08/21
23S3-PC-220-EL-430 | 23S3-ECC-CAF-017 | 220-EC-CAF-EL-001 | 220 | CAF | EL | motor free run test | 1 | 2019-11-12 | 2019-11-13 | 1398/08/21 | 1398/08/22
Combusition Air Fan Instrument System (220-EC-CAF-IN-001) | 23S3-ECC-CAF-017 | 220-EC-CAF-IN-001 | 220 | CAF | IN |  | 5 | 2019-11-09 | 2019-11-13 | 1398/08/18 | 1398/08/22
23S3-PC-220-IN-880 | 23S3-ECC-CAF-017 | 220-EC-CAF-IN-001 | 220 | CAF | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-220-IN-890 | 23S3-ECC-CAF-017 | 220-EC-CAF-IN-001 | 220 | CAF | IN | device calibration | 1 | 2019-11-09 | 2019-11-10 | 1398/08/18 | 1398/08/19
23S3-PC-220-IN-900 | 23S3-ECC-CAF-017 | 220-EC-CAF-IN-001 | 220 | CAF | IN | device installation final check and punch clearance | 2 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
23S3-PC-220-IN-910 | 23S3-ECC-CAF-017 | 220-EC-CAF-IN-001 | 220 | CAF | IN | IO and loop checking | 1 | 2019-11-11 | 2019-11-12 | 1398/08/20 | 1398/08/21
23S3-PC-220-IN-920 | 23S3-ECC-CAF-017 | 220-EC-CAF-IN-001 | 220 | CAF | IN | function test | 1 | 2019-11-12 | 2019-11-13 | 1398/08/21 | 1398/08/22
Combusition Air Fan Mechanical System (220-EC-CAF-ME-001) | 23S3-ECC-CAF-017 | 220-EC-CAF-ME-001 | 220 | CAF | ME |  | 4 | 2019-11-07 | 2019-11-11 | 1398/08/16 | 1398/08/20
23S3-PC-220-ME-360 | 23S3-ECC-CAF-017 | 220-EC-CAF-ME-001 | 220 | CAF | ME | Motor and Fan installation final check and punch clearance | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-220-ME-370 | 23S3-ECC-CAF-017 | 220-EC-CAF-ME-001 | 220 | CAF | ME | Flange Parallel Check and adjastment | 1 | 2019-11-07 | 2019-11-08 | 1398/08/16 | 1398/08/17
23S3-PC-220-ME-380 | 23S3-ECC-CAF-017 | 220-EC-CAF-ME-001 | 220 | CAF | ME | duct work final check and punch clearance | 3 | 2019-11-08 | 2019-11-11 | 1398/08/17 | 1398/08/20
23S3-PC-220-ME-390 | 23S3-ECC-CAF-017 | 220-EC-CAF-ME-001 | 220 | CAF | ME | Coupling fan / load run test | 1 | 2019-11-10 | 2019-11-11 | 1398/08/19 | 1398/08/20
220-FSF BY-PASS DAMPER (23S3-ECC-BDP-028) | 23S3-ECC-BDP-028 |  | 220 | BDP |  |  | 2 | 2019-11-09 | 2019-11-11 | 1398/08/24 | 1398/08/26
By-Pass Damper Mechanical System (220-EC-BPD-ME-001) | 23S3-ECC-BDP-028 | 220-EC-BPD-ME-001 | 220 | BDP | ME |  | 2 | 2019-11-09 | 2019-11-11 | 1398/08/24 | 1398/08/26
23S3-PC-220-ME-410 | 23S3-ECC-BDP-028 | 220-EC-BPD-ME-001 | 220 | BDP | ME | final check and punch clearance | 1 | 2019-11-15 | 2019-11-16 | 1398/08/24 | 1398/08/25
23S3-PC-220-ME-420 | 23S3-ECC-BDP-028 | 220-EC-BPD-ME-001 | 220 | BDP | ME | final boxup | 1 | 2019-11-16 | 2019-11-17 | 1398/08/25 | 1398/08/26
225-WHB (MILESTONE) | WHB MILESTONE |  | 225 | MILESTONE |  |  | 0 | 2019-12-20 | 2019-12-20 | 1398/09/29 | 1398/09/29
23S3-PC-225-MLS-100 | WHB MILESTONE | WHB MILESTONE | 225 | MILESTONE |  | Vendor At Site ( Outotec Process Supervisor ) | 0 | 2019-12-20 |  | 1398/09/29
23S3-PC-225-MLS-110 | WHB MILESTONE | WHB MILESTONE | 225 | MILESTONE | EL | Electrical | 0 |  | 2019-12-20 |  | 1398/09/29
23S3-PC-225-MLS-120 | WHB MILESTONE | WHB MILESTONE | 225 | MILESTONE | IN | Instrument | 0 |  | 2019-12-20 |  | 1398/09/29
23S3-PC-225-MLS-130 | WHB MILESTONE | WHB MILESTONE | 225 | MILESTONE | ME | Mechanical | 0 |  | 2019-12-20 |  | 1398/09/29
23S3-PC-225-MLS-140 | WHB MILESTONE | WHB MILESTONE | 225 | MILESTONE | PI | Piping | 0 |  | 2019-12-20 |  | 1398/09/29
225-WHB BLOW DOWN AND BLEED WATER SYSTEM (23S3-ECC-BDW-030) | 23S3-ECC-BDW-030 |  | 225 | BDW |  |  | 6 | 2019-11-20 | 2019-11-26 | 1398/08/29 | 1398/09/05
FSF Off Gas Handling Bleed Electrical System (225-EC-BDW-EL-001) | 23S3-ECC-BDW-030 | 225-EC-BDW-EL-001 | 225 | BDW | EL |  | 2 | 2019-11-24 | 2019-11-26 | 1398/09/03 | 1398/09/05
23S3-PC-225-EL-300 | 23S3-ECC-BDW-030 | 225-EC-BDW-EL-001 | 225 | BDW | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
23S3-PC-225-EL-310 | 23S3-ECC-BDW-030 | 225-EC-BDW-EL-001 | 225 | BDW | EL | motor continuity megger test | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
23S3-PC-225-EL-320 | 23S3-ECC-BDW-030 | 225-EC-BDW-EL-001 | 225 | BDW | EL | gland and connection final inspection | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
23S3-PC-225-EL-330 | 23S3-ECC-BDW-030 | 225-EC-BDW-EL-001 | 225 | BDW | EL | LCS final function test | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-225-EL-460 | 23S3-ECC-BDW-030 | 225-EC-BDW-EL-001 | 225 | BDW | EL | feeder final checking | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-225-EL-470 | 23S3-ECC-BDW-030 | 225-EC-BDW-EL-001 | 225 | BDW | EL | motor free run & load test | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
FSF Off Gas Handling Bleed Instrument System (225-EC-BDW-IN-001) | 23S3-ECC-BDW-030 | 225-EC-BDW-IN-001 | 225 | BDW | IN |  | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-225-IN-100 | 23S3-ECC-BDW-030 | 225-EC-BDW-IN-001 | 225 | BDW | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-225-IN-110 | 23S3-ECC-BDW-030 | 225-EC-BDW-IN-001 | 225 | BDW | IN | device calibration | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-225-IN-120 | 23S3-ECC-BDW-030 | 225-EC-BDW-IN-001 | 225 | BDW | IN | device installation final check and punch clearance | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-225-IN-130 | 23S3-ECC-BDW-030 | 225-EC-BDW-IN-001 | 225 | BDW | IN | IO and loop checking | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-225-IN-140 | 23S3-ECC-BDW-030 | 225-EC-BDW-IN-001 | 225 | BDW | IN | function test | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
FSF Off Gas Handling Bleed Mechanical System (225-EC-BDW-ME-001) | 23S3-ECC-BDW-030 | 225-EC-BDW-ME-001 | 225 | BDW | ME |  | 4 | 2019-11-20 | 2019-11-24 | 1398/08/29 | 1398/09/03
23S3-PC-225-ME-100 | 23S3-ECC-BDW-030 | 225-EC-BDW-ME-001 | 225 | BDW | ME | Motor and Pump installation final check and punch clearance | 1 | 2019-11-20 | 2019-11-21 | 1398/08/29 | 1398/08/30
23S3-PC-225-ME-110 | 23S3-ECC-BDW-030 | 225-EC-BDW-ME-001 | 225 | BDW | ME | Flange Parallel Check and adjastment | 1 | 2019-11-21 | 2019-11-22 | 1398/08/30 | 1398/09/01
23S3-PC-225-ME-120 | 23S3-ECC-BDW-030 | 225-EC-BDW-ME-001 | 225 | BDW | ME | Pump Adjustment | 1 | 2019-11-22 | 2019-11-23 | 1398/09/01 | 1398/09/02
23S3-PC-225-ME-290 | 23S3-ECC-BDW-030 | 225-EC-BDW-ME-001 | 225 | BDW | ME | Coupling pump and motor / load run test | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
FSF Off Gas Handling Bleed Piping System (225-EC-BDW-PI-001) | 23S3-ECC-BDW-030 | 225-EC-BDW-PI-001 | 225 | BDW | PI |  | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
23S3-PC-225-PI-100 | 23S3-ECC-BDW-030 | 225-EC-BDW-PI-001 | 225 | BDW | PI | Punch Clearance | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
225-ESP (MILESTONE) | ESP MILESTONE |  | 225 | MILESTONE |  |  | 9 | 2019-11-21 | 2019-11-30 | 1398/08/30 | 1398/09/09
23S3-PC-225-MLS-150 | ESP MILESTONE | ESP MILESTONE | 225 | MILESTONE | EL | Electrical | 0 |  | 2019-11-30 |  | 1398/09/09
23S3-PC-225-MLS-160 | ESP MILESTONE | ESP MILESTONE | 225 | MILESTONE | IN | Instrument | 0 |  | 2019-11-28 |  | 1398/09/07
23S3-PC-225-MLS-170 | ESP MILESTONE | ESP MILESTONE | 225 | MILESTONE | ME | Mechanical | 0 |  | 2019-11-21 |  | 1398/08/30
23S3-PC-225-MLS-180 | ESP MILESTONE | ESP MILESTONE | 225 | MILESTONE | PI | Piping | 0 |  | 2019-11-25 |  | 1398/09/04
225-WHB &ESP MEASUREMENT AND DUCT WORK SYSTEM (23S3-ECC-OGF-034) | 23S3-ECC-OGF-034 |  | 225 | OGF |  |  | 16 | 2019-11-30 | 2019-12-16 | 1398/09/09 | 1398/09/25
FSF Gas Handling & Dust Collection Duct Work Electrical System (225-EC-OGF-EL-001) | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-001 | 225 | OGF | EL |  | 3 | 2019-12-02 | 2019-12-05 | 1398/09/11 | 1398/09/14
23S3-PC-225-EL-340 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-001 | 225 | OGF | EL | Electrical Cable Check and continuity megger test | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-225-EL-350 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-001 | 225 | OGF | EL | motor continuity megger test | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-225-EL-360 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-001 | 225 | OGF | EL | gland and connection final inspection | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-225-EL-370 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-001 | 225 | OGF | EL | LCS final function test | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-225-EL-380 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-001 | 225 | OGF | EL | feeder final checking | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-225-EL-390 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-001 | 225 | OGF | EL | Fan free run & load test | 1 | 2019-12-04 | 2019-12-05 | 1398/09/13 | 1398/09/14
FSF Gas Handling & Dust Collection Duct Work Electrical System (225-EC-OGF-EL-002) | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-002 | 225 | OGF | EL |  | 7 | 2019-12-07 | 2019-12-14 | 1398/09/16 | 1398/09/23
23S3-PC-225-EL-400 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-002 | 225 | OGF | EL | Electrical Cable Check and continuity megger test | 1 | 2019-12-07 | 2019-12-08 | 1398/09/16 | 1398/09/17
23S3-PC-225-EL-410 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-002 | 225 | OGF | EL | motor continuity megger test | 1 | 2019-12-08 | 2019-12-09 | 1398/09/17 | 1398/09/18
23S3-PC-225-EL-420 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-002 | 225 | OGF | EL | gland and connection final inspection | 1 | 2019-12-09 | 2019-12-10 | 1398/09/18 | 1398/09/19
23S3-PC-225-EL-430 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-002 | 225 | OGF | EL | LCS final function test | 1 | 2019-12-10 | 2019-12-11 | 1398/09/19 | 1398/09/20
23S3-PC-225-EL-440 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-002 | 225 | OGF | EL | feeder final checking | 1 | 2019-12-11 | 2019-12-12 | 1398/09/20 | 1398/09/21
23S3-PC-225-EL-450 | 23S3-ECC-OGF-034 | 225-EC-OGF-EL-002 | 225 | OGF | EL | Fan free run & load test | 2 | 2019-12-12 | 2019-12-14 | 1398/09/21 | 1398/09/23
FSF Gas Handling & Dust Collection Duct Work Instrument System (225-EC-OGF-IN-001) | 23S3-ECC-OGF-034 | 225-EC-OGF-IN-001 | 225 | OGF | IN |  | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
23S3-PC-225-IN-150 | 23S3-ECC-OGF-034 | 225-EC-OGF-IN-001 | 225 | OGF | IN | Instrument Cable Check and continuity megger test | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-225-IN-160 | 23S3-ECC-OGF-034 | 225-EC-OGF-IN-001 | 225 | OGF | IN | device calibration | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-225-IN-170 | 23S3-ECC-OGF-034 | 225-EC-OGF-IN-001 | 225 | OGF | IN | device installation final check and punch clearance | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-225-IN-180 | 23S3-ECC-OGF-034 | 225-EC-OGF-IN-001 | 225 | OGF | IN | IO and loop checking | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-225-IN-190 | 23S3-ECC-OGF-034 | 225-EC-OGF-IN-001 | 225 | OGF | IN | function test | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
FSF Gas Handling & Dust Collection Duct Work Mechanical System (225-EC-OGF-ME-001) | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-001 | 225 | OGF | ME |  | 5 | 2019-12-06 | 2019-12-11 | 1398/09/15 | 1398/09/20
23S3-PC-225-ME-150 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-001 | 225 | OGF | ME | duct work final check and punch clearance | 5 | 2019-12-06 | 2019-12-11 | 1398/09/15 | 1398/09/20
FSF Gas Handling & Dust Collection Duct Work Mechanical System (225-EC-OGF-ME-002) | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-002 | 225 | OGF | ME |  | 3 | 2019-11-30 | 2019-12-03 | 1398/09/09 | 1398/09/12
23S3-PC-225-ME-170 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-002 | 225 | OGF | ME | Motor and Fan installation final check and punch clearance | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-225-ME-180 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-002 | 225 | OGF | ME | Flange Parallel Check and adjastment | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-225-ME-190 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-002 | 225 | OGF | ME | Fan Adjustment | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
23S3-PC-225-ME-200 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-002 | 225 | OGF | ME | Coupling Fan and motor / load run test | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
FSF Gas Handling & Dust Collection Duct Work Mechanical System (225-EC-OGF-ME-003) | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-003 | 225 | OGF | ME |  | 16 | 2019-11-30 | 2019-12-16 | 1398/09/09 | 1398/09/25
23S3-PC-225-ME-210 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-003 | 225 | OGF | ME | Motor and Fan installation final check and punch clearance | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
23S3-PC-225-ME-220 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-003 | 225 | OGF | ME | Flange Parallel Check and adjastment | 3 | 2019-12-02 | 2019-12-05 | 1398/09/11 | 1398/09/14
23S3-PC-225-ME-230 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-003 | 225 | OGF | ME | Fan Adjustment | 2 | 2019-12-05 | 2019-12-07 | 1398/09/14 | 1398/09/16
23S3-PC-225-ME-240 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-003 | 225 | OGF | ME | Coupling Fan & Motor / load run test | 2 | 2019-12-14 | 2019-12-16 | 1398/09/23 | 1398/09/25
FSF Gas Handling & Dust Collection Duct Work Mechanical System (225-EC-OGF-ME-004) | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-004 | 225 | OGF | ME |  | 5 | 2019-12-06 | 2019-12-11 | 1398/09/15 | 1398/09/20
23S3-PC-225-ME-270 | 23S3-ECC-OGF-034 | 225-EC-OGF-ME-004 | 225 | OGF | ME | duct work final check and punch clearance | 5 | 2019-12-06 | 2019-12-11 | 1398/09/15 | 1398/09/20
220-PROCESS AIR FAN/OXYGEN ENRICHMENT (23S3-ECC-PAF-015) | 23S3-ECC-PAF-015 |  | 220 | PAF |  |  | 13 | 2019-11-23 | 2019-12-06 | 1398/09/02 | 1398/09/15
Process Air Fan/Oxygen Enrichment Electrical System (220-EC-PAF-EL-001) | 23S3-ECC-PAF-015 | 220-EC-PAF-EL-001 | 220 | PAF | EL |  | 2 | 2019-11-26 | 2019-11-28 | 1398/09/05 | 1398/09/07
23S3-PC-220-EL-500 | 23S3-ECC-PAF-015 | 220-EC-PAF-EL-001 | 220 | PAF | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-510 | 23S3-ECC-PAF-015 | 220-EC-PAF-EL-001 | 220 | PAF | EL | motor continuity megger test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-520 | 23S3-ECC-PAF-015 | 220-EC-PAF-EL-001 | 220 | PAF | EL | gland and connection final inspection | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-530 | 23S3-ECC-PAF-015 | 220-EC-PAF-EL-001 | 220 | PAF | EL | LCS final function test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-540 | 23S3-ECC-PAF-015 | 220-EC-PAF-EL-001 | 220 | PAF | EL | feeder final checking | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-550 | 23S3-ECC-PAF-015 | 220-EC-PAF-EL-001 | 220 | PAF | EL | Fan free run & load test | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
Process Air Fan/Oxygen Enrichment Instrument System (220-EC-PAF-IN-001) | 23S3-ECC-PAF-015 | 220-EC-PAF-IN-001 | 220 | PAF | IN |  | 7 | 2019-11-24 | 2019-12-01 | 1398/09/03 | 1398/09/10
23S3-PC-220-IN-930 | 23S3-ECC-PAF-015 | 220-EC-PAF-IN-001 | 220 | PAF | IN | Instrument Cable Check and continuity megger test | 2 | 2019-11-24 | 2019-11-26 | 1398/09/03 | 1398/09/05
23S3-PC-220-IN-940 | 23S3-ECC-PAF-015 | 220-EC-PAF-IN-001 | 220 | PAF | IN | device calibration | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-220-IN-950 | 23S3-ECC-PAF-015 | 220-EC-PAF-IN-001 | 220 | PAF | IN | device installation final check and punch clearance | 2 | 2019-11-26 | 2019-11-28 | 1398/09/05 | 1398/09/07
23S3-PC-220-IN-960 | 23S3-ECC-PAF-015 | 220-EC-PAF-IN-001 | 220 | PAF | IN | IO and loop checking | 3 | 2019-11-27 | 2019-11-30 | 1398/09/06 | 1398/09/09
23S3-PC-220-IN-970 | 23S3-ECC-PAF-015 | 220-EC-PAF-IN-001 | 220 | PAF | IN | function test | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
Process Air Fan/Oxygen Enrichment Mechanical System (220-EC-PAF-ME-001) | 23S3-ECC-PAF-015 | 220-EC-PAF-ME-001 | 220 | PAF | ME |  | 13 | 2019-11-23 | 2019-12-06 | 1398/09/02 | 1398/09/15
23S3-PC-220-ME-460 | 23S3-ECC-PAF-015 | 220-EC-PAF-ME-001 | 220 | PAF | ME | motor and fan installation final check and punch clearance | 1 | 2019-11-23 | 2019-11-24 | 1398/09/02 | 1398/09/03
23S3-PC-220-ME-470 | 23S3-ECC-PAF-015 | 220-EC-PAF-ME-001 | 220 | PAF | ME | duct work final check and punch clearance | 2 | 2019-11-23 | 2019-11-25 | 1398/09/02 | 1398/09/04
23S3-PC-220-ME-480 | 23S3-ECC-PAF-015 | 220-EC-PAF-ME-001 | 220 | PAF | ME | Flange Parallel Check and adjastment | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-220-ME-970 | 23S3-ECC-PAF-015 | 220-EC-PAF-ME-001 | 220 | PAF | ME | Fan Adjustment | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
23S3-PC-220-ME-980 | 23S3-ECC-PAF-015 | 220-EC-PAF-ME-001 | 220 | PAF | ME | Coupling Fan & Motor / load run test | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
23S3-PC-220-ME-990 | 23S3-ECC-PAF-015 | 220-EC-PAF-ME-001 | 220 | PAF | ME | check for pre box-up and punch clearance | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
23S3-PC-220-ME-995 | 23S3-ECC-PAF-015 | 220-EC-PAF-ME-001 | 220 | PAF | ME | final boxup | 2 | 2019-12-04 | 2019-12-06 | 1398/09/13 | 1398/09/15
220-CONCENTRATE BURNER WITH FEEDING (23S3-ECC-CBU-023) | 23S3-ECC-CBU-023 |  | 220 | CBU |  |  | 10 | 2019-11-24 | 2019-12-04 | 1398/09/03 | 1398/09/13
Concentrate Burner With Feeding Electrical System (220-EC-CBU-EL-001) | 23S3-ECC-CBU-023 | 220-EC-CBU-EL-001 | 220 | CBU | EL |  | 2 | 2019-11-26 | 2019-11-28 | 1398/09/05 | 1398/09/07
23S3-PC-220-EL-560 | 23S3-ECC-CBU-023 | 220-EC-CBU-EL-001 | 220 | CBU | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-570 | 23S3-ECC-CBU-023 | 220-EC-CBU-EL-001 | 220 | CBU | EL | motor continuity megger test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-580 | 23S3-ECC-CBU-023 | 220-EC-CBU-EL-001 | 220 | CBU | EL | gland and connection final inspection | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-590 | 23S3-ECC-CBU-023 | 220-EC-CBU-EL-001 | 220 | CBU | EL | LCS final function test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-600 | 23S3-ECC-CBU-023 | 220-EC-CBU-EL-001 | 220 | CBU | EL | feeder final checking | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-610 | 23S3-ECC-CBU-023 | 220-EC-CBU-EL-001 | 220 | CBU | EL | Fan free run & load test | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
Concentrate Burner With Feeding Instrument System (220-EC-CBU-IN-001) | 23S3-ECC-CBU-023 | 220-EC-CBU-IN-001 | 220 | CBU | IN |  | 10 | 2019-11-24 | 2019-12-04 | 1398/09/03 | 1398/09/13
23S3-PC-220-IN-0980 | 23S3-ECC-CBU-023 | 220-EC-CBU-IN-001 | 220 | CBU | IN | Instrument Cable Check and continuity megger test | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
23S3-PC-220-IN-0990 | 23S3-ECC-CBU-023 | 220-EC-CBU-IN-001 | 220 | CBU | IN | device calibration | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-IN-1000 | 23S3-ECC-CBU-023 | 220-EC-CBU-IN-001 | 220 | CBU | IN | device installation final check and punch clearance | 2 | 2019-11-27 | 2019-11-29 | 1398/09/06 | 1398/09/08
23S3-PC-220-IN-1010 | 23S3-ECC-CBU-023 | 220-EC-CBU-IN-001 | 220 | CBU | IN | IO and loop checking | 4 | 2019-11-29 | 2019-12-03 | 1398/09/08 | 1398/09/12
23S3-PC-220-IN-1020 | 23S3-ECC-CBU-023 | 220-EC-CBU-IN-001 | 220 | CBU | IN | function test | 5 | 2019-11-29 | 2019-12-04 | 1398/09/08 | 1398/09/13
Concentrate Burner With Feeding Mechanical System (220-EC-CBU-ME-001) | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-001 | 220 | CBU | ME |  | 6 | 2019-11-24 | 2019-11-30 | 1398/09/03 | 1398/09/09
23S3-PC-220-ME-490 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-001 | 220 | CBU | ME | Vendor at Site ( Outotec Mechanic & Process supervisor ) | 0 | 2019-11-24 |  | 1398/09/03
23S3-PC-220-ME-495 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-001 | 220 | CBU | ME | Burner And Accessory installation final check and punch clearance | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
23S3-PC-220-ME-500 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-001 | 220 | CBU | ME | Burner adjustment | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-220-ME-540 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-001 | 220 | CBU | ME | All hose connection installation final check and punch clearance | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
Concentrate Burner With Feeding Mechanical System (220-EC-CBU-ME-002) | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-002 | 220 | CBU | ME |  | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
23S3-PC-220-ME-550 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-002 | 220 | CBU | ME | Conveyor And Accessory installation final check and punch clearance | 3 | 2019-11-24 | 2019-11-27 | 1398/09/03 | 1398/09/06
23S3-PC-220-ME-560 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-002 | 220 | CBU | ME | Conveyor adjustment | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
Concentrate Burner With Feeding Mechanical System (220-EC-CBU-ME-003) | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-003 | 220 | CBU | ME |  | 5 | 2019-11-24 | 2019-11-29 | 1398/09/03 | 1398/09/08
23S3-PC-220-ME-610 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-003 | 220 | CBU | ME | motor and fan installation final check and punch clearance | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
23S3-PC-220-ME-620 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-003 | 220 | CBU | ME | duct work final check and punch clearance | 2 | 2019-11-24 | 2019-11-26 | 1398/09/03 | 1398/09/05
23S3-PC-220-ME-630 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-003 | 220 | CBU | ME | Flange Parallel Check and adjastment | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-ME-640 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-003 | 220 | CBU | ME | Fan Adjustment | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-220-ME-650 | 23S3-ECC-CBU-023 | 220-EC-CBU-ME-003 | 220 | CBU | ME | Coupling the motor and no load run test | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
220-LOW PRESSURE OXYGEN SYSTEM (23S3-ECC-LPO-016) | 23S3-ECC-LPO-016 |  | 220 | LPO |  |  | 3 | 2019-11-30 | 2019-12-03 | 1398/09/09 | 1398/09/12
Low Pressure Oxygen Instrument System (220-EC-LPO-IN-001) | 23S3-ECC-LPO-016 | 220-EC-LPO-IN-001 | 220 | LPO | IN |  | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
23S3-PC-220-IN-1030 | 23S3-ECC-LPO-016 | 220-EC-LPO-IN-001 | 220 | LPO | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-220-IN-1040 | 23S3-ECC-LPO-016 | 220-EC-LPO-IN-001 | 220 | LPO | IN | device calibration | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-220-IN-1050 | 23S3-ECC-LPO-016 | 220-EC-LPO-IN-001 | 220 | LPO | IN | device installation final check and punch clearance | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-220-IN-1060 | 23S3-ECC-LPO-016 | 220-EC-LPO-IN-001 | 220 | LPO | IN | IO and loop checking | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-220-IN-1070 | 23S3-ECC-LPO-016 | 220-EC-LPO-IN-001 | 220 | LPO | IN | function test | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
Low Pressure Oxygen Mechanical System (220-EC-LPO-ME-001) | 23S3-ECC-LPO-016 | 220-EC-LPO-ME-001 | 220 | LPO | ME |  | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-220-ME-670 | 23S3-ECC-LPO-016 | 220-EC-LPO-ME-001 | 220 | LPO | ME | Lance And Accessory installation final check and punch clearance | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
Low Pressure Oxygen Piping System (220-EC-LPO-PI-001) | 23S3-ECC-LPO-016 | 220-EC-LPO-PI-001 | 220 | LPO | PI |  | 3 | 2019-11-30 | 2019-12-03 | 1398/09/09 | 1398/09/12
23S3-PC-220-PI-170 | 23S3-ECC-LPO-016 | 220-EC-LPO-PI-001 | 220 | LPO | PI | Punch Clearance | 3 | 2019-11-30 | 2019-12-03 | 1398/09/09 | 1398/09/12
220-FSF OXYGEN HIGH PRESSURE NET WORK (23S3-ECC-OHP-022) | 23S3-ECC-OHP-022 |  | 220 | OHP |  |  | 11 | 2019-11-23 | 2019-12-04 | 1398/09/02 | 1398/09/13
FSF Oxygen High Pressure Net Work Instrument System (220-EC-OHP-IN-001) | 23S3-ECC-OHP-022 | 220-EC-OHP-IN-001 | 220 | OHP | IN |  | 4 | 2019-11-30 | 2019-12-04 | 1398/09/09 | 1398/09/13
23S3-PC-220-IN-1080 | 23S3-ECC-OHP-022 | 220-EC-OHP-IN-001 | 220 | OHP | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-220-IN-1090 | 23S3-ECC-OHP-022 | 220-EC-OHP-IN-001 | 220 | OHP | IN | device calibration | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-220-IN-1100 | 23S3-ECC-OHP-022 | 220-EC-OHP-IN-001 | 220 | OHP | IN | device installation final check and punch clearance | 2 | 2019-12-01 | 2019-12-03 | 1398/09/10 | 1398/09/12
23S3-PC-220-IN-1110 | 23S3-ECC-OHP-022 | 220-EC-OHP-IN-001 | 220 | OHP | IN | IO and loop checking | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-220-IN-1120 | 23S3-ECC-OHP-022 | 220-EC-OHP-IN-001 | 220 | OHP | IN | function test | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
FSF Oxygen High Pressure Net Work Piping System (220-EC-OHP-PI-001) | 23S3-ECC-OHP-022 | 220-EC-OHP-PI-001 | 220 | OHP | PI |  | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
23S3-PC-220-PI-180 | 23S3-ECC-OHP-022 | 220-EC-OHP-PI-001 | 220 | OHP | PI | Punch Clearance | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
220-FSF VENTILATION DUKT WORK MODIFICATION (23S3-ECC-VDW-029) | 23S3-ECC-VDW-029 |  | 220 | VDW |  |  | 6 | 2019-11-23 | 2019-11-29 | 1398/09/02 | 1398/09/08
FSF ventilation Dukt Work Modification Instrument System (220-EC-VDW-IN-001) | 23S3-ECC-VDW-029 | 220-EC-VDW-IN-001 | 220 | VDW | IN |  | 3 | 2019-11-25 | 2019-11-28 | 1398/09/04 | 1398/09/07
23S3-PC-220-IN-1130 | 23S3-ECC-VDW-029 | 220-EC-VDW-IN-001 | 220 | VDW | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-220-IN-1140 | 23S3-ECC-VDW-029 | 220-EC-VDW-IN-001 | 220 | VDW | IN | device calibration | 1 | 2019-11-25 | 2019-11-26 | 1398/09/04 | 1398/09/05
23S3-PC-220-IN-1150 | 23S3-ECC-VDW-029 | 220-EC-VDW-IN-001 | 220 | VDW | IN | device installation final check and punch clearance | 2 | 2019-11-26 | 2019-11-28 | 1398/09/05 | 1398/09/07
23S3-PC-220-IN-1160 | 23S3-ECC-VDW-029 | 220-EC-VDW-IN-001 | 220 | VDW | IN | IO and loop checking | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-220-IN-1170 | 23S3-ECC-VDW-029 | 220-EC-VDW-IN-001 | 220 | VDW | IN | function test | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
FSF ventilation Dukt Work Modification Mechanical System (220-EC-VDW-ME-001) | 23S3-ECC-VDW-029 | 220-EC-VDW-ME-001 | 220 | VDW | ME |  | 6 | 2019-11-23 | 2019-11-29 | 1398/09/02 | 1398/09/08
23S3-PC-220-ME-680 | 23S3-ECC-VDW-029 | 220-EC-VDW-ME-001 | 220 | VDW | ME | duct work final check and punch clearance | 3 | 2019-11-23 | 2019-11-26 | 1398/09/02 | 1398/09/05
23S3-PC-220-ME-690 | 23S3-ECC-VDW-029 | 220-EC-VDW-ME-001 | 220 | VDW | ME | check for pre box-up and punch clearance | 2 | 2019-11-26 | 2019-11-28 | 1398/09/05 | 1398/09/07
23S3-PC-220-ME-700 | 23S3-ECC-VDW-029 | 220-EC-VDW-ME-001 | 220 | VDW | ME | Final Box-up | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
220-Concentrate BIN & LIW Feeding (23S3-ECC-CBL-013) | 23S3-ECC-CBL-013 |  | 220 | CBL |  |  | 18 | 2019-11-24 | 2019-12-12 | 1398/09/03 | 1398/09/21
Concentrate BIN & LIW FeedingElectrical System (220-EC-CBL-EL-001) | 23S3-ECC-CBL-013 | 220-EC-CBL-EL-001 | 220 | CBL | EL |  | 3 | 2019-11-25 | 2019-11-28 | 1398/09/04 | 1398/09/07
23S3-PC-220-EL-620 | 23S3-ECC-CBL-013 | 220-EC-CBL-EL-001 | 220 | CBL | EL | Electrical Cable Check and continuity megger test | 2 | 2019-11-25 | 2019-11-27 | 1398/09/04 | 1398/09/06
23S3-PC-220-EL-630 | 23S3-ECC-CBL-013 | 220-EC-CBL-EL-001 | 220 | CBL | EL | motor continuity megger test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-640 | 23S3-ECC-CBL-013 | 220-EC-CBL-EL-001 | 220 | CBL | EL | gland and connection final inspection | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-650 | 23S3-ECC-CBL-013 | 220-EC-CBL-EL-001 | 220 | CBL | EL | LCS final function test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-660 | 23S3-ECC-CBL-013 | 220-EC-CBL-EL-001 | 220 | CBL | EL | feeder final checking | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-EL-670 | 23S3-ECC-CBL-013 | 220-EC-CBL-EL-001 | 220 | CBL | EL | motor free run test | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
Concentrate BIN & LIW FeedingInstrument System (220-EC-CBL-IN-001) | 23S3-ECC-CBL-013 | 220-EC-CBL-IN-001 | 220 | CBL | IN |  | 10 | 2019-12-02 | 2019-12-12 | 1398/09/11 | 1398/09/21
23S3-PC-220-IN-1180 | 23S3-ECC-CBL-013 | 220-EC-CBL-IN-001 | 220 | CBL | IN | Instrument Cable Check and continuity megger test | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
23S3-PC-220-IN-1190 | 23S3-ECC-CBL-013 | 220-EC-CBL-IN-001 | 220 | CBL | IN | device calibration | 2 | 2019-12-03 | 2019-12-05 | 1398/09/12 | 1398/09/14
23S3-PC-220-IN-1200 | 23S3-ECC-CBL-013 | 220-EC-CBL-IN-001 | 220 | CBL | IN | device installation final check and punch clearance | 3 | 2019-12-04 | 2019-12-07 | 1398/09/13 | 1398/09/16
23S3-PC-220-IN-1210 | 23S3-ECC-CBL-013 | 220-EC-CBL-IN-001 | 220 | CBL | IN | IO and loop checking | 2 | 2019-12-06 | 2019-12-08 | 1398/09/15 | 1398/09/17
23S3-PC-220-IN-1220 | 23S3-ECC-CBL-013 | 220-EC-CBL-IN-001 | 220 | CBL | IN | function test | 5 | 2019-12-07 | 2019-12-12 | 1398/09/16 | 1398/09/21
Concentrate BIN & LIW FeedingMechanical System (220-EC-CBL-ME-001) | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-001 | 220 | CBL | ME |  | 12 | 2019-11-25 | 2019-12-07 | 1398/09/04 | 1398/09/16
23S3-PC-220-ME-710 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-001 | 220 | CBL | ME | duct work final check and punch clearance | 5 | 2019-11-25 | 2019-11-30 | 1398/09/04 | 1398/09/09
23S3-PC-220-ME-740 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-001 | 220 | CBL | ME | Motor and Fan installation final check and punch clearance | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-220-ME-750 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-001 | 220 | CBL | ME | Flange Parallel Check and adjastment | 2 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-220-ME-760 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-001 | 220 | CBL | ME | Valve Check | 5 | 2019-12-01 | 2019-12-06 | 1398/09/10 | 1398/09/15
23S3-PC-220-ME-770 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-001 | 220 | CBL | ME | Coupling fan / load run test | 1 | 2019-12-06 | 2019-12-07 | 1398/09/15 | 1398/09/16
Concentrate BIN & LIW FeedingMechanical System (220-EC-CBL-ME-002) | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-002 | 220 | CBL | ME |  | 7 | 2019-11-25 | 2019-12-02 | 1398/09/04 | 1398/09/11
23S3-PC-220-ME-780 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-002 | 220 | CBL | ME | check for pre box-up and punch clearance | 5 | 2019-11-25 | 2019-11-30 | 1398/09/04 | 1398/09/09
23S3-PC-220-ME-800 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-002 | 220 | CBL | ME | Valve Check | 3 | 2019-11-27 | 2019-11-30 | 1398/09/06 | 1398/09/09
23S3-PC-220-ME-810 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-002 | 220 | CBL | ME | Final Box-up | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
Concentrate BIN & LIW FeedingMechanical System (220-EC-CBL-ME-003) | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-003 | 220 | CBL | ME |  | 11 | 2019-11-25 | 2019-12-06 | 1398/09/04 | 1398/09/15
23S3-PC-220-ME-850 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-003 | 220 | CBL | ME | duct work final check and punch clearance | 3 | 2019-11-25 | 2019-11-28 | 1398/09/04 | 1398/09/07
23S3-PC-220-ME-860 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-003 | 220 | CBL | ME | check for pre box-up and punch clearance | 3 | 2019-11-28 | 2019-12-01 | 1398/09/07 | 1398/09/10
23S3-PC-220-ME-870 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-003 | 220 | CBL | ME | Final Box-up | 2 | 2019-12-01 | 2019-12-03 | 1398/09/10 | 1398/09/12
23S3-PC-220-ME-880 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-003 | 220 | CBL | ME | Motor and Fan installation final check and punch clearance | 3 | 2019-12-02 | 2019-12-05 | 1398/09/11 | 1398/09/14
23S3-PC-220-ME-890 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-003 | 220 | CBL | ME | Flange Parallel Check and adjastment | 2 | 2019-12-04 | 2019-12-06 | 1398/09/13 | 1398/09/15
23S3-PC-220-ME-900 | 23S3-ECC-CBL-013 | 220-EC-CBL-ME-003 | 220 | CBL | ME | Motor load run test | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
Concentrate BIN & LIW Feeding Piping System (220-EC-CBL-PI-001) | 23S3-ECC-CBL-013 | 220-EC-CBL-PI-001 | 220 | CBL | PI |  | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
23S3-PC-220-PI-200 | 23S3-ECC-CBL-013 | 220-EC-CBL-PI-001 | 220 | CBL | PI | Punch Clearance | 1 | 2019-11-24 | 2019-11-25 | 1398/09/03 | 1398/09/04
220-FLUE DUST BIN & LIW FEEDING (23S3-ECC-FDL-014) | 23S3-ECC-FDL-014 |  | 220 | FDL |  |  | 11 | 2019-11-26 | 2019-12-06 | 1398/09/05 | 1398/09/15
Flue Dust Bin & Liw Feeding Electrical System (220-EC-FDL-EL-001) | 23S3-ECC-FDL-014 | 220-EC-FDL-EL-001 | 220 | FDL | EL |  | 8 | 2019-11-29 | 2019-12-06 | 1398/09/08 | 1398/09/15
23S3-PC-220-EL-680 | 23S3-ECC-FDL-014 | 220-EC-FDL-EL-001 | 220 | FDL | EL | Electrical Cable Check and continuity megger test | 2 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-220-EL-690 | 23S3-ECC-FDL-014 | 220-EC-FDL-EL-001 | 220 | FDL | EL | motor continuity megger test | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
23S3-PC-220-EL-700 | 23S3-ECC-FDL-014 | 220-EC-FDL-EL-001 | 220 | FDL | EL | gland and connection final inspection | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-220-EL-710 | 23S3-ECC-FDL-014 | 220-EC-FDL-EL-001 | 220 | FDL | EL | LCS final function test | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-220-EL-720 | 23S3-ECC-FDL-014 | 220-EC-FDL-EL-001 | 220 | FDL | EL | feeder final checking | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-220-EL-730 | 23S3-ECC-FDL-014 | 220-EC-FDL-EL-001 | 220 | FDL | EL | motor free run test | 2 | 2019-12-04 | 2019-12-06 | 1398/09/13 | 1398/09/15
Flue Dust Bin & Liw Feeding Instrument System (220-EC-FDL-IN-001) | 23S3-ECC-FDL-014 | 220-EC-FDL-IN-001 | 220 | FDL | IN |  | 6 | 2019-11-29 | 2019-12-04 | 1398/09/08 | 1398/09/13
23S3-PC-220-IN-1230 | 23S3-ECC-FDL-014 | 220-EC-FDL-IN-001 | 220 | FDL | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-220-IN-1240 | 23S3-ECC-FDL-014 | 220-EC-FDL-IN-001 | 220 | FDL | IN | device calibration | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-220-IN-1245 | 23S3-ECC-FDL-014 | 220-EC-FDL-IN-001 | 220 | FDL | IN | Vendor at Site | 0 | 2019-11-30 |  | 1398/09/09
23S3-PC-220-IN-1250 | 23S3-ECC-FDL-014 | 220-EC-FDL-IN-001 | 220 | FDL | IN | device installation final check and punch clearance | 2 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-220-IN-1260 | 23S3-ECC-FDL-014 | 220-EC-FDL-IN-001 | 220 | FDL | IN | IO and loop checking | 2 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-220-IN-1270 | 23S3-ECC-FDL-014 | 220-EC-FDL-IN-001 | 220 | FDL | IN | function test | 3 | 2019-12-01 | 2019-12-04 | 1398/09/10 | 1398/09/13
Flue Dust Bin & Liw Feeding Mechanical System (220-EC-FDL-ME-001) | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-001 | 220 | FDL | ME |  | 11 | 2019-11-26 | 2019-12-06 | 1398/09/05 | 1398/09/15
23S3-PC-220-ME-920 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-001 | 220 | FDL | ME | duct work final check and punch clearance | 3 | 2019-11-26 | 2019-11-29 | 1398/09/05 | 1398/09/08
23S3-PC-220-ME-921 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-001 | 220 | FDL | ME | check for pre box-up and punch clearance | 3 | 2019-11-27 | 2019-11-30 | 1398/09/06 | 1398/09/09
23S3-PC-220-ME-922 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-001 | 220 | FDL | ME | Final Box-up | 2 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-220-ME-923 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-001 | 220 | FDL | ME | Motor and Fan installation final check and punch clearance | 3 | 2019-11-29 | 2019-12-02 | 1398/09/08 | 1398/09/11
23S3-PC-220-ME-924 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-001 | 220 | FDL | ME | Flange Parallel Check and adjastment | 2 | 2019-12-01 | 2019-12-03 | 1398/09/10 | 1398/09/12
23S3-PC-220-ME-925 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-001 | 220 | FDL | ME | Coupling Motor and fan / load run test | 2 | 2019-12-03 | 2019-12-05 | 1398/09/12 | 1398/09/14
23S3-PC-220-ME-945 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-001 | 220 | FDL | ME | Valve Check | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
Flue Dust Bin & Liw Feeding Mechanical System (220-EC-FDL-ME-002) | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-002 | 220 | FDL | ME |  | 6 | 2019-11-26 | 2019-12-01 | 1398/09/05 | 1398/09/10
23S3-PC-220-ME-933 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-002 | 220 | FDL | ME | Motor and Fan installation final check and punch clearance | 3 | 2019-11-26 | 2019-11-29 | 1398/09/05 | 1398/09/08
23S3-PC-220-ME-934 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-002 | 220 | FDL | ME | Flange Parallel Check and adjastment | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
23S3-PC-220-ME-935 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-002 | 220 | FDL | ME | Coupling pump and fan / load run test | 2 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-220-ME-965 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-002 | 220 | FDL | ME | Valve Check | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
Flue Dust Bin & Liw Feeding Mechanical System (220-EC-FDL-ME-003) | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-003 | 220 | FDL | ME |  | 4 | 2019-11-26 | 2019-11-30 | 1398/09/05 | 1398/09/09
23S3-PC-220-ME-953 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-003 | 220 | FDL | ME | Conveyor installation final check and punch clearance | 2 | 2019-11-26 | 2019-11-28 | 1398/09/05 | 1398/09/07
23S3-PC-220-ME-954 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-003 | 220 | FDL | ME | Belt adjastment | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-220-ME-975 | 23S3-ECC-FDL-014 | 220-EC-FDL-ME-003 | 220 | FDL | ME | Motor load run test | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
Flue Dust Bin & Liw Feeding Piping System (220-EC-FDL-PI-001) | 23S3-ECC-FDL-014 | 220-EC-FDL-PI-001 | 220 | FDL | PI |  | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-220-PI-190 | 23S3-ECC-FDL-014 | 220-EC-FDL-PI-001 | 220 | FDL | PI | Punch Clearance | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
210-Steam Drying (23S3-ECC-STD-009) | 23S3-ECC-STD-009 |  | 210 | STD |  |  | 9 | 2019-11-26 | 2019-12-05 | 1398/09/05 | 1398/09/14
STEAM DRYER ELECTRICAL SYSTEM (210-EC-STD-EL-001) | 23S3-ECC-STD-009 | 210-EC-STD-EL-001 | 210 | STD | EL |  | 5 | 2019-11-26 | 2019-12-01 | 1398/09/05 | 1398/09/10
23S3-PC-210-EL-259 | 23S3-ECC-STD-009 | 210-EC-STD-EL-001 | 210 | STD | EL | Vendor at Site | 0 | 2019-11-26 |  | 1398/09/05
23S3-PC-210-EL-260 | 23S3-ECC-STD-009 | 210-EC-STD-EL-001 | 210 | STD | EL | Electrical Cable Check and continuity megger test | 3 | 2019-11-26 | 2019-11-29 | 1398/09/05 | 1398/09/08
23S3-PC-210-EL-261 | 23S3-ECC-STD-009 | 210-EC-STD-EL-001 | 210 | STD | EL | motor continuity megger test | 2 | 2019-11-27 | 2019-11-29 | 1398/09/06 | 1398/09/08
23S3-PC-210-EL-262 | 23S3-ECC-STD-009 | 210-EC-STD-EL-001 | 210 | STD | EL | gland and connection final inspection | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
23S3-PC-210-EL-263 | 23S3-ECC-STD-009 | 210-EC-STD-EL-001 | 210 | STD | EL | LCS final function test | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
23S3-PC-210-EL-264 | 23S3-ECC-STD-009 | 210-EC-STD-EL-001 | 210 | STD | EL | feeder final checking | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
23S3-PC-210-EL-265 | 23S3-ECC-STD-009 | 210-EC-STD-EL-001 | 210 | STD | EL | motor free run & load test | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
STEAM DRYER ELECTRICAL CRANE SYSTEM (210-EC-STD-EL-002) | 23S3-ECC-STD-009 | 210-EC-STD-EL-002 | 210 | STD | EL |  | 5 | 2019-11-26 | 2019-12-01 | 1398/09/05 | 1398/09/10
23S3-PC-210-EL-270 | 23S3-ECC-STD-009 | 210-EC-STD-EL-002 | 210 | STD | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-26 | 2019-11-27 | 1398/09/05 | 1398/09/06
23S3-PC-210-EL-280 | 23S3-ECC-STD-009 | 210-EC-STD-EL-002 | 210 | STD | EL | motor continuity megger test | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-210-EL-290 | 23S3-ECC-STD-009 | 210-EC-STD-EL-002 | 210 | STD | EL | gland and connection final inspection | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
23S3-PC-210-EL-310 | 23S3-ECC-STD-009 | 210-EC-STD-EL-002 | 210 | STD | EL | feeder final checking | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-210-EL-311 | 23S3-ECC-STD-009 | 210-EC-STD-EL-002 | 210 | STD | EL | motor free run & load test | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
STEAM DRYER INSTRUMENTATION SYSTEM (210-EC-STD-IN-001) | 23S3-ECC-STD-009 | 210-EC-STD-IN-001 | 210 | STD | IN |  | 8 | 2019-11-26 | 2019-12-04 | 1398/09/05 | 1398/09/13
23S3-PC-210-IN-100 | 23S3-ECC-STD-009 | 210-EC-STD-IN-001 | 210 | STD | IN | Instrument Cable Check and continuity megger test | 2 | 2019-11-26 | 2019-11-28 | 1398/09/05 | 1398/09/07
23S3-PC-210-IN-110 | 23S3-ECC-STD-009 | 210-EC-STD-IN-001 | 210 | STD | IN | device calibration | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-210-IN-120 | 23S3-ECC-STD-009 | 210-EC-STD-IN-001 | 210 | STD | IN | device installation final check and punch clearance | 3 | 2019-11-27 | 2019-11-30 | 1398/09/06 | 1398/09/09
23S3-PC-210-IN-130 | 23S3-ECC-STD-009 | 210-EC-STD-IN-001 | 210 | STD | IN | IO and loop checking | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
23S3-PC-210-IN-140 | 23S3-ECC-STD-009 | 210-EC-STD-IN-001 | 210 | STD | IN | function test | 3 | 2019-12-01 | 2019-12-04 | 1398/09/10 | 1398/09/13
STEAM DRYER MECHANICAL SYSTEM (210-EC-STD-ME-001) | 23S3-ECC-STD-009 | 210-EC-STD-ME-001 | 210 | STD | ME |  | 9 | 2019-11-26 | 2019-12-05 | 1398/09/05 | 1398/09/14
23S3-PC-210-ME-100 | 23S3-ECC-STD-009 | 210-EC-STD-ME-001 | 210 | STD | ME | check for pre box-up and punch clearance | 3 | 2019-11-26 | 2019-11-29 | 1398/09/05 | 1398/09/08
23S3-PC-210-ME-110 | 23S3-ECC-STD-009 | 210-EC-STD-ME-001 | 210 | STD | ME | final boxup | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-210-ME-120 | 23S3-ECC-STD-009 | 210-EC-STD-ME-001 | 210 | STD | ME | motor and Crain installation final check and punch clearance | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-210-ME-130 | 23S3-ECC-STD-009 | 210-EC-STD-ME-001 | 210 | STD | ME | Dryer and other accessories adjustment final check and punch clearance | 4 | 2019-11-30 | 2019-12-04 | 1398/09/09 | 1398/09/13
23S3-PC-210-ME-140 | 23S3-ECC-STD-009 | 210-EC-STD-ME-001 | 210 | STD | ME | Coupling the motor and no load run test | 1 | 2019-12-04 | 2019-12-05 | 1398/09/13 | 1398/09/14
210-Steam Drying (23S3-ECC-STO-010) | 23S3-ECC-STO-010 |  | 210 | STO |  |  | 9 | 2019-11-26 | 2019-12-05 | 1398/09/05 | 1398/09/14
STEAM DRYER OFFGAS INSTRUMENTATION SYSTEM (210-EC-STO-IN-001) | 23S3-ECC-STO-010 | 210-EC-STO-IN-001 | 210 | STO | IN |  | 6 | 2019-11-28 | 2019-12-04 | 1398/09/07 | 1398/09/13
23S3-PC-210-IN-150 | 23S3-ECC-STO-010 | 210-EC-STO-IN-001 | 210 | STO | IN | Instrument Cable Check and continuity megger test | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
23S3-PC-210-IN-160 | 23S3-ECC-STO-010 | 210-EC-STO-IN-001 | 210 | STO | IN | device calibration | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-210-IN-170 | 23S3-ECC-STO-010 | 210-EC-STO-IN-001 | 210 | STO | IN | device installation final check and punch clearance | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
23S3-PC-210-IN-180 | 23S3-ECC-STO-010 | 210-EC-STO-IN-001 | 210 | STO | IN | IO and loop checking | 2 | 2019-12-01 | 2019-12-03 | 1398/09/10 | 1398/09/12
23S3-PC-210-IN-190 | 23S3-ECC-STO-010 | 210-EC-STO-IN-001 | 210 | STO | IN | function test | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
STEAM DRYER OFFGAS ELECTRICAL SYSTEM (210-EC-STO-EL-001) | 23S3-ECC-STO-010 | 210-EC-STO-EL-001 | 210 | STO | EL |  | 8 | 2019-11-27 | 2019-12-05 | 1398/09/06 | 1398/09/14
23S3-PC-210-EL-320 | 23S3-ECC-STO-010 | 210-EC-STO-EL-001 | 210 | STO | EL | Electrical Cable Check and continuity megger test | 2 | 2019-11-27 | 2019-11-29 | 1398/09/06 | 1398/09/08
23S3-PC-210-EL-330 | 23S3-ECC-STO-010 | 210-EC-STO-EL-001 | 210 | STO | EL | motor continuity megger test | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-210-EL-340 | 23S3-ECC-STO-010 | 210-EC-STO-EL-001 | 210 | STO | EL | gland and connection final inspection | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-210-EL-350 | 23S3-ECC-STO-010 | 210-EC-STO-EL-001 | 210 | STO | EL | LCS final function test | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-210-EL-360 | 23S3-ECC-STO-010 | 210-EC-STO-EL-001 | 210 | STO | EL | feeder final checking | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-210-EL-361 | 23S3-ECC-STO-010 | 210-EC-STO-EL-001 | 210 | STO | EL | motor free run & load test | 2 | 2019-12-03 | 2019-12-05 | 1398/09/12 | 1398/09/14
STEAM DRYER OFFGAS ELECTRICAL SYSTEM (210-EC-STO-EL-002) | 23S3-ECC-STO-010 | 210-EC-STO-EL-002 | 210 | STO | EL |  | 6 | 2019-11-27 | 2019-12-03 | 1398/09/06 | 1398/09/12
23S3-PC-210-EL-370 | 23S3-ECC-STO-010 | 210-EC-STO-EL-002 | 210 | STO | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-27 | 2019-11-28 | 1398/09/06 | 1398/09/07
23S3-PC-210-EL-380 | 23S3-ECC-STO-010 | 210-EC-STO-EL-002 | 210 | STO | EL | motor continuity megger test | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
23S3-PC-210-EL-390 | 23S3-ECC-STO-010 | 210-EC-STO-EL-002 | 210 | STO | EL | gland and connection final inspection | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-210-EL-400 | 23S3-ECC-STO-010 | 210-EC-STO-EL-002 | 210 | STO | EL | LCS final function test | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-210-EL-410 | 23S3-ECC-STO-010 | 210-EC-STO-EL-002 | 210 | STO | EL | feeder final checking | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-210-EL-411 | 23S3-ECC-STO-010 | 210-EC-STO-EL-002 | 210 | STO | EL | motor free run & load test | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
STEAM DRYER OFFGAS MECHANICAL SYSTEM (210-EC-STO-ME-001) | 23S3-ECC-STO-010 | 210-EC-STO-ME-001 | 210 | STO | ME |  | 7 | 2019-11-27 | 2019-12-04 | 1398/09/06 | 1398/09/13
23S3-PC-210-ME-170 | 23S3-ECC-STO-010 | 210-EC-STO-ME-001 | 210 | STO | ME | duct work final check and punch clearance | 4 | 2019-11-27 | 2019-12-01 | 1398/09/06 | 1398/09/10
23S3-PC-210-ME-190 | 23S3-ECC-STO-010 | 210-EC-STO-ME-001 | 210 | STO | ME | final boxup | 3 | 2019-12-01 | 2019-12-04 | 1398/09/10 | 1398/09/13
STEAM DRYER OFFGAS MECHANICAL SYSTEM (210-EC-STO-ME-002) | 23S3-ECC-STO-010 | 210-EC-STO-ME-002 | 210 | STO | ME |  | 6 | 2019-11-26 | 2019-12-02 | 1398/09/05 | 1398/09/11
23S3-PC-210-ME-200 | 23S3-ECC-STO-010 | 210-EC-STO-ME-002 | 210 | STO | ME | check for pre box-up and punch clearance | 2 | 2019-11-26 | 2019-11-28 | 1398/09/05 | 1398/09/07
23S3-PC-210-ME-210 | 23S3-ECC-STO-010 | 210-EC-STO-ME-002 | 210 | STO | ME | final boxup | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
23S3-PC-210-ME-240 | 23S3-ECC-STO-010 | 210-EC-STO-ME-002 | 210 | STO | ME | accessories adjustment final check and punch clearance | 3 | 2019-11-29 | 2019-12-02 | 1398/09/08 | 1398/09/11
STEAM DRYER OFFGAS MECHANICAL SYSTEM (210-EC-STO-ME-003) | 23S3-ECC-STO-010 | 210-EC-STO-ME-003 | 210 | STO | ME |  | 7 | 2019-11-26 | 2019-12-03 | 1398/09/05 | 1398/09/12
23S3-PC-210-ME-250 | 23S3-ECC-STO-010 | 210-EC-STO-ME-003 | 210 | STO | ME | check for pre box-up and punch clearance | 3 | 2019-11-26 | 2019-11-29 | 1398/09/05 | 1398/09/08
23S3-PC-210-ME-260 | 23S3-ECC-STO-010 | 210-EC-STO-ME-003 | 210 | STO | ME | final boxup | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-210-ME-270 | 23S3-ECC-STO-010 | 210-EC-STO-ME-003 | 210 | STO | ME | motor and conveyor installation final check and punch clearance | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-210-ME-280 | 23S3-ECC-STO-010 | 210-EC-STO-ME-003 | 210 | STO | ME | belt and other accessories adjustment final check and punch clearance | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
23S3-PC-210-ME-290 | 23S3-ECC-STO-010 | 210-EC-STO-ME-003 | 210 | STO | ME | Coupling the motor and no load run test | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
STEAM DRYER OFFGAS MECHANICAL SYSTEM (210-EC-STO-ME-004) | 23S3-ECC-STO-010 | 210-EC-STO-ME-004 | 210 | STO | ME |  | 3 | 2019-11-27 | 2019-11-30 | 1398/09/06 | 1398/09/09
23S3-PC-210-ME-300 | 23S3-ECC-STO-010 | 210-EC-STO-ME-004 | 210 | STO | ME | motor and conveyer installation final check and punch clearance | 2 | 2019-11-27 | 2019-11-29 | 1398/09/06 | 1398/09/08
23S3-PC-210-ME-320 | 23S3-ECC-STO-010 | 210-EC-STO-ME-004 | 210 | STO | ME | Coupling the motor and no load run test | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
STEAM DRYER OFFGAS PIPING SYSTEM (210-EC-STO-PI-001) | 23S3-ECC-STO-010 | 210-EC-STO-PI-001 | 210 | STO | PI |  | 2 | 2019-11-27 | 2019-11-29 | 1398/09/06 | 1398/09/08
23S3-PC-210-PI-110 | 23S3-ECC-STO-010 | 210-EC-STO-PI-001 | 210 | STO | PI | Punch Clearance | 2 | 2019-11-27 | 2019-11-29 | 1398/09/06 | 1398/09/08
210-Steam Drying (23S3-ECC-DFM-011) | 23S3-ECC-DFM-011 |  | 210 | DFM |  |  | 15 | 2019-11-28 | 2019-12-13 | 1398/09/07 | 1398/09/22
DRED FEED MIXTURE INSTRUMENTATION SYSTEM (210-EC-DFM-IN-001) | 23S3-ECC-DFM-011 | 210-EC-DFM-IN-001 | 210 | DFM | IN |  | 8 | 2019-11-28 | 2019-12-06 | 1398/09/07 | 1398/09/15
23S3-PC-210-IN-200 | 23S3-ECC-DFM-011 | 210-EC-DFM-IN-001 | 210 | DFM | IN | Instrument Cable Check and continuity megger test | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
23S3-PC-210-IN-210 | 23S3-ECC-DFM-011 | 210-EC-DFM-IN-001 | 210 | DFM | IN | device calibration | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-210-IN-220 | 23S3-ECC-DFM-011 | 210-EC-DFM-IN-001 | 210 | DFM | IN | device installation final check and punch clearance | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-210-IN-230 | 23S3-ECC-DFM-011 | 210-EC-DFM-IN-001 | 210 | DFM | IN | IO and loop checking | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
23S3-PC-210-IN-240 | 23S3-ECC-DFM-011 | 210-EC-DFM-IN-001 | 210 | DFM | IN | function test | 2 | 2019-12-04 | 2019-12-06 | 1398/09/13 | 1398/09/15
DRED FEED MIXTURE PIPING SYSTEM (210-EC-DFM-PI-001) | 23S3-ECC-DFM-011 | 210-EC-DFM-PI-001 | 210 | DFM | PI |  | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
23S3-PC-210-PI-120 | 23S3-ECC-DFM-011 | 210-EC-DFM-PI-001 | 210 | DFM | PI | Punch Clearance | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
DRED FEED MIXTURE MECHANICAL SYSTEM (210-EC-DFM-ME-001) | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-001 | 210 | DFM | ME |  | 15 | 2019-11-28 | 2019-12-13 | 1398/09/07 | 1398/09/22
23S3-PC-210-ME-350 | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-001 | 210 | DFM | ME | conveyer installation final check and punch clearance | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
23S3-PC-210-ME-360 | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-001 | 210 | DFM | ME | accessories adjustment final check and punch clearance | 3 | 2019-11-30 | 2019-12-03 | 1398/09/09 | 1398/09/12
23S3-PC-210-ME-380 | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-001 | 210 | DFM | ME | check for pre box-up and punch clearance | 8 | 2019-12-02 | 2019-12-10 | 1398/09/11 | 1398/09/19
23S3-PC-210-ME-390 | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-001 | 210 | DFM | ME | final boxup | 4 | 2019-12-09 | 2019-12-13 | 1398/09/18 | 1398/09/22
DRED FEED MIXTURE MECHANICAL SYSTEM (210-EC-DFM-ME-002) | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-002 | 210 | DFM | ME |  | 3 | 2019-11-28 | 2019-12-01 | 1398/09/07 | 1398/09/10
23S3-PC-210-ME-400 | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-002 | 210 | DFM | ME | conveyer installation final check and punch clearance | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
23S3-PC-210-ME-410 | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-002 | 210 | DFM | ME | accessories adjustment final check and punch clearance | 1 | 2019-11-28 | 2019-11-29 | 1398/09/07 | 1398/09/08
23S3-PC-210-ME-430 | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-002 | 210 | DFM | ME | check for pre box-up and punch clearance | 2 | 2019-11-28 | 2019-11-30 | 1398/09/07 | 1398/09/09
23S3-PC-210-ME-440 | 23S3-ECC-DFM-011 | 210-EC-DFM-ME-002 | 210 | DFM | ME | final boxup | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
210-Steam Drying (23S3-ECC-STC-012) | 23S3-ECC-STC-012 |  | 210 | STC |  |  | 7 | 2019-11-29 | 2019-12-06 | 1398/09/08 | 1398/09/15
STEAM AND CONDENSATE ELECTRICAL SYSTEM (210-EC-STC-EL-001) | 23S3-ECC-STC-012 | 210-EC-STC-EL-001 | 210 | STC | EL |  | 6 | 2019-11-29 | 2019-12-05 | 1398/09/08 | 1398/09/14
23S3-PC-210-EL-420 | 23S3-ECC-STC-012 | 210-EC-STC-EL-001 | 210 | STC | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-29 | 2019-11-30 | 1398/09/08 | 1398/09/09
23S3-PC-210-EL-430 | 23S3-ECC-STC-012 | 210-EC-STC-EL-001 | 210 | STC | EL | motor continuity megger test | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-210-EL-440 | 23S3-ECC-STC-012 | 210-EC-STC-EL-001 | 210 | STC | EL | gland and connection final inspection | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-210-EL-450 | 23S3-ECC-STC-012 | 210-EC-STC-EL-001 | 210 | STC | EL | LCS final function test | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-210-EL-460 | 23S3-ECC-STC-012 | 210-EC-STC-EL-001 | 210 | STC | EL | feeder final checking | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-210-EL-470 | 23S3-ECC-STC-012 | 210-EC-STC-EL-001 | 210 | STC | EL | motor free run test | 1 | 2019-12-04 | 2019-12-05 | 1398/09/13 | 1398/09/14
STEAM AND CONDENSATE INSTRUMENTATION SYSTEM (210-EC-STC-IN-001) | 23S3-ECC-STC-012 | 210-EC-STC-IN-001 | 210 | STC | IN |  | 7 | 2019-11-29 | 2019-12-06 | 1398/09/08 | 1398/09/15
23S3-PC-210-IN-250 | 23S3-ECC-STC-012 | 210-EC-STC-IN-001 | 210 | STC | IN | Instrument Cable Check and continuity megger test | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
23S3-PC-210-IN-260 | 23S3-ECC-STC-012 | 210-EC-STC-IN-001 | 210 | STC | IN | device calibration | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-210-IN-270 | 23S3-ECC-STC-012 | 210-EC-STC-IN-001 | 210 | STC | IN | device installation final check and punch clearance | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-210-IN-280 | 23S3-ECC-STC-012 | 210-EC-STC-IN-001 | 210 | STC | IN | IO and loop checking | 2 | 2019-12-03 | 2019-12-05 | 1398/09/12 | 1398/09/14
23S3-PC-210-IN-290 | 23S3-ECC-STC-012 | 210-EC-STC-IN-001 | 210 | STC | IN | function test | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
STEAM AND CONDENSATE MECHANICAL SYSTEM (210-EC-STC-ME-001) | 23S3-ECC-STC-012 | 210-EC-STC-ME-001 | 210 | STC | ME |  | 6 | 2019-11-29 | 2019-12-05 | 1398/09/08 | 1398/09/14
23S3-PC-210-ME-450 | 23S3-ECC-STC-012 | 210-EC-STC-ME-001 | 210 | STC | ME | Pump & Motor installation final check and punch clearance | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
23S3-PC-210-ME-470 | 23S3-ECC-STC-012 | 210-EC-STC-ME-001 | 210 | STC | ME | Coupling the motor and load run test | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-210-ME-480 | 23S3-ECC-STC-012 | 210-EC-STC-ME-001 | 210 | STC | ME | check for pre box-up and punch clearance | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
23S3-PC-210-ME-490 | 23S3-ECC-STC-012 | 210-EC-STC-ME-001 | 210 | STC | ME | final boxup | 1 | 2019-12-04 | 2019-12-05 | 1398/09/13 | 1398/09/14
STEAM PIPING SYSTEM (210-EC-STC-PI-001) | 23S3-ECC-STC-012 | 210-EC-STC-PI-001 | 210 | STC | PI |  | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
23S3-PC-210-PI-130 | 23S3-ECC-STC-012 | 210-EC-STC-PI-001 | 210 | STC | PI | Punch Clearance | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
CONDENSATE PIPING SYSTEM (210-EC-STC-PI-002) | 23S3-ECC-STC-012 | 210-EC-STC-PI-002 | 210 | STC | PI |  | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
23S3-PC-210-PI-140 | 23S3-ECC-STC-012 | 210-EC-STC-PI-002 | 210 | STC | PI | Punch Clearance | 2 | 2019-11-29 | 2019-12-01 | 1398/09/08 | 1398/09/10
150-Concentrate Blending (23S3-ECC-FMB-001) | 23S3-ECC-FMB-001 |  | 150 | FMB |  |  | 9 | 2019-11-30 | 2019-12-09 | 1398/09/09 | 1398/09/18
FEED MATERIAL CONVEYING AND BLENDING MODIFICATION ELECTRICAL (150-EC-FMB-EL-001) | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-001 | 150 | FMB | EL |  | 7 | 2019-11-30 | 2019-12-07 | 1398/09/09 | 1398/09/16
23S3-PC-150-EL-180 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-001 | 150 | FMB | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-150-EL-190 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-001 | 150 | FMB | EL | motor continuity megger test | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-150-EL-200 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-001 | 150 | FMB | EL | gland and connection final inspection | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-150-EL-210 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-001 | 150 | FMB | EL | LCS final function test | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-150-EL-220 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-001 | 150 | FMB | EL | feeder final checking | 1 | 2019-12-04 | 2019-12-05 | 1398/09/13 | 1398/09/14
23S3-PC-150-EL-230 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-001 | 150 | FMB | EL | motor free run test | 2 | 2019-12-05 | 2019-12-07 | 1398/09/14 | 1398/09/16
FEED MATERIAL CONVEYING AND BLENDING MODIFICATION ELECTRICAL (150-EC-FMB-EL-002) | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-002 | 150 | FMB | EL |  | 6 | 2019-11-30 | 2019-12-06 | 1398/09/09 | 1398/09/15
23S3-PC-150-EL-240 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-002 | 150 | FMB | EL | Electrical Cable Check and continuity megger test | 1 | 2019-11-30 | 2019-12-01 | 1398/09/09 | 1398/09/10
23S3-PC-150-EL-250 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-002 | 150 | FMB | EL | motor continuity megger test | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-150-EL-260 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-002 | 150 | FMB | EL | gland and connection final inspection | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-150-EL-270 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-002 | 150 | FMB | EL | LCS final function test | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-150-EL-280 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-002 | 150 | FMB | EL | feeder final checking | 1 | 2019-12-04 | 2019-12-05 | 1398/09/13 | 1398/09/14
23S3-PC-150-EL-290 | 23S3-ECC-FMB-001 | 150-EC-FMB-EL-002 | 150 | FMB | EL | motor free run test | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
FEED MATERIAL CONVEYING AND BLENDING MODIFICATION INSTRUMENTATION (150-EC-FMB-IN-001) | 23S3-ECC-FMB-001 | 150-EC-FMB-IN-001 | 150 | FMB | IN |  | 8 | 2019-11-30 | 2019-12-08 | 1398/09/09 | 1398/09/17
23S3-PC-150-IN-100 | 23S3-ECC-FMB-001 | 150-EC-FMB-IN-001 | 150 | FMB | IN | Instrument Cable Check and continuity megger test | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
23S3-PC-150-IN-110 | 23S3-ECC-FMB-001 | 150-EC-FMB-IN-001 | 150 | FMB | IN | device calibration | 3 | 2019-12-01 | 2019-12-04 | 1398/09/10 | 1398/09/13
23S3-PC-150-IN-120 | 23S3-ECC-FMB-001 | 150-EC-FMB-IN-001 | 150 | FMB | IN | device installation final check and punch clearance | 3 | 2019-12-03 | 2019-12-06 | 1398/09/12 | 1398/09/15
23S3-PC-150-IN-130 | 23S3-ECC-FMB-001 | 150-EC-FMB-IN-001 | 150 | FMB | IN | IO and loop checking | 2 | 2019-12-05 | 2019-12-07 | 1398/09/14 | 1398/09/16
23S3-PC-150-IN-140 | 23S3-ECC-FMB-001 | 150-EC-FMB-IN-001 | 150 | FMB | IN | function test | 1 | 2019-12-07 | 2019-12-08 | 1398/09/16 | 1398/09/17
FEED MATERIAL CONVEYING AND BLENDING MODIFICATION MECHANICAL (150-EC-FMB-ME-001) | 23S3-ECC-FMB-001 | 150-EC-FMB-ME-001 | 150 | FMB | ME |  | 4 | 2019-11-30 | 2019-12-04 | 1398/09/09 | 1398/09/13
23S3-PC-150-ME-130 | 23S3-ECC-FMB-001 | 150-EC-FMB-ME-001 | 150 | FMB | ME | check for pre box-up and punch clearance | 2 | 2019-11-30 | 2019-12-02 | 1398/09/09 | 1398/09/11
23S3-PC-150-ME-140 | 23S3-ECC-FMB-001 | 150-EC-FMB-ME-001 | 150 | FMB | ME | final boxup | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
FEED MATERIAL CONVEYING AND BLENDING MODIFICATION MECHANICAL (150-EC-FMB-ME-002) | 23S3-ECC-FMB-001 | 150-EC-FMB-ME-002 | 150 | FMB | ME |  | 9 | 2019-11-30 | 2019-12-09 | 1398/09/09 | 1398/09/18
23S3-PC-150-ME-150 | 23S3-ECC-FMB-001 | 150-EC-FMB-ME-002 | 150 | FMB | ME | motor and conveyer installation final check and punch clearance | 5 | 2019-11-30 | 2019-12-05 | 1398/09/09 | 1398/09/14
23S3-PC-150-ME-160 | 23S3-ECC-FMB-001 | 150-EC-FMB-ME-002 | 150 | FMB | ME | belt and other accessories adjustment final check and punch clearance | 5 | 2019-12-02 | 2019-12-07 | 1398/09/11 | 1398/09/16
23S3-PC-150-ME-170 | 23S3-ECC-FMB-001 | 150-EC-FMB-ME-002 | 150 | FMB | ME | Coupling the motor and no load run test | 3 | 2019-12-06 | 2019-12-09 | 1398/09/15 | 1398/09/18
150-Concentrate Blending (23S3-ECC-FMS-002) | 23S3-ECC-FMS-002 |  | 150 | FMS |  |  | 11 | 2019-12-01 | 2019-12-12 | 1398/09/10 | 1398/09/21
FEED MATERIAL CONVEYING AND BLENDING MODIFICATION ELECTRICAL (150-EC-FMS-EL-001) | 23S3-ECC-FMS-002 | 150-EC-FMS-EL-001 | 150 | FMS | EL |  | 6 | 2019-12-01 | 2019-12-07 | 1398/09/10 | 1398/09/16
23S3-PC-150-EL-300 | 23S3-ECC-FMS-002 | 150-EC-FMS-EL-001 | 150 | FMS | EL | Electrical Cable Check and continuity megger test | 2 | 2019-12-01 | 2019-12-03 | 1398/09/10 | 1398/09/12
23S3-PC-150-EL-310 | 23S3-ECC-FMS-002 | 150-EC-FMS-EL-001 | 150 | FMS | EL | motor continuity megger test | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
23S3-PC-150-EL-320 | 23S3-ECC-FMS-002 | 150-EC-FMS-EL-001 | 150 | FMS | EL | gland and connection final inspection | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-150-EL-330 | 23S3-ECC-FMS-002 | 150-EC-FMS-EL-001 | 150 | FMS | EL | LCS final function test | 2 | 2019-12-03 | 2019-12-05 | 1398/09/12 | 1398/09/14
23S3-PC-150-EL-340 | 23S3-ECC-FMS-002 | 150-EC-FMS-EL-001 | 150 | FMS | EL | feeder final checking | 2 | 2019-12-04 | 2019-12-06 | 1398/09/13 | 1398/09/15
23S3-PC-150-EL-350 | 23S3-ECC-FMS-002 | 150-EC-FMS-EL-001 | 150 | FMS | EL | motor free run test | 2 | 2019-12-05 | 2019-12-07 | 1398/09/14 | 1398/09/16
FEED MATERIAL CONVEYING AND BLENDING MODIFICATION INSTRUMENTATION (150-EC-FMS-IN-001) | 23S3-ECC-FMS-002 | 150-EC-FMS-IN-001 | 150 | FMS | IN |  | 11 | 2019-12-01 | 2019-12-12 | 1398/09/10 | 1398/09/21
23S3-PC-150-IN-150 | 23S3-ECC-FMS-002 | 150-EC-FMS-IN-001 | 150 | FMS | IN | Instrument Cable Check and continuity megger test | 2 | 2019-12-01 | 2019-12-03 | 1398/09/10 | 1398/09/12
23S3-PC-150-IN-160 | 23S3-ECC-FMS-002 | 150-EC-FMS-IN-001 | 150 | FMS | IN | device calibration | 3 | 2019-12-03 | 2019-12-06 | 1398/09/12 | 1398/09/15
23S3-PC-150-IN-170 | 23S3-ECC-FMS-002 | 150-EC-FMS-IN-001 | 150 | FMS | IN | device installation final check and punch clearance | 3 | 2019-12-06 | 2019-12-09 | 1398/09/15 | 1398/09/18
23S3-PC-150-IN-180 | 23S3-ECC-FMS-002 | 150-EC-FMS-IN-001 | 150 | FMS | IN | IO and loop checking | 2 | 2019-12-09 | 2019-12-11 | 1398/09/18 | 1398/09/20
23S3-PC-150-IN-190 | 23S3-ECC-FMS-002 | 150-EC-FMS-IN-001 | 150 | FMS | IN | function test | 1 | 2019-12-11 | 2019-12-12 | 1398/09/20 | 1398/09/21
FEED MATERIAL CONVEYING AND BLENDING MODIFICATION MACHINERY (150-EC-FMS-ME-001) | 23S3-ECC-FMS-002 | 150-EC-FMS-ME-001 | 150 | FMS | ME |  | 4 | 2019-12-01 | 2019-12-05 | 1398/09/10 | 1398/09/14
23S3-PC-150-ME-200 | 23S3-ECC-FMS-002 | 150-EC-FMS-ME-001 | 150 | FMS | ME | motor and conveyer installation final check and punch clearance | 3 | 2019-12-01 | 2019-12-04 | 1398/09/10 | 1398/09/13
23S3-PC-150-ME-210 | 23S3-ECC-FMS-002 | 150-EC-FMS-ME-001 | 150 | FMS | ME | belt and other accessories adjustment final check and punch clearance | 3 | 2019-12-01 | 2019-12-04 | 1398/09/10 | 1398/09/13
23S3-PC-150-ME-220 | 23S3-ECC-FMS-002 | 150-EC-FMS-ME-001 | 150 | FMS | ME | Coupling the motor and no load run test | 2 | 2019-12-03 | 2019-12-05 | 1398/09/12 | 1398/09/14
255-PS-DUST CONVEING (23S3-ECC-PSD-006) | 23S3-ECC-PSD-006 |  | 255 | PSD |  |  | 10 | 2019-12-01 | 2019-12-11 | 1398/09/10 | 1398/09/20
PS-DUST CONVEING ELECTRICAL SYSTEM (255-EC-PSD-EL-001) | 23S3-ECC-PSD-006 | 255-EC-PSD-EL-001 | 255 | PSD | EL |  | 7 | 2019-12-02 | 2019-12-09 | 1398/09/11 | 1398/09/18
23S3-PC-255-EL-100 | 23S3-ECC-PSD-006 | 255-EC-PSD-EL-001 | 255 | PSD | EL | Electrical Cable Check and continuity megger test | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-255-EL-110 | 23S3-ECC-PSD-006 | 255-EC-PSD-EL-001 | 255 | PSD | EL | motor continuity megger test | 1 | 2019-12-03 | 2019-12-04 | 1398/09/12 | 1398/09/13
23S3-PC-255-EL-120 | 23S3-ECC-PSD-006 | 255-EC-PSD-EL-001 | 255 | PSD | EL | gland and connection final inspection | 1 | 2019-12-04 | 2019-12-05 | 1398/09/13 | 1398/09/14
23S3-PC-255-EL-130 | 23S3-ECC-PSD-006 | 255-EC-PSD-EL-001 | 255 | PSD | EL | LCS final function test | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
23S3-PC-255-EL-140 | 23S3-ECC-PSD-006 | 255-EC-PSD-EL-001 | 255 | PSD | EL | feeder final checking | 1 | 2019-12-06 | 2019-12-07 | 1398/09/15 | 1398/09/16
23S3-PC-255-EL-150 | 23S3-ECC-PSD-006 | 255-EC-PSD-EL-001 | 255 | PSD | EL | motor free run test | 2 | 2019-12-07 | 2019-12-09 | 1398/09/16 | 1398/09/18
PS-DUST CONVEING INSTRUMENTATION (255-EC-PSD-IN-001) | 23S3-ECC-PSD-006 | 255-EC-PSD-IN-001 | 255 | PSD | IN |  | 6 | 2019-12-01 | 2019-12-07 | 1398/09/10 | 1398/09/16
23S3-PC-255-IN-100 | 23S3-ECC-PSD-006 | 255-EC-PSD-IN-001 | 255 | PSD | IN | Instrument Cable Check and continuity megger test | 1 | 2019-12-01 | 2019-12-02 | 1398/09/10 | 1398/09/11
23S3-PC-255-IN-110 | 23S3-ECC-PSD-006 | 255-EC-PSD-IN-001 | 255 | PSD | IN | device calibration | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-255-IN-120 | 23S3-ECC-PSD-006 | 255-EC-PSD-IN-001 | 255 | PSD | IN | device installation final check and punch clearance | 2 | 2019-12-03 | 2019-12-05 | 1398/09/12 | 1398/09/14
23S3-PC-255-IN-130 | 23S3-ECC-PSD-006 | 255-EC-PSD-IN-001 | 255 | PSD | IN | IO and loop checking | 2 | 2019-12-04 | 2019-12-06 | 1398/09/13 | 1398/09/15
23S3-PC-255-IN-140 | 23S3-ECC-PSD-006 | 255-EC-PSD-IN-001 | 255 | PSD | IN | function test | 1 | 2019-12-06 | 2019-12-07 | 1398/09/15 | 1398/09/16
PS-DUST CONVEING MECHANICAL (255-EC-PSD-ME-001) | 23S3-ECC-PSD-006 | 255-EC-PSD-ME-001 | 255 | PSD | ME |  | 9 | 2019-12-02 | 2019-12-11 | 1398/09/11 | 1398/09/20
23S3-PC-255-ME-100 | 23S3-ECC-PSD-006 | 255-EC-PSD-ME-001 | 255 | PSD | ME | belt and other accessories adjustment final check and punch clearance | 1 | 2019-12-02 | 2019-12-03 | 1398/09/11 | 1398/09/12
23S3-PC-255-ME-110 | 23S3-ECC-PSD-006 | 255-EC-PSD-ME-001 | 255 | PSD | ME | Chain and other accessories adjustment final check and punch clearance | 2 | 2019-12-03 | 2019-12-05 | 1398/09/12 | 1398/09/14
23S3-PC-255-ME-120 | 23S3-ECC-PSD-006 | 255-EC-PSD-ME-001 | 255 | PSD | ME | Coupling the motor and no load run test | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
23S3-PC-255-ME-230 | 23S3-ECC-PSD-006 | 255-EC-PSD-ME-001 | 255 | PSD | ME | check for pre box-up and punch clearance | 3 | 2019-12-06 | 2019-12-09 | 1398/09/15 | 1398/09/18
23S3-PC-255-ME-270 | 23S3-ECC-PSD-006 | 255-EC-PSD-ME-001 | 255 | PSD | ME | Final Box-up | 2 | 2019-12-09 | 2019-12-11 | 1398/09/18 | 1398/09/20
PS-DUST PNEUMATIC CONVEING PIPING (255-EC-PSD-PI-001) | 23S3-ECC-PSD-006 | 255-EC-PSD-PI-001 | 255 | PSD | PI |  | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
23S3-PC-225-PI-110 | 23S3-ECC-PSD-006 | 255-EC-PSD-PI-001 | 255 | PSD | PI | Punch Clearance | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
225-ESP DUST COLLECTION SYSTEM (23S3-ECC-ESP-032) | 23S3-ECC-ESP-032 |  | 225 | ESP |  |  | 12 | 2019-12-02 | 2019-12-14 | 1398/09/11 | 1398/09/23
ESP Dust Collection Electrical system (225-EC-ESP-EL-001) | 23S3-ECC-ESP-032 | 225-EC-ESP-EL-001 | 225 | ESP | EL |  | 8 | 2019-12-02 | 2019-12-10 | 1398/09/11 | 1398/09/19
23S3-PC-225-EL-500 | 23S3-ECC-ESP-032 | 225-EC-ESP-EL-001 | 225 | ESP | EL | Electrical Cable Check and continuity megger test | 2 | 2019-12-02 | 2019-12-04 | 1398/09/11 | 1398/09/13
23S3-PC-225-EL-510 | 23S3-ECC-ESP-032 | 225-EC-ESP-EL-001 | 225 | ESP | EL | motor continuity megger test | 1 | 2019-12-04 | 2019-12-05 | 1398/09/13 | 1398/09/14
23S3-PC-225-EL-520 | 23S3-ECC-ESP-032 | 225-EC-ESP-EL-001 | 225 | ESP | EL | gland and connection final inspection | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
23S3-PC-225-EL-530 | 23S3-ECC-ESP-032 | 225-EC-ESP-EL-001 | 225 | ESP | EL | LCS final function test | 1 | 2019-12-06 | 2019-12-07 | 1398/09/15 | 1398/09/16
23S3-PC-225-EL-540 | 23S3-ECC-ESP-032 | 225-EC-ESP-EL-001 | 225 | ESP | EL | feeder final checking | 1 | 2019-12-07 | 2019-12-08 | 1398/09/16 | 1398/09/17
23S3-PC-225-EL-550 | 23S3-ECC-ESP-032 | 225-EC-ESP-EL-001 | 225 | ESP | EL | motor free run test | 3 | 2019-12-07 | 2019-12-10 | 1398/09/16 | 1398/09/19
ESP Dust Collection Mechanical system (225-EC-ESP-ME-001) | 23S3-ECC-ESP-032 | 225-EC-ESP-ME-001 | 225 | ESP | ME |  | 11 | 2019-12-03 | 2019-12-14 | 1398/09/12 | 1398/09/23
23S3-PC-255-ME-130 | 23S3-ECC-ESP-032 | 225-EC-ESP-ME-001 | 225 | ESP | ME | Motor & Conveyor Installation Final Check and Punch Clearance | 2 | 2019-12-03 | 2019-12-05 | 1398/09/12 | 1398/09/14
23S3-PC-255-ME-140 | 23S3-ECC-ESP-032 | 225-EC-ESP-ME-001 | 225 | ESP | ME | Motor & Crusher Installation Final Check and Punch Clearance | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
23S3-PC-255-ME-160 | 23S3-ECC-ESP-032 | 225-EC-ESP-ME-001 | 225 | ESP | ME | Air Lock Feeder Installation Final Check and Punch Clearance | 1 | 2019-12-06 | 2019-12-07 | 1398/09/15 | 1398/09/16
23S3-PC-255-ME-170 | 23S3-ECC-ESP-032 | 225-EC-ESP-ME-001 | 225 | ESP | ME | Flange Parallel Check and adjastment | 3 | 2019-12-06 | 2019-12-09 | 1398/09/15 | 1398/09/18
23S3-PC-255-ME-180 | 23S3-ECC-ESP-032 | 225-EC-ESP-ME-001 | 225 | ESP | ME | duct work final check and punch clearance | 5 | 2019-12-07 | 2019-12-12 | 1398/09/16 | 1398/09/21
23S3-PC-255-ME-190 | 23S3-ECC-ESP-032 | 225-EC-ESP-ME-001 | 225 | ESP | ME | Coupling pump and fan / load run test | 4 | 2019-12-10 | 2019-12-14 | 1398/09/19 | 1398/09/23
225-ESP DUST CONVEYING SYSTEM (23S3-ECC-DUC-033) | 23S3-ECC-DUC-033 |  | 225 | DUC |  |  | 7 | 2019-12-04 | 2019-12-11 | 1398/09/13 | 1398/09/20
ESP Dust Conveying Instrument System (225-DUC-IN-001) | 23S3-ECC-DUC-033 | 225-DUC-IN-001 | 225 | DUC | IN |  | 5 | 2019-12-04 | 2019-12-09 | 1398/09/13 | 1398/09/18
23S3-PC-255-IN-200 | 23S3-ECC-DUC-033 | 225-DUC-IN-001 | 225 | DUC | IN | Instrument Cable Check and continuity megger test | 1 | 2019-12-04 | 2019-12-05 | 1398/09/13 | 1398/09/14
23S3-PC-255-IN-210 | 23S3-ECC-DUC-033 | 225-DUC-IN-001 | 225 | DUC | IN | device calibration | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
23S3-PC-255-IN-220 | 23S3-ECC-DUC-033 | 225-DUC-IN-001 | 225 | DUC | IN | device installation final check and punch clearance | 1 | 2019-12-06 | 2019-12-07 | 1398/09/15 | 1398/09/16
23S3-PC-255-IN-230 | 23S3-ECC-DUC-033 | 225-DUC-IN-001 | 225 | DUC | IN | IO and loop checking | 1 | 2019-12-07 | 2019-12-08 | 1398/09/16 | 1398/09/17
23S3-PC-255-IN-240 | 23S3-ECC-DUC-033 | 225-DUC-IN-001 | 225 | DUC | IN | function test | 1 | 2019-12-08 | 2019-12-09 | 1398/09/17 | 1398/09/18
ESP Dust Conveying Mechanical System (225-DUC-ME-001) | 23S3-ECC-DUC-033 | 225-DUC-ME-001 | 225 | DUC | ME |  | 6 | 2019-12-05 | 2019-12-11 | 1398/09/14 | 1398/09/20
23S3-PC-255-ME-200 | 23S3-ECC-DUC-033 | 225-DUC-ME-001 | 225 | DUC | ME | duct work final check and punch clearance | 3 | 2019-12-05 | 2019-12-08 | 1398/09/14 | 1398/09/17
23S3-PC-255-ME-210 | 23S3-ECC-DUC-033 | 225-DUC-ME-001 | 225 | DUC | ME | check for pre box-up and punch clearance | 2 | 2019-12-08 | 2019-12-10 | 1398/09/17 | 1398/09/19
23S3-PC-255-ME-220 | 23S3-ECC-DUC-033 | 225-DUC-ME-001 | 225 | DUC | ME | Final Box-up | 1 | 2019-12-10 | 2019-12-11 | 1398/09/19 | 1398/09/20
ESP Dust Conveying Mechanical System (225-DUC-ME-002) | 23S3-ECC-DUC-033 | 225-DUC-ME-002 | 225 | DUC | ME |  | 6 | 2019-12-04 | 2019-12-10 | 1398/09/13 | 1398/09/19
23S3-PC-255-ME-240 | 23S3-ECC-DUC-033 | 225-DUC-ME-002 | 225 | DUC | ME | duct work final check and punch clearance | 3 | 2019-12-04 | 2019-12-07 | 1398/09/13 | 1398/09/16
23S3-PC-255-ME-250 | 23S3-ECC-DUC-033 | 225-DUC-ME-002 | 225 | DUC | ME | check for pre box-up and punch clearance | 2 | 2019-12-07 | 2019-12-09 | 1398/09/16 | 1398/09/18
23S3-PC-255-ME-260 | 23S3-ECC-DUC-033 | 225-DUC-ME-002 | 225 | DUC | ME | Final Box-up | 1 | 2019-12-09 | 2019-12-10 | 1398/09/18 | 1398/09/19
ESP Dust Conveying Piping System (225-DUC-PI-001) | 23S3-ECC-DUC-033 | 225-DUC-PI-001 | 225 | DUC | PI |  | 2 | 2019-12-04 | 2019-12-06 | 1398/09/13 | 1398/09/15
23S3-PC-225-PI-120 | 23S3-ECC-DUC-033 | 225-DUC-PI-001 | 225 | DUC | PI | Punch Clearance | 2 | 2019-12-04 | 2019-12-06 | 1398/09/13 | 1398/09/15
225-FSF SULPHATATION SYSTEM (23S3-ECC-SUL-031) | 23S3-ECC-SUL-031 |  | 225 | SUL |  |  | 5 | 2019-12-05 | 2019-12-10 | 1398/09/14 | 1398/09/19
FSF Sulphatation Instrument System (225-EC-SUL-IN-001) | 23S3-ECC-SUL-031 | 225-EC-SUL-IN-001 | 225 | SUL | IN |  | 5 | 2019-12-05 | 2019-12-10 | 1398/09/14 | 1398/09/19
23S3-PC-255-IN-250 | 23S3-ECC-SUL-031 | 225-EC-SUL-IN-001 | 225 | SUL | IN | Instrument Cable Check and continuity megger test | 1 | 2019-12-05 | 2019-12-06 | 1398/09/14 | 1398/09/15
23S3-PC-255-IN-260 | 23S3-ECC-SUL-031 | 225-EC-SUL-IN-001 | 225 | SUL | IN | device calibration | 1 | 2019-12-06 | 2019-12-07 | 1398/09/15 | 1398/09/16
23S3-PC-255-IN-270 | 23S3-ECC-SUL-031 | 225-EC-SUL-IN-001 | 225 | SUL | IN | device installation final check and punch clearance | 1 | 2019-12-07 | 2019-12-08 | 1398/09/16 | 1398/09/17
23S3-PC-255-IN-280 | 23S3-ECC-SUL-031 | 225-EC-SUL-IN-001 | 225 | SUL | IN | IO and loop checking | 1 | 2019-12-08 | 2019-12-09 | 1398/09/17 | 1398/09/18
23S3-PC-255-IN-290 | 23S3-ECC-SUL-031 | 225-EC-SUL-IN-001 | 225 | SUL | IN | function test | 1 | 2019-12-09 | 2019-12-10 | 1398/09/18 | 1398/09/19
FSF Sulphatation Mechanical System (225-EC-SUL-ME-001) | 23S3-ECC-SUL-031 | 225-EC-SUL-ME-001 | 225 | SUL | ME |  | 3 | 2019-12-05 | 2019-12-08 | 1398/09/14 | 1398/09/17
23S3-PC-255-ME-280 | 23S3-ECC-SUL-031 | 225-EC-SUL-ME-001 | 225 | SUL | ME | duct work final check and punch clearance | 3 | 2019-12-05 | 2019-12-08 | 1398/09/14 | 1398/09/17
230-HIGH PRESSURE OXYGEN TO SLAG TAPHOLES (23S3-ECC-OXG-036) | 23S3-ECC-OXG-036 |  | 230 | OXG |  |  | 7 | 2019-12-06 | 2019-12-13 | 1398/09/15 | 1398/09/22
HIGH PRESSURE OXYGEN TO SLAG TAPHOLES PIPING SYSTEM (230-EC-OXG-PI-001) | 23S3-ECC-OXG-036 | 230-EC-OXG-PI-001 | 230 | OXG | PI |  | 7 | 2019-12-06 | 2019-12-13 | 1398/09/15 | 1398/09/22
23S3-PC-230-PI-100 | 23S3-ECC-OXG-036 | 230-EC-OXG-PI-001 | 230 | OXG | PI | Punch Clearance | 2 | 2019-12-06 | 2019-12-08 | 1398/09/15 | 1398/09/17
23S3-PC-230-PI-110 | 23S3-ECC-OXG-036 | 230-EC-OXG-PI-001 | 230 | OXG | PI | Chemical Cleaning | 5 | 2019-12-08 | 2019-12-13 | 1398/09/17 | 1398/09/22
250-OXYGEN DISTRIBUTION SYSTEM (23S3-ECC-OXE-005) | 23S3-ECC-OXE-005 |  | 250 | OXE |  |  | 5 | 2019-12-08 | 2019-12-13 | 1398/09/17 | 1398/09/22
OXYGEN DISTRIBUTION INSTRUMENTATION SYSTEM (250-EC-OXE-IN-001) | 23S3-ECC-OXE-005 | 250-EC-OXE-IN-001 | 250 | OXE | IN |  | 5 | 2019-12-08 | 2019-12-13 | 1398/09/17 | 1398/09/22
23S3-PC-250-IN-100 | 23S3-ECC-OXE-005 | 250-EC-OXE-IN-001 | 250 | OXE | IN | Instrument Cable Check and continuity megger test | 1 | 2019-12-08 | 2019-12-09 | 1398/09/17 | 1398/09/18
23S3-PC-250-IN-110 | 23S3-ECC-OXE-005 | 250-EC-OXE-IN-001 | 250 | OXE | IN | device calibration | 1 | 2019-12-09 | 2019-12-10 | 1398/09/18 | 1398/09/19
23S3-PC-250-IN-120 | 23S3-ECC-OXE-005 | 250-EC-OXE-IN-001 | 250 | OXE | IN | device installation final check and punch clearance | 1 | 2019-12-10 | 2019-12-11 | 1398/09/19 | 1398/09/20
23S3-PC-250-IN-130 | 23S3-ECC-OXE-005 | 250-EC-OXE-IN-001 | 250 | OXE | IN | IO and loop checking | 1 | 2019-12-11 | 2019-12-12 | 1398/09/20 | 1398/09/21
23S3-PC-250-IN-140 | 23S3-ECC-OXE-005 | 250-EC-OXE-IN-001 | 250 | OXE | IN | function test | 1 | 2019-12-12 | 2019-12-13 | 1398/09/21 | 1398/09/22
OXYGEN DISTRIBUTION SYSTEM DUCT WORK (250-EC-OXE-ME-001) | 23S3-ECC-OXE-005 | 250-EC-OXE-ME-001 | 250 | OXE | ME |  | 4 | 2019-12-09 | 2019-12-13 | 1398/09/18 | 1398/09/22
23S3-PC-250-ME-100 | 23S3-ECC-OXE-005 | 250-EC-OXE-ME-001 | 250 | OXE | ME | duct work final check and punch clearance | 3 | 2019-12-09 | 2019-12-12 | 1398/09/18 | 1398/09/21
23S3-PC-250-ME-120 | 23S3-ECC-OXE-005 | 250-EC-OXE-ME-001 | 250 | OXE | ME | Final Box-up | 1 | 2019-12-12 | 2019-12-13 | 1398/09/21 | 1398/09/22
OXYGEN DISTRIBUTION PIPING SYSTEM (250-EC-OXE-PI-001) | 23S3-ECC-OXE-005 | 250-EC-OXE-PI-001 | 250 | OXE | PI |  | 4 | 2019-12-09 | 2019-12-13 | 1398/09/18 | 1398/09/22
23S3-PC-250-PI-100 | 23S3-ECC-OXE-005 | 250-EC-OXE-PI-001 | 250 | OXE | PI | Punch Clearance | 2 | 2019-12-09 | 2019-12-11 | 1398/09/18 | 1398/09/20
23S3-PC-250-PI-110 | 23S3-ECC-OXE-005 | 250-EC-OXE-PI-001 | 250 | OXE | PI | Chemical Cleaning | 2 | 2019-12-11 | 2019-12-13 | 1398/09/20 | 1398/09/22
230-VENTATION GAS HANDLING (23S3-ECC-VGH-004) | 23S3-ECC-VGH-004 |  | 230 | VGH |  |  | 9 | 2019-12-10 | 2019-12-19 | 1398/09/19 | 1398/09/28
VENTATION GAS HANDLING ELECTRICAL (230-EC-VGH-EL-001) | 23S3-ECC-VGH-004 | 230-EC-VGH-EL-001 | 230 | VGH | EL |  | 5 | 2019-12-10 | 2019-12-15 | 1398/09/19 | 1398/09/24
23S3-PC-230-EL-180 | 23S3-ECC-VGH-004 | 230-EC-VGH-EL-001 | 230 | VGH | EL | Electrical Cable Check and continuity megger test | 1 | 2019-12-10 | 2019-12-11 | 1398/09/19 | 1398/09/20
23S3-PC-230-EL-190 | 23S3-ECC-VGH-004 | 230-EC-VGH-EL-001 | 230 | VGH | EL | gland and connection final inspection | 1 | 2019-12-11 | 2019-12-12 | 1398/09/20 | 1398/09/21
23S3-PC-230-EL-200 | 23S3-ECC-VGH-004 | 230-EC-VGH-EL-001 | 230 | VGH | EL | motor continuity megger test | 1 | 2019-12-12 | 2019-12-13 | 1398/09/21 | 1398/09/22
23S3-PC-230-EL-210 | 23S3-ECC-VGH-004 | 230-EC-VGH-EL-001 | 230 | VGH | EL | feeder final checking | 1 | 2019-12-13 | 2019-12-14 | 1398/09/22 | 1398/09/23
23S3-PC-230-EL-220 | 23S3-ECC-VGH-004 | 230-EC-VGH-EL-001 | 230 | VGH | EL | motor load run test | 1 | 2019-12-14 | 2019-12-15 | 1398/09/23 | 1398/09/24
VENTILATION GAS HANDELING INSTRUMENTATION (230-EC-VGH-IN-001) | 23S3-ECC-VGH-004 | 230-EC-VGH-IN-001 | 230 | VGH | IN |  | 5 | 2019-12-11 | 2019-12-16 | 1398/09/20 | 1398/09/25
23S3-PC-230-IN-150 | 23S3-ECC-VGH-004 | 230-EC-VGH-IN-001 | 230 | VGH | IN | Instrument Cable Check and continuity megger test | 1 | 2019-12-11 | 2019-12-12 | 1398/09/20 | 1398/09/21
23S3-PC-230-IN-160 | 23S3-ECC-VGH-004 | 230-EC-VGH-IN-001 | 230 | VGH | IN | device calibration | 1 | 2019-12-12 | 2019-12-13 | 1398/09/21 | 1398/09/22
23S3-PC-230-IN-170 | 23S3-ECC-VGH-004 | 230-EC-VGH-IN-001 | 230 | VGH | IN | device installation final check and punch clearance | 1 | 2019-12-13 | 2019-12-14 | 1398/09/22 | 1398/09/23
23S3-PC-230-IN-180 | 23S3-ECC-VGH-004 | 230-EC-VGH-IN-001 | 230 | VGH | IN | IO and loop checking | 1 | 2019-12-14 | 2019-12-15 | 1398/09/23 | 1398/09/24
23S3-PC-230-IN-190 | 23S3-ECC-VGH-004 | 230-EC-VGH-IN-001 | 230 | VGH | IN | function test | 1 | 2019-12-15 | 2019-12-16 | 1398/09/24 | 1398/09/25
VENTILATION GAS HANDELING MACHINERY (230-EC-VGH-ME-001) | 23S3-ECC-VGH-004 | 230-EC-VGH-ME-001 | 230 | VGH | ME |  | 6 | 2019-12-13 | 2019-12-19 | 1398/09/22 | 1398/09/28
23S3-PC-230-ME-100 | 23S3-ECC-VGH-004 | 230-EC-VGH-ME-001 | 230 | VGH | ME | Motor installation final check and punch clearance | 2 | 2019-12-13 | 2019-12-15 | 1398/09/22 | 1398/09/24
23S3-PC-230-ME-110 | 23S3-ECC-VGH-004 | 230-EC-VGH-ME-001 | 230 | VGH | ME | Flange Parallel Check and adjastment | 2 | 2019-12-15 | 2019-12-17 | 1398/09/24 | 1398/09/26
23S3-PC-230-ME-120 | 23S3-ECC-VGH-004 | 230-EC-VGH-ME-001 | 230 | VGH | ME | Final Box-up | 2 | 2019-12-17 | 2019-12-19 | 1398/09/26 | 1398/09/28
VENTILATION GAS HANDELING MECHANICAL (230-EC-VGH-ME-002) | 23S3-ECC-VGH-004 | 230-EC-VGH-ME-002 | 230 | VGH | ME |  | 6 | 2019-12-13 | 2019-12-19 | 1398/09/22 | 1398/09/28
23S3-PC-230-ME-130 | 23S3-ECC-VGH-004 | 230-EC-VGH-ME-002 | 230 | VGH | ME | Check For Pre-Box up | 4 | 2019-12-13 | 2019-12-17 | 1398/09/22 | 1398/09/26
23S3-PC-230-ME-150 | 23S3-ECC-VGH-004 | 230-EC-VGH-ME-002 | 230 | VGH | ME | Final Box-up | 2 | 2019-12-17 | 2019-12-19 | 1398/09/26 | 1398/09/28
By Pass Damper Bridge Crain System (220-EC-CRN-047) | 220-EC-CRN-047 |  | 220 | CRN |  |  | 10 | 2019-12-18 | 2019-12-28 | 1398/09/27 | 1398/10/07
FSF CRANE ELECTRICAL SYSTEM (220-EC-BPD-EL-001) | 220-EC-CRN-047 | 220-EC-BPD-EL-001 | 220 | CRN | EL |  | 5 | 2019-12-23 | 2019-12-28 | 1398/10/02 | 1398/10/07
23S3-PC-220-EL-440 | 220-EC-CRN-047 | 220-EC-BPD-EL-001 | 220 | CRN | EL | Electrical Cable Check and continuity megger test | 1 | 2019-12-23 | 2019-12-24 | 1398/10/02 | 1398/10/03
23S3-PC-220-EL-450 | 220-EC-CRN-047 | 220-EC-BPD-EL-001 | 220 | CRN | EL | motor continuity megger test | 1 | 2019-12-24 | 2019-12-25 | 1398/10/03 | 1398/10/04
23S3-PC-220-EL-460 | 220-EC-CRN-047 | 220-EC-BPD-EL-001 | 220 | CRN | EL | gland and connection final inspection | 1 | 2019-12-25 | 2019-12-26 | 1398/10/04 | 1398/10/05
23S3-PC-220-EL-480 | 220-EC-CRN-047 | 220-EC-BPD-EL-001 | 220 | CRN | EL | feeder final checking | 1 | 2019-12-26 | 2019-12-27 | 1398/10/05 | 1398/10/06
23S3-PC-220-EL-490 | 220-EC-CRN-047 | 220-EC-BPD-EL-001 | 220 | CRN | EL | motor load run test | 1 | 2019-12-27 | 2019-12-28 | 1398/10/06 | 1398/10/07
FSF CRANE MECHANICAL SYSTEM (220-EC-BPD-ME-001) | 220-EC-CRN-047 | 220-EC-BPD-ME-001 | 220 | CRN | ME |  | 2 | 2019-12-18 | 2019-12-20 | 1398/09/27 | 1398/09/29
23S3-PC-220-ME-440 | 220-EC-CRN-047 | 220-EC-BPD-ME-001 | 220 | CRN | ME | final check and punch clearance | 1 | 2019-12-18 | 2019-12-19 | 1398/09/27 | 1398/09/28
23S3-PC-220-ME-450 | 220-EC-CRN-047 | 220-EC-BPD-ME-001 | 220 | CRN | ME | final boxup | 1 | 2019-12-19 | 2019-12-20 | 1398/09/28 | 1398/09/29